## Project #2 RDTE Pt Est Phased
POST Report
Time Phased Report for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit
Costs in BY2005 $M, 2000 iterations
Wednesday, 10 June 2009, 11:43 am
Time Phased Results for Point Estimate
Costs in BY2005 $M
| WBS | Total | 2010 | 2011 | 2012
ACE3430 | Project #2 RDT&E | 50.3466 | 17.249 | 18.9318 | 14.1659
ACE3471 | Contract Costs | 33.5002 | 11.6955 | 13.085 | 8.7198
ACE3431 | Prime Mission Product | 14.851 | 6.1563 | 5.4581 | 3.2366
ACE3472 | Hardware | 9.4129 | 4.6044 | 3.9139 | 0.89461
ACE3594 | Subsystem #1 HW | 6.5719 | 3.2147 | 2.7326 | 0.6246
ACE3569 | Subsystem #1 HW Labor | 2.7525 | 1.3464 | 1.1445 | 0.2616
ACE3570 | Subsystem #1 HW Material | 3.8193 | 1.8683 | 1.5881 | 0.363
ACE3595 | Subsystem #2 | 2.841 | 1.3897 | 1.1813 | 0.27002
ACE3592 | Subsystem #2 HW Labor | 2.202 | 1.0771 | 0.9156 | 0.20928
ACE3593 | Subsystem #2 HW Material | 0.63902 | 0.31258 | 0.26571 | 0.060733
ACE4087 | Software | 3.1727 | 1.552 | 1.3192 | 0.30154
ACE3440 | Subsystem #1 SW | 1.0983 | 0.53722 | 0.45666 | 0.10438
ACE4088 | Subsystem #2 SW | 0.8542 | 0.41784 | 0.35518 | 0.081184
ACE4089 | Subsystem #3 SW | 1.2203 | 0.59691 | 0.5074 | 0.11598
ACE3441 | Integration Assembly Test & Checkout | 2.2654 |  | 0.22494 | 2.0405
ACE3442 | Acquisition Support (SEPM, ST&E, DATA) | 13.5245 | 3.9465 | 5.6162 | 3.9618
ACE3444 | Training | 0.59404 | 0.24625 | 0.21832 | 0.12947
ACE3445 | Peculiar Support Equipment (PSE)
ACE3446 | Operational Site Activation | 0.94129 | 0.093275 | 0.39039 | 0.45763
ACE3449 | Developmental Spares [Covered in HW]
ACE3562 | Contractor Fee | 3.5893 | 1.2531 | 1.402 | 0.93426
ACE3451 | Government Costs | 16.8464 | 5.5535 | 5.8468 | 5.4461
ACE3452 | Program Office Support | 11.0365 | 3.6527 | 3.6819 | 3.7018
ACE3453 | MITRE | 2.7591 | 0.91318 | 0.92048 | 0.92546
ACE3455 | SCS | 1.3796 | 0.45659 | 0.46024 | 0.46273
ACE3456 | PASS | 2.7591 | 0.91318 | 0.92048 | 0.92546
ACE3457 | ETASS | 4.1387 | 1.3698 | 1.3807 | 1.3882
ACE3533 | MIT/LL Support | 0.52668 | 0.17836 | 0.17566 | 0.17266
ACE3458 | Travel | 0.26334 | 0.089178 | 0.087832 | 0.08633
ACE3459 | Government Test Support | 0.35576 | 0.035253 | 0.14755 | 0.17296
ACE3460 | Assessments (ESC 3%) | 1.3705 | 0.46953 | 0.51534 | 0.38561
ACE3461 | Withholds (SMC/SAF 7%) | 3.2937 | 1.1284 | 1.2385 | 0.92674
Note on A1: Version=1.3 Type=TimePhasedReport
Note on A4: culture=en-US Timestamp=6/10/2009 11:43:35 AM Heading=Time Phased Report for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit Cases="Sanitized ACE Example for Demos V1 08JUN2009.aceit,Point Estimate" RowFilter=All SelectedRows="ACE3430,Y" FirstYear=2009 LastYear=2013 TotalLocation=Beginning
Note on A11: Version=1.3 Type=Table Style=PhasedCaseTable Name=72A1-41CD-23AC-A611 Description=Time Phased Table Culture=en-US Timestamp=6/10/2009 11:43:35 AM Footprint=R12C4:R45C8 Locks=

## Project #2 RDTE Pareto
POST Report
Pareto Chart for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit
Funding in TY $M, 2000 iterations
Wednesday, 10 June 2009, 11:43 am
Pareto Chart
Ranked Total Results for Point Estimate
Funding in TY $M
| WBS | Point Estimate | % of Total
ACE3471 | Contract Costs | 38.113
ACE3442 | Acquisition Support (SEPM, ST&E, DATA) | 15.4088 | 40.43%
ACE3570 | Subsystem #1 HW Material | 4.3236 | 11.34%
ACE3562 | Contractor Fee | 4.0835 | 10.71%
ACE3569 | Subsystem #1 HW Labor | 3.1159 | 8.175%
ACE3441 | Integration Assembly Test & Checkout | 2.6197 | 6.873%
ACE3592 | Subsystem #2 HW Labor | 2.4927 | 6.54%
ACE4089 | Subsystem #3 SW | 1.3814 | 3.624%
Note on A1: Version=1.3 Type=ParetoChart
Note on A4: culture=en-US Timestamp=6/10/2009 11:43:55 AM Heading=Pareto Chart for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit ShowRowNumbers=False Cutoff=7 Inflation=ThenYear Cases="Sanitized ACE Example for Demos V1 08JUN2009.aceit,Point Estimate" SelectedRow=ACE3471,Contract Costs RowFilter=Cost, NonCost SelectedRows="ACE3695,Y","ACE4002,Y","ACE3250,Y","ACE3301,Y","ACE3308,Y","ACE3249,Y","ACE3247,Y","ACE3266,Y","ACE3264,Y","ACE3268,Y","ACE3270,Y","ACE3067,Y","ACE3066,Y","ACE3068,Y","ACE3075,Y","ACE3074,Y","ACE3076,Y","ACE3295,Y","ACE3297,Y","ACE3296,Y","ACE2881,Y","ACE2882,Y","ACE2883,Y","ACE2957,Y","ACE2958,Y","ACE2959,Y","ACE3048,Y","ACE3049,Y","ACE3050,Y","ACE3154,Y","ACE3155,Y","ACE3156,Y","ACE3102,Y","ACE3103,Y","ACE3104,Y","ACE3005,Y","ACE3006,Y","ACE3007,Y","ACE4136,Y","ACE4137,Y","ACE4138,Y","ACE4147,Y","ACE4148,Y","ACE4149,Y","ACE4153,Y","ACE4154,Y","ACE4155,Y","ACE4159,Y","ACE4160,Y","ACE4161,Y","ACE4165,Y","ACE4166,Y","ACE4167,Y","ACE4171,Y","ACE4172,Y","ACE4173,Y","ACE3787,Y","ACE3797,Y","ACE3807,Y","ACE3817,Y","ACE3827,Y","ACE3911,Y","ACE3916,Y","ACE3921,Y","ACE3926,Y","ACE3931,Y","FULL3600$,Y","ACE4090,Y","ACE3936,Y","ACE3236,Y","ACE3429,Y","ACE3172,Y","ACE4067,Y","ACE4066,Y","ACE4065,Y","ACE3495,Y","ACE3483,Y","ACE3596,Y","ACE3486,Y","ACE3496,Y","ACE3585,Y","ACE4084,Y","ACE3350,Y","ACE3360,Y","ACE3354,Y","ACE3356,Y","Monthly_Avg_Labor_Rate$,Y","ACE3362,Y","Proj1_IATCO%,Y","Proj1_Trg%,Y","Proj1_OSA%,Y","ACE4069,Y","ACE3576,Y","ACE3575,Y","ACE3574,Y","CSPU_FEE%,Y","ACE3598,Y","ACE2829,Y","ACE2830,Y","ACE2831,Y","ACE2832,Y","ACE2833,Y","ACE2835,Y","ACE2836,Y","ACE2846,Y","ACE2847,Y","ACE2848,Y","ACE2849,Y","ACE2850,Y","ACE2851,Y","ACE2852,Y","Proj1_SW_NoGrowth$,Y","SOFTWARE,Y","ACQ_SPT_CER$,Y","Adj_SE_dat,Y","Adj_SE_Proj1,Y","ACE3516,Y","ACE3523,Y","ACE3616,Y","ACE3625,Y","ACE3217,Y","CSWS_SPARE129$,Y","ACE3541,Y","MIT_LL$,Y","ACE3549,Y","ACE3538,Y","ACE3535,Y","ACE3527,Y","ACE3531,Y","ACE3530,Y","ACE3536,Y","ACE3528,Y" DisplayAs=Bars DisplayIn3d=False DisplayFilteredBy=True ColorScheme=Pastels
Note on A9: Version=1.3 Type=Chart Style=ParetoChart Name=6DA5-5745-7E41-2828 Description=Pareto Chart Culture=en-US Timestamp=6/10/2009 11:43:55 AM Footprint=R10C4:R39C8 Locks=Title.Visibility,Title.Text,Title.Font,Title.Border,Title.Interior,Series.Type,Series.Color,Series.Pattern,Series.Effects,Series.LineWeight,Series.LineStyle,Series.MarkerStyle,Series.MarkerSize,XAxis.TitleText,XAxis.TitleFormat,XAxis.Line,XAxis.Labels,XAxis.Font,XAxis.NumberFormat,XAxis.Spacing,XAxis.TickMarks,XAxis.GridLines,XAxis.Crossing,XAxis.MinimumScale,XAxis.MaximumScale,YAxis.TitleText,YAxis.TitleFormat,YAxis.Line,YAxis.Labels,YAxis.Font,YAxis.NumberFormat,YAxis.Units,YAxis.TickMarks,YAxis.GridLines,YAxis.Crossing,YAxis.MinimumScale,YAxis.MaximumScale,Legend.Visibility,Legend.Position,Legend.Size,Legend.Font,Legend.Border,Legend.Interior,PlotArea.Position,PlotArea.Size,PlotArea.Border,PlotArea.Interior,Walls.Border,Walls.Interior
Note on A44: Version=1.3 Type=Table Style=RankedTotalsTable Name=6DA7-B997-13A1-C5A9 Description=Ranked Totals Table Culture=en-US Timestamp=6/10/2009 11:43:55 AM Footprint=R45C4:R54C6 Locks=

## Project #2 RDTE Risk Stats
POST Report
RI$K Statistics Report for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit
Costs in BY2005 $M, 2000 iterations
Tuesday, 23 June 2009, 3:04 pm
RI$K Statistics in 5% intervals
Costs in BY2005 $M
| WBS | Point Estimate | Confidence | Mean | Std Dev | CV | 0% | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% | 65% | 70% | 75% | 80% | 85% | 90% | 95% | 100%
ACE3430 | Project #2 RDT&E | 50.3466 | 22.2% | 64.4976 | 19.3256 | 0.29963 | 26.8685 | 40.4081 | 43.9645 | 46.7954 | 49.3097 | 51.3932 | 53.1971 | 55.1049 | 56.782 | 58.4248 | 60.6847 | 62.9148 | 65.0666 | 67.7413 | 70.6215 | 73.7417 | 77.9477 | 82.5971 | 88.3731 | 101.7724 | 177.695
ACE3471 | Contract Costs | 33.5002 | 22.09% | 46.304 | 17.3996 | 0.37577 | 12.6773 | 25.0876 | 28.3362 | 30.5402 | 32.6775 | 34.4898 | 36.1422 | 37.553 | 39.2412 | 41.051 | 42.7159 | 44.592 | 46.5817 | 49.3665 | 51.6834 | 54.5023 | 58.0986 | 62.7129 | 67.6944 | 80.8827 | 151.1214
ACE3431 | Prime Mission Product | 14.851 | 21.84% | 21.3387 | 8.6998 | 0.4077 | 5.7399 | 10.8873 | 12.3948 | 13.5755 | 14.5412 | 15.4364 | 16.2103 | 16.9771 | 17.8042 | 18.514 | 19.377 | 20.4318 | 21.434 | 22.6318 | 23.8373 | 25.4969 | 27.1844 | 29.5302 | 32.6701 | 37.3955 | 81.6409
ACE3472 | Hardware | 9.4129 | 30.62% | 12.5853 | 5.6052 | 0.44538 | 2.5989 | 5.7716 | 6.8344 | 7.5835 | 8.2104 | 8.8156 | 9.3658 | 9.8856 | 10.3961 | 10.9199 | 11.3631 | 11.9684 | 12.6279 | 13.3639 | 14.2923 | 15.1203 | 16.1501 | 17.7062 | 19.6384 | 22.894 | 56.5581
ACE3594 | Subsystem #1 HW | 6.5719 | 38.62% | 8.7159 | 4.9984 | 0.57348 | 1.4005 | 3.2299 | 3.8622 | 4.3685 | 4.8272 | 5.3175 | 5.7902 | 6.2669 | 6.721 | 7.164 | 7.6344 | 8.0726 | 8.5745 | 9.1977 | 9.9472 | 10.7379 | 11.722 | 13.0168 | 14.8444 | 17.6168 | 51.9659
ACE3569 | Subsystem #1 HW Labor | 2.7525 | 46.79% | 3.9296 | 3.4959 | 0.88962 | 0.16748 | 0.7942 | 1.0957 | 1.3166 | 1.5586 | 1.7646 | 1.9342 | 2.1725 | 2.3801 | 2.6735 | 2.926 | 3.2471 | 3.6458 | 3.9981 | 4.3904 | 4.8547 | 5.6128 | 6.5731 | 7.9426 | 10.3769 | 49.2651
ACE3570 | Subsystem #1 HW Material | 3.8193 | 50.01% | 4.7862 | 3.607 | 0.75361 | 0.38662 | 1.2647 | 1.6146 | 1.9031 | 2.1702 | 2.4275 | 2.6866 | 2.9489 | 3.2206 | 3.5098 | 3.8187 | 4.1554 | 4.528 | 4.9488 | 5.4302 | 6.0091 | 6.7204 | 7.6607 | 9.0356 | 11.5346 | 40.3595
ACE3595 | Subsystem #2 | 2.841 | 38.05% | 3.8694 | 2.2945 | 0.59299 | 0.50668 | 1.4385 | 1.7617 | 1.968 | 2.1753 | 2.3741 | 2.546 | 2.7396 | 2.9291 | 3.1281 | 3.3333 | 3.5491 | 3.7558 | 4.0466 | 4.3082 | 4.6936 | 5.1711 | 5.7991 | 6.7021 | 8.2276 | 29.9331
ACE3592 | Subsystem #2 HW Labor | 2.202 | 45.59% | 2.7371 | 1.6547 | 0.60453 | 0.31695 | 0.93554 | 1.1612 | 1.3233 | 1.4666 | 1.6134 | 1.7296 | 1.8791 | 2.0346 | 2.1871 | 2.3479 | 2.5321 | 2.712 | 2.9066 | 3.1086 | 3.3718 | 3.7518 | 4.1901 | 4.7377 | 6.0311 | 21.0348
ACE3593 | Subsystem #2 HW Material | 0.63902 | 50.73% | 1.1323 | 1.6286 | 1.4383 | 0.012294 | 0.11224 | 0.16067 | 0.20242 | 0.25193 | 0.30139 | 0.35121 | 0.41299 | 0.47599 | 0.54226 | 0.62393 | 0.72879 | 0.83525 | 0.97807 | 1.151 | 1.3036 | 1.5819 | 1.9698 | 2.5513 | 3.7258 | 28.8676
ACE4087 | Software | 3.1727 | 32.75% | 4.9065 | 3.4874 | 0.71077 | 0.73301 | 1.6251 | 1.9959 | 2.2754 | 2.4972 | 2.7711 | 3.0213 | 3.2736 | 3.5154 | 3.7899 | 4.066 | 4.3167 | 4.61 | 4.9443 | 5.3585 | 5.8255 | 6.473 | 7.2694 | 8.767 | 11.3253 | 42.9115
ACE3440 | Subsystem #1 SW | 1.0983 | 47.55% | 1.6332 | 1.5964 | 0.97752 | 0.079531 | 0.29979 | 0.39808 | 0.49921 | 0.59102 | 0.67123 | 0.75755 | 0.84471 | 0.94087 | 1.0363 | 1.1437 | 1.2703 | 1.4165 | 1.5772 | 1.752 | 2.0057 | 2.3235 | 2.7202 | 3.339 | 4.7323 | 15.1814
ACE4088 | Subsystem #2 SW | 0.8542 | 46.98% | 1.1502 | 0.9004 | 0.7828 | 0.076093 | 0.28369 | 0.37336 | 0.44444 | 0.51715 | 0.56845 | 0.61834 | 0.6779 | 0.73963 | 0.8172 | 0.90028 | 0.996 | 1.1012 | 1.1869 | 1.3001 | 1.4423 | 1.6008 | 1.8543 | 2.1834 | 2.9243 | 10.5953
ACE4089 | Subsystem #3 SW | 1.2203 | 48.44% | 2.1231 | 2.7553 | 1.2978 | 0.038107 | 0.25267 | 0.36393 | 0.45584 | 0.55984 | 0.6669 | 0.76723 | 0.88175 | 0.99616 | 1.1361 | 1.284 | 1.4563 | 1.6664 | 1.8973 | 2.1525 | 2.5265 | 2.9775 | 3.6051 | 4.5791 | 6.6714 | 40.4779
ACE3441 | Integration Assembly Test & Checkout | 2.2654 | 36.55% | 3.8469 | 3.1539 | 0.81986 | 0.31639 | 0.89429 | 1.17 | 1.3814 | 1.603 | 1.787 | 1.9886 | 2.2096 | 2.4261 | 2.689 | 2.9392 | 3.2493 | 3.5898 | 3.8842 | 4.3689 | 4.8899 | 5.453 | 6.2581 | 7.5598 | 9.7778 | 26.8414
ACE3442 | Acquisition Support (SEPM, ST&E, DATA) | 13.5245 | 27.93% | 17.8867 | 6.9518 | 0.38866 | 4.7365 | 9.2438 | 10.5785 | 11.537 | 12.426 | 13.1938 | 13.8094 | 14.4699 | 15.1097 | 15.8011 | 16.5839 | 17.316 | 18.1877 | 18.981 | 20.0225 | 21.1412 | 22.4623 | 24.4604 | 26.779 | 31.0527 | 67.5169
ACE3444 | Training | 0.59404 | 24.25% | 0.85312 | 0.37441 | 0.43887 | 0.17957 | 0.40739 | 0.4704 | 0.51803 | 0.56775 | 0.59967 | 0.63753 | 0.66749 | 0.70524 | 0.73937 | 0.77529 | 0.81132 | 0.85602 | 0.90462 | 0.95533 | 1.0138 | 1.1048 | 1.1923 | 1.3269 | 1.5461 | 4.0304
ACE3445 | Peculiar Support Equipment (PSE)
ACE3446 | Operational Site Activation | 0.94129 | 33.91% | 1.2601 | 0.5997 | 0.47593 | 0.22991 | 0.55417 | 0.64636 | 0.71819 | 0.78276 | 0.84512 | 0.9002 | 0.9537 | 1.0159 | 1.0813 | 1.1448 | 1.2074 | 1.2824 | 1.3484 | 1.4377 | 1.527 | 1.656 | 1.8048 | 2.0098 | 2.3434 | 5.6771
ACE3449 | Developmental Spares [Covered in HW]
ACE3562 | Contractor Fee | 3.5893 | 25.52% | 4.9654 | 2.0535 | 0.41356 | 1.3548 | 2.5299 | 2.8793 | 3.105 | 3.3207 | 3.5684 | 3.7747 | 3.964 | 4.1763 | 4.3629 | 4.5446 | 4.7879 | 4.9946 | 5.2239 | 5.5221 | 5.8727 | 6.3135 | 6.7844 | 7.5521 | 8.9131 | 17.88
ACE3451 | Government Costs | 16.8464 | 34.63% | 18.1936 | 2.9345 | 0.1613 | 9.946 | 13.7607 | 14.6322 | 15.1864 | 15.6445 | 16.1293 | 16.474 | 16.8917 | 17.2618 | 17.5792 | 17.9773 | 18.378 | 18.7513 | 19.1477 | 19.5737 | 20.034 | 20.6315 | 21.2466 | 22.0109 | 23.2849 | 32.945
ACE3452 | Program Office Support | 11.0365 | 51.78% | 11.0282 | 2.1117 | 0.19148 | 4.8367 | 7.7787 | 8.3722 | 8.8015 | 9.1392 | 9.5051 | 9.8309 | 10.1445 | 10.4234 | 10.683 | 10.9451 | 11.2029 | 11.4556 | 11.7367 | 12.0293 | 12.3994 | 12.7549 | 13.321 | 13.8163 | 14.7268 | 17.9949
ACE3453 | MITRE | 2.7591 | 53.97% | 2.7563 | 0.986 | 0.35773 | 0.25312 | 1.291 | 1.5641 | 1.7346 | 1.9085 | 2.0564 | 2.2015 | 2.3142 | 2.4272 | 2.5484 | 2.6695 | 2.7818 | 2.9312 | 3.0844 | 3.2197 | 3.3679 | 3.5503 | 3.7685 | 4.0706 | 4.5094 | 8.2084
ACE3455 | SCS | 1.3796 | 54.42% | 1.377 | 0.49296 | 0.358 | 0.16428 | 0.65087 | 0.79916 | 0.88966 | 0.96771 | 1.0331 | 1.0968 | 1.1563 | 1.2023 | 1.2633 | 1.3173 | 1.3934 | 1.449 | 1.5157 | 1.586 | 1.664 | 1.7596 | 1.8886 | 2.0437 | 2.2772 | 4.2077
ACE3456 | PASS | 2.7591 | 53.7% | 2.7555 | 0.99122 | 0.35973 | 0.28348 | 1.3426 | 1.5799 | 1.7354 | 1.877 | 2.0305 | 2.159 | 2.2957 | 2.4193 | 2.5445 | 2.6682 | 2.7949 | 2.9364 | 3.0715 | 3.2238 | 3.3641 | 3.5397 | 3.737 | 4.0631 | 4.5527 | 6.9795
ACE3457 | ETASS | 4.1387 | 53.44% | 4.1394 | 1.4839 | 0.35848 | 0.47847 | 1.9167 | 2.3191 | 2.6009 | 2.8787 | 3.1158 | 3.2907 | 3.4698 | 3.6323 | 3.8086 | 4.0007 | 4.1921 | 4.3909 | 4.5896 | 4.8326 | 5.0792 | 5.3519 | 5.7037 | 6.1606 | 6.8278 | 10.0454
ACE3533 | MIT/LL Support | 0.52668 | 50% | 0.52669 | 0.13171 | 0.25006 | 0.050057 | 0.3099 | 0.35789 | 0.39022 | 0.41589 | 0.43788 | 0.45765 | 0.47588 | 0.4933 | 0.51011 | 0.52667 | 0.54322 | 0.55998 | 0.57747 | 0.59568 | 0.61555 | 0.6375 | 0.66306 | 0.69551 | 0.74334 | 1.0022
ACE3458 | Travel | 0.26334 | 49.98% | 0.26335 | 0.065861 | 0.25009 | 0.035235 | 0.15512 | 0.17903 | 0.19514 | 0.20797 | 0.21894 | 0.22882 | 0.23798 | 0.24665 | 0.25506 | 0.26337 | 0.27161 | 0.28 | 0.28871 | 0.29786 | 0.30773 | 0.31876 | 0.33153 | 0.34765 | 0.37162 | 0.50169
ACE3459 | Government Test Support | 0.35576 | 31.51% | 0.40023 | 0.079981 | 0.19984 | 0.23537 | 0.283 | 0.30404 | 0.31877 | 0.33241 | 0.34202 | 0.35123 | 0.36343 | 0.37406 | 0.38158 | 0.39008 | 0.40044 | 0.41251 | 0.42269 | 0.43435 | 0.44851 | 0.46556 | 0.48475 | 0.51032 | 0.54328 | 0.73845
ACE3460 | Assessments (ESC 3%) | 1.3705 | 22.2% | 1.7557 | 0.52606 | 0.29963 | 0.73138 | 1.0999 | 1.1967 | 1.2738 | 1.3422 | 1.399 | 1.4481 | 1.5 | 1.5456 | 1.5904 | 1.6519 | 1.7126 | 1.7712 | 1.844 | 1.9224 | 2.0073 | 2.1218 | 2.2484 | 2.4056 | 2.7703 | 4.837
ACE3461 | Withholds (SMC/SAF 7%) | 3.2937 | 22.2% | 4.2195 | 1.2643 | 0.29963 | 1.7577 | 2.6435 | 2.8762 | 3.0614 | 3.2259 | 3.3622 | 3.4802 | 3.605 | 3.7147 | 3.8222 | 3.97 | 4.1159 | 4.2567 | 4.4317 | 4.6201 | 4.8242 | 5.0994 | 5.4035 | 5.7814 | 6.658 | 11.6249
Note on A1: Version=1.3 Type=RiskReport
Note on A4: culture=en-US Timestamp=6/23/2009 3:04:40 PM Heading=RI$K Statistics Report for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit Cases="Sanitized ACE Example for Demos V1 08JUN2009.aceit,Point Estimate" RowFilter=All SelectedRows="ACE3430,Y"
Note on A11: Version=1.3 Type=Table Style=RiskStatisticsTable Name=372C-140D-37C2-1FD9 Description=RI$K Statistics Table Culture=en-US Timestamp=6/23/2009 3:04:40 PM Footprint=R12C4:R45C30 Locks=Cells.NumberFormat,Cells.FontStyle,Cells.FontSize,Cells.FontColor,Cells.InteriorColor,Cells.PatternColor,Cells.Pattern,Table.InsideBorders,Table.OutsideBorders

## Project #1 RDTE Time w Risk
POST Report
Time Phased Report for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit
Funding in TY $M, 2000 iterations
Wednesday, 10 June 2009, 11:43 am
Time Phased Results for Point Estimate
Funding in TY $M
| WBS | Total | 2006 | 2007 | 2008 | 2009 | 2010 | 2011
ACE3769 | *Risk Dollars Summaries - Project #1
ACE3781 | *50% Confidence
ACE3787 | RDT&E REQUIRED @ 50% CONFIDENCE | 106.6324 | 0.259 | 6.943 | 13.601 | 23.3164 | 26.4727 | 36.0403
ACE3788 | RDT&E POINT ESTIMATE | 95.0661 | 0.259 | 6.943 | 13.601 | 23.3164 | 20.1442 | 30.8025
ACE3789 | RDT&E RISK DOLLARS TO 50% CONF | 11.5664 |  |  |  |  | 6.3286 | 5.2378
ACE3790
ACE3791 | *Mean Confidence
ACE3797 | RDT&E REQUIRED @ Mean CONFIDENCE | 108.7441 | 0.259 | 6.943 | 13.601 | 23.3164 | 27.4533 | 37.1714
ACE3798 | RDT&E POINT ESTIMATE | 95.0661 | 0.259 | 6.943 | 13.601 | 23.3164 | 20.1442 | 30.8025
ACE3799 | RDT&E RISK DOLLARS TO Mean CONF | 13.678 |  |  |  |  | 7.3092 | 6.3689
ACE3800
ACE3801 | *60% Confidence
ACE3807 | RDT&E REQUIRED @ 60% CONFIDENCE | 111.0104 | 0.259 | 6.943 | 13.601 | 23.3164 | 28.4235 | 38.4675
ACE3808 | RDT&E POINT ESTIMATE | 95.0661 | 0.259 | 6.943 | 13.601 | 23.3164 | 20.1442 | 30.8025
ACE3809 | RDT&E RISK DOLLARS TO 60% CONF | 15.9443 |  |  |  |  | 8.2793 | 7.6649
ACE3810
ACE3811 | *70% Confidence
ACE3817 | RDT&E REQUIRED @ 70% CONFIDENCE | 116.3209 | 0.259 | 6.943 | 13.601 | 23.3164 | 30.3896 | 41.8119
ACE3818 | RDT&E POINT ESTIMATE | 95.0661 | 0.259 | 6.943 | 13.601 | 23.3164 | 20.1442 | 30.8025
ACE3819 | RDT&E RISK DOLLARS TO 70% CONF | 21.2548 |  |  |  |  | 10.2454 | 11.0094
ACE3820
ACE3821 | *80% Confidence
ACE3827 | RDT&E REQUIRED @ 80% CONFIDENCE | 121.9102 | 0.259 | 6.943 | 13.601 | 23.3164 | 32.0299 | 45.761
ACE3828 | RDT&E POINT ESTIMATE | 95.0661 | 0.259 | 6.943 | 13.601 | 23.3164 | 20.1442 | 30.8025
ACE3829 | RDT&E RISK DOLLARS TO 80% CONF | 26.8441 |  |  |  |  | 11.8857 | 14.9584
ACE3830
Note on A1: Version=1.3 Type=TimePhasedReport
Note on A4: culture=en-US Timestamp=6/10/2009 11:43:56 AM Heading=Time Phased Report for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit Inflation=ThenYear Cases="Sanitized ACE Example for Demos V1 08JUN2009.aceit,Point Estimate" RowFilter=All SelectedRows="ACE3769,Y","ACE3781,Y","ACE3787,Y","ACE3790,Y","ACE3791,Y","ACE3797,Y","ACE3800,Y","ACE3801,Y","ACE3807,Y","ACE3810,Y","ACE3811,Y","ACE3817,Y","ACE3820,Y","ACE3821,Y","ACE3827,Y","ACE3830,Y" FirstYear=2003 LastYear=2013 TotalLocation=Beginning
Note on A11: Version=1.3 Type=Table Style=PhasedCaseTable Name=3587-430D-4969-CE3C Description=Time Phased Table Culture=en-US Timestamp=6/10/2009 11:43:56 AM Footprint=R12C4:R39C11 Locks=Cells.NumberFormat,Cells.FontStyle,Cells.FontSize,Cells.FontColor,Cells.InteriorColor,Cells.PatternColor,Cells.Pattern,Table.InsideBorders,Table.OutsideBorders

## Project #2 RDTE Time w Risk
POST Report
Time Phased Report for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit
Funding in TY $M, 2000 iterations
Wednesday, 10 June 2009, 11:43 am
Time Phased Results for Point Estimate
Funding in TY $M
| WBS | Total | 2010 | 2011 | 2012
ACE3909 | *Risk Dollars Summaries - Project #2 (Constrained Schedule)
ACE3910 | *50% Confidence
ACE3911 | RDT&E REQUIRED @ 50% CONFIDENCE | 69.158 | 20.491 | 26.436 | 22.231
ACE3912 | RDT&E POINT ESTIMATE | 57.3057 | 19.3422 | 21.5545 | 16.409
ACE3913 | RDT&E RISK DOLLARS TO 50% CONF | 11.8523 | 1.1488 | 4.8815 | 5.822
ACE3914
ACE3915 | *Mean Confidence
ACE3916 | RDT&E REQUIRED @ Mean CONFIDENCE | 73.5293 | 20.9147 | 28.2364 | 24.3782
ACE3917 | RDT&E POINT ESTIMATE | 57.3057 | 19.3422 | 21.5545 | 16.409
ACE3918 | RDT&E RISK DOLLARS TO Mean CONF | 16.2235 | 1.5724 | 6.6819 | 7.9692
ACE3919
ACE3920 | *60% Confidence
ACE3921 | RDT&E REQUIRED @ 60% CONFIDENCE | 74.1816 | 20.9779 | 28.5051 | 24.6987
ACE3922 | RDT&E POINT ESTIMATE | 57.3057 | 19.3422 | 21.5545 | 16.409
ACE3923 | RDT&E RISK DOLLARS TO 60% CONF | 16.8759 | 1.6357 | 6.9506 | 8.2896
ACE3924
ACE3925 | *70% Confidence
ACE3926 | RDT&E REQUIRED @ 70% CONFIDENCE | 80.5501 | 21.5952 | 31.128 | 27.8269
ACE3927 | RDT&E POINT ESTIMATE | 57.3057 | 19.3422 | 21.5545 | 16.409
ACE3928 | RDT&E RISK DOLLARS TO 70% CONF | 23.2444 | 2.2529 | 9.5735 | 11.4179
ACE3929
ACE3930 | *80% Confidence
ACE3931 | RDT&E REQUIRED @ 80% CONFIDENCE | 88.9494 | 22.4092 | 34.5874 | 31.9527
ACE3932 | RDT&E POINT ESTIMATE | 57.3057 | 19.3422 | 21.5545 | 16.409
ACE3933 | RDT&E RISK DOLLARS TO 80% CONF | 31.6436 | 3.067 | 13.0329 | 15.5437
ACE3934
Note on A1: Version=1.3 Type=TimePhasedReport
Note on A4: culture=en-US Timestamp=6/10/2009 11:43:56 AM Heading=Time Phased Report for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit Inflation=ThenYear Cases="Sanitized ACE Example for Demos V1 08JUN2009.aceit,Point Estimate" RowFilter=All SelectedRows="ACE3909,Y","ACE3910,Y","ACE3911,Y","ACE3914,Y","ACE3915,Y","ACE3916,Y","ACE3919,Y","ACE3920,Y","ACE3921,Y","ACE3924,Y","ACE3925,Y","ACE3926,Y","ACE3929,Y","ACE3930,Y","ACE3931,Y","ACE3934,Y" FirstYear=2003 LastYear=2013 TotalLocation=Beginning
Note on A11: Version=1.3 Type=Table Style=PhasedCaseTable Name=3587-430D-4969-CE3C Description=Time Phased Table Culture=en-US Timestamp=6/10/2009 11:43:56 AM Footprint=R12C4:R39C8 Locks=Cells.NumberFormat,Cells.FontStyle,Cells.FontSize,Cells.FontColor,Cells.InteriorColor,Cells.PatternColor,Cells.Pattern,Table.InsideBorders,Table.OutsideBorders

## Project #2 Sand 50 Cstr
POST Report
Sand Chart for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit
Funding in TY $M, 2000 iterations
Wednesday, 10 June 2009, 11:43 am
Sand Chart
Time Phased Results for Point Estimate
Funding in TY $M
| WBS | 2010 | 2011 | 2012
ACE3911 | RDT&E REQUIRED @ 50% CONFIDENCE | 20.491 | 26.436 | 22.231
ACE3912 | RDT&E POINT ESTIMATE | 19.3422 | 21.5545 | 16.409
ACE3913 | RDT&E RISK DOLLARS TO 50% CONF | 1.1488 | 4.8815 | 5.822
Note on A1: Version=1.3 Type=SandChart
Note on A4: culture=en-US Timestamp=6/10/2009 11:43:56 AM Heading=Sand Chart for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit Inflation=ThenYear Cases="Sanitized ACE Example for Demos V1 08JUN2009.aceit,Point Estimate" SelectedRow=ACE3911,RDT&E REQUIRED @ 50% CONFIDENCE RowFilter=Cost, NonCost VisibilityLevel=2 SelectedRows="ACE3695,Y","ACE4002,Y","ACE3250,Y","ACE3301,Y","ACE3308,Y","ACE3249,Y","ACE3247,Y","ACE3266,Y","ACE3264,Y","ACE3268,Y","ACE3270,Y","ACE3067,Y","ACE3066,Y","ACE3068,Y","ACE3075,Y","ACE3074,Y","ACE3076,Y","ACE3295,Y","ACE3297,Y","ACE3296,Y","ACE2881,Y","ACE2882,Y","ACE2883,Y","ACE2957,Y","ACE2958,Y","ACE2959,Y","ACE3048,Y","ACE3049,Y","ACE3050,Y","ACE3154,Y","ACE3155,Y","ACE3156,Y","ACE3102,Y","ACE3103,Y","ACE3104,Y","ACE3005,Y","ACE3006,Y","ACE3007,Y","ACE4136,Y","ACE4137,Y","ACE4138,Y","ACE4147,Y","ACE4148,Y","ACE4149,Y","ACE4153,Y","ACE4154,Y","ACE4155,Y","ACE4159,Y","ACE4160,Y","ACE4161,Y","ACE4165,Y","ACE4166,Y","ACE4167,Y","ACE4171,Y","ACE4172,Y","ACE4173,Y","ACE3787,Y","ACE3797,Y","ACE3807,Y","ACE3817,Y","ACE3827,Y","ACE3911,Y","ACE3916,Y","ACE3921,Y","ACE3926,Y","ACE3931,Y","FULL3600$,Y","ACE4090,Y","ACE3936,Y","ACE3236,Y","ACE3429,Y","ACE3172,Y","ACE4067,Y","ACE4066,Y","ACE4065,Y","ACE3495,Y","ACE3483,Y","ACE3596,Y","ACE3486,Y","ACE3496,Y","ACE3585,Y","ACE4084,Y","ACE3350,Y","ACE3360,Y","ACE3354,Y","ACE3356,Y","Monthly_Avg_Labor_Rate$,Y","ACE3362,Y","Proj1_IATCO%,Y","Proj1_Trg%,Y","Proj1_OSA%,Y","ACE4069,Y","ACE3576,Y","ACE3575,Y","ACE3574,Y","CSPU_FEE%,Y","ACE3598,Y","ACE2829,Y","ACE2830,Y","ACE2831,Y","ACE2832,Y","ACE2833,Y","ACE2835,Y","ACE2836,Y","ACE2846,Y","ACE2847,Y","ACE2848,Y","ACE2849,Y","ACE2850,Y","ACE2851,Y","ACE2852,Y","Proj1_SW_NoGrowth$,Y","SOFTWARE,Y","ACQ_SPT_CER$,Y","Adj_SE_dat,Y","Adj_SE_Proj1,Y","ACE3516,Y","ACE3523,Y","ACE3616,Y","ACE3625,Y","ACE3217,Y","CSWS_SPARE129$,Y","ACE3541,Y","MIT_LL$,Y","ACE3549,Y","ACE3538,Y","ACE3535,Y","ACE3527,Y","ACE3531,Y","ACE3530,Y","ACE3536,Y","ACE3528,Y" FirstYear=2003 LastYear=2013 TotalLocation=None DisplayAs=Areas DisplayIn3d=False DisplayFilteredBy=True ColorScheme=Standard
Note on A9: Version=1.3 Type=Chart Style=SandChart Name=3773-73DA-41E2-E1B5 Description=Sand Chart Culture=en-US Timestamp=6/10/2009 11:43:56 AM Footprint=R10C4:R39C8 Locks=Title.Visibility,Title.Text,Title.Font,Title.Border,Title.Interior,Series.Type,Series.Color,Series.Pattern,Series.Effects,Series.LineWeight,Series.LineStyle,Series.MarkerStyle,Series.MarkerSize,XAxis.TitleText,XAxis.TitleFormat,XAxis.Line,XAxis.Labels,XAxis.Font,XAxis.NumberFormat,XAxis.Spacing,XAxis.TickMarks,XAxis.GridLines,XAxis.Crossing,XAxis.MinimumScale,XAxis.MaximumScale,YAxis.TitleText,YAxis.TitleFormat,YAxis.Line,YAxis.Labels,YAxis.Font,YAxis.NumberFormat,YAxis.Units,YAxis.TickMarks,YAxis.GridLines,YAxis.Crossing,YAxis.MinimumScale,YAxis.MaximumScale,Legend.Visibility,Legend.Position,Legend.Size,Legend.Font,Legend.Border,Legend.Interior,PlotArea.Position,PlotArea.Size,PlotArea.Border,PlotArea.Interior,Walls.Border,Walls.Interior
Note on A44: Version=1.3 Type=Table Style=PhasedCaseTable Name=3773-73DA-4D46-A03B Description=Time Phased Table Culture=en-US Timestamp=6/10/2009 11:43:56 AM Footprint=R45C4:R49C7 Locks=
Note on A50: Version=1.3 Type=Table Style=PhasedCaseTable Name=0BEA-844F-2E89-1710 Description=Time Phased Table Culture=en-US Timestamp=6/8/2009 2:25:16 PM Footprint=R53C4:R55C14 Locks=

## Project #2 Sand 80 Cstr
POST Report
Sand Chart for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit
Funding in TY $M, 2000 iterations
Wednesday, 10 June 2009, 11:43 am
Sand Chart
Time Phased Results for Point Estimate
Funding in TY $M
| WBS | 2010 | 2011 | 2012
ACE3931 | RDT&E REQUIRED @ 80% CONFIDENCE | 22.4092 | 34.5874 | 31.9527
ACE3932 | RDT&E POINT ESTIMATE | 19.3422 | 21.5545 | 16.409
ACE3933 | RDT&E RISK DOLLARS TO 80% CONF | 3.067 | 13.0329 | 15.5437
Note on A1: Version=1.3 Type=SandChart
Note on A4: culture=en-US Timestamp=6/10/2009 11:43:56 AM Heading=Sand Chart for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit Inflation=ThenYear Cases="Sanitized ACE Example for Demos V1 08JUN2009.aceit,Point Estimate" SelectedRow=ACE3931,RDT&E REQUIRED @ 80% CONFIDENCE RowFilter=Cost, NonCost VisibilityLevel=2 SelectedRows="ACE3695,Y","ACE4002,Y","ACE3250,Y","ACE3301,Y","ACE3308,Y","ACE3249,Y","ACE3247,Y","ACE3266,Y","ACE3264,Y","ACE3268,Y","ACE3270,Y","ACE3067,Y","ACE3066,Y","ACE3068,Y","ACE3075,Y","ACE3074,Y","ACE3076,Y","ACE3295,Y","ACE3297,Y","ACE3296,Y","ACE2881,Y","ACE2882,Y","ACE2883,Y","ACE2957,Y","ACE2958,Y","ACE2959,Y","ACE3048,Y","ACE3049,Y","ACE3050,Y","ACE3154,Y","ACE3155,Y","ACE3156,Y","ACE3102,Y","ACE3103,Y","ACE3104,Y","ACE3005,Y","ACE3006,Y","ACE3007,Y","ACE4136,Y","ACE4137,Y","ACE4138,Y","ACE4147,Y","ACE4148,Y","ACE4149,Y","ACE4153,Y","ACE4154,Y","ACE4155,Y","ACE4159,Y","ACE4160,Y","ACE4161,Y","ACE4165,Y","ACE4166,Y","ACE4167,Y","ACE4171,Y","ACE4172,Y","ACE4173,Y","ACE3787,Y","ACE3797,Y","ACE3807,Y","ACE3817,Y","ACE3827,Y","ACE3911,Y","ACE3916,Y","ACE3921,Y","ACE3926,Y","ACE3931,Y","FULL3600$,Y","ACE4090,Y","ACE3936,Y","ACE3236,Y","ACE3429,Y","ACE3172,Y","ACE4067,Y","ACE4066,Y","ACE4065,Y","ACE3495,Y","ACE3483,Y","ACE3596,Y","ACE3486,Y","ACE3496,Y","ACE3585,Y","ACE4084,Y","ACE3350,Y","ACE3360,Y","ACE3354,Y","ACE3356,Y","Monthly_Avg_Labor_Rate$,Y","ACE3362,Y","Proj1_IATCO%,Y","Proj1_Trg%,Y","Proj1_OSA%,Y","ACE4069,Y","ACE3576,Y","ACE3575,Y","ACE3574,Y","CSPU_FEE%,Y","ACE3598,Y","ACE2829,Y","ACE2830,Y","ACE2831,Y","ACE2832,Y","ACE2833,Y","ACE2835,Y","ACE2836,Y","ACE2846,Y","ACE2847,Y","ACE2848,Y","ACE2849,Y","ACE2850,Y","ACE2851,Y","ACE2852,Y","Proj1_SW_NoGrowth$,Y","SOFTWARE,Y","ACQ_SPT_CER$,Y","Adj_SE_dat,Y","Adj_SE_Proj1,Y","ACE3516,Y","ACE3523,Y","ACE3616,Y","ACE3625,Y","ACE3217,Y","CSWS_SPARE129$,Y","ACE3541,Y","MIT_LL$,Y","ACE3549,Y","ACE3538,Y","ACE3535,Y","ACE3527,Y","ACE3531,Y","ACE3530,Y","ACE3536,Y","ACE3528,Y" FirstYear=2003 LastYear=2013 TotalLocation=None DisplayAs=Areas DisplayIn3d=False DisplayFilteredBy=True ColorScheme=Standard
Note on A9: Version=1.3 Type=Chart Style=SandChart Name=3773-73DA-41E2-E1B5 Description=Sand Chart Culture=en-US Timestamp=6/10/2009 11:43:56 AM Footprint=R10C4:R39C8 Locks=Title.Visibility,Title.Text,Title.Font,Title.Border,Title.Interior,Series.Type,Series.Color,Series.Pattern,Series.Effects,Series.LineWeight,Series.LineStyle,Series.MarkerStyle,Series.MarkerSize,XAxis.TitleText,XAxis.TitleFormat,XAxis.Line,XAxis.Labels,XAxis.Font,XAxis.NumberFormat,XAxis.Spacing,XAxis.TickMarks,XAxis.GridLines,XAxis.Crossing,XAxis.MinimumScale,XAxis.MaximumScale,YAxis.TitleText,YAxis.TitleFormat,YAxis.Line,YAxis.Labels,YAxis.Font,YAxis.NumberFormat,YAxis.Units,YAxis.TickMarks,YAxis.GridLines,YAxis.Crossing,YAxis.MinimumScale,YAxis.MaximumScale,Legend.Visibility,Legend.Position,Legend.Size,Legend.Font,Legend.Border,Legend.Interior,PlotArea.Position,PlotArea.Size,PlotArea.Border,PlotArea.Interior,Walls.Border,Walls.Interior
Note on A44: Version=1.3 Type=Table Style=PhasedCaseTable Name=3773-73DA-4D46-A03B Description=Time Phased Table Culture=en-US Timestamp=6/10/2009 11:43:56 AM Footprint=R45C4:R49C7 Locks=
Note on A50: Version=1.3 Type=Table Style=PhasedCaseTable Name=226F-2ED3-7F61-C951 Description=Time Phased Table Culture=en-US Timestamp=6/8/2009 2:25:40 PM Footprint=R53C4:R55C11

## Project #2 Layered Sand
POST Report
Sand Chart for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit
Funding in TY $M, 2000 iterations
Wednesday, 10 June 2009, 11:43 am
Sand Chart
Time Phased Results for Point Estimate
Funding in TY $M
| WBS | 2010 | 2011 | 2012
ACE4240 | RDT&E REQUIRED @ 80% CONFIDENCE | 22.4092 | 34.5874 | 31.9527
ACE4241 | RDT&E POINT ESTIMATE | 19.3422 | 21.5545 | 16.409
ACE4242 | RDT&E RISK DOLLARS TO 50% CONF | 1.1488 | 4.8815 | 5.822
ACE4251 | RDT&E RISK DOLLARS 50% TO 80% CONF | 1.9182 | 8.1514 | 9.7218
Note on A1: Version=1.3 Type=SandChart
Note on A4: culture=en-US Timestamp=6/10/2009 11:43:56 AM Heading=Sand Chart for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit Inflation=ThenYear Cases="Sanitized ACE Example for Demos V1 08JUN2009.aceit,Point Estimate" SelectedRow=ACE4240,RDT&E REQUIRED @ 80% CONFIDENCE RowFilter=Cost, NonCost VisibilityLevel=2 SelectedRows="ACE3695,Y","ACE4002,Y","ACE3250,Y","ACE3301,Y","ACE3308,Y","ACE3249,Y","ACE3247,Y","ACE3266,Y","ACE3264,Y","ACE3268,Y","ACE3270,Y","ACE3067,Y","ACE3066,Y","ACE3068,Y","ACE3075,Y","ACE3074,Y","ACE3076,Y","ACE3295,Y","ACE3297,Y","ACE3296,Y","ACE2881,Y","ACE2882,Y","ACE2883,Y","ACE2957,Y","ACE2958,Y","ACE2959,Y","ACE3048,Y","ACE3049,Y","ACE3050,Y","ACE3154,Y","ACE3155,Y","ACE3156,Y","ACE3102,Y","ACE3103,Y","ACE3104,Y","ACE3005,Y","ACE3006,Y","ACE3007,Y","ACE4136,Y","ACE4137,Y","ACE4138,Y","ACE4147,Y","ACE4148,Y","ACE4149,Y","ACE4153,Y","ACE4154,Y","ACE4155,Y","ACE4159,Y","ACE4160,Y","ACE4161,Y","ACE4165,Y","ACE4166,Y","ACE4167,Y","ACE4171,Y","ACE4172,Y","ACE4173,Y","ACE3787,Y","ACE3797,Y","ACE3807,Y","ACE3817,Y","ACE3827,Y","ACE3911,Y","ACE3916,Y","ACE3921,Y","ACE3926,Y","ACE3931,Y","ACE4240,Y","ACE4208,Y","ACE4213,Y","ACE4218,Y","ACE4223,Y","ACE4228,Y","FULL3600$,Y","ACE4090,Y","ACE3936,Y","ACE3236,Y","ACE3429,Y","ACE3172,Y","ACE4067,Y","ACE4066,Y","ACE4065,Y","ACE3495,Y","ACE3483,Y","ACE3596,Y","ACE3486,Y","ACE3496,Y","ACE3585,Y","ACE4084,Y","ACE3350,Y","ACE3360,Y","ACE3354,Y","ACE3356,Y","Monthly_Avg_Labor_Rate$,Y","ACE3362,Y","Proj1_IATCO%,Y","Proj1_Trg%,Y","Proj1_OSA%,Y","ACE4069,Y","ACE3576,Y","ACE3575,Y","ACE3574,Y","CSPU_FEE%,Y","ACE3598,Y","ACE2829,Y","ACE2830,Y","ACE2831,Y","ACE2832,Y","ACE2833,Y","ACE2835,Y","ACE2836,Y","ACE2846,Y","ACE2847,Y","ACE2848,Y","ACE2849,Y","ACE2850,Y","ACE2851,Y","ACE2852,Y","Proj1_SW_NoGrowth$,Y","SOFTWARE,Y","ACQ_SPT_CER$,Y","Adj_SE_dat,Y","Adj_SE_Proj1,Y","ACE3516,Y","ACE3523,Y","ACE3616,Y","ACE3625,Y","ACE3217,Y","CSWS_SPARE129$,Y","ACE3541,Y","MIT_LL$,Y","ACE3549,Y","ACE3538,Y","ACE3535,Y","ACE3527,Y","ACE3531,Y","ACE3530,Y","ACE3536,Y","ACE3528,Y" FirstYear=2003 LastYear=2013 TotalLocation=None DisplayAs=Areas DisplayIn3d=False DisplayFilteredBy=True ColorScheme=Standard
Note on A9: Version=1.3 Type=Chart Style=SandChart Name=06E0-B6B5-203A-3C81 Description=Sand Chart Culture=en-US Timestamp=6/10/2009 11:43:56 AM Footprint=R10C4:R39C8 Locks=Title.Visibility,Title.Text,Title.Font,Title.Border,Title.Interior,Series.Type,Series.Color,Series.Pattern,Series.Effects,Series.LineWeight,Series.LineStyle,Series.MarkerStyle,Series.MarkerSize,XAxis.TitleText,XAxis.TitleFormat,XAxis.Line,XAxis.Labels,XAxis.Font,XAxis.NumberFormat,XAxis.Spacing,XAxis.TickMarks,XAxis.GridLines,XAxis.Crossing,XAxis.MinimumScale,XAxis.MaximumScale,YAxis.TitleText,YAxis.TitleFormat,YAxis.Line,YAxis.Labels,YAxis.Font,YAxis.NumberFormat,YAxis.Units,YAxis.TickMarks,YAxis.GridLines,YAxis.Crossing,YAxis.MinimumScale,YAxis.MaximumScale,Legend.Visibility,Legend.Position,Legend.Size,Legend.Font,Legend.Border,Legend.Interior,PlotArea.Position,PlotArea.Size,PlotArea.Border,PlotArea.Interior,Walls.Border,Walls.Interior
Note on A44: Version=1.3 Type=Table Style=PhasedCaseTable Name=06E3-1907-6EC5-4BD6 Description=Time Phased Table Culture=en-US Timestamp=6/10/2009 11:43:56 AM Footprint=R45C4:R50C7 Locks=
Note on A51: Version=1.3 Type=Table Style=PhasedCaseTable Name=0943-FD67-41C5-73E3 Description=Time Phased Table Culture=en-US Timestamp=6/10/2009 11:37:57 AM Footprint=R54C4:R56C11

## Project #2 Sand 80 Uncstr
POST Report
Sand Chart for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit
Funding in TY $M, 2000 iterations
Wednesday, 10 June 2009, 11:43 am
Sand Chart
Time Phased Results for Point Estimate
Funding in TY $M
| WBS | 2010 | 2011 | 2012 | 2013
ACE4228 | RDT&E REQUIRED @ 80% CONFIDENCE | 21.0139 | 27.8846 | 29.7141 | 10.6885
ACE4229 | RDT&E POINT ESTIMATE | 19.3422 | 21.5545 | 16.409
ACE4230 | RDT&E RISK DOLLARS TO 80% CONF | 1.6717 | 6.3301 | 13.3051 | 10.6885
Note on A1: Version=1.3 Type=SandChart
Note on A4: culture=en-US Timestamp=6/10/2009 11:43:57 AM Heading=Sand Chart for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit Inflation=ThenYear Cases="Sanitized ACE Example for Demos V1 08JUN2009.aceit,Point Estimate" SelectedRow=ACE4228,RDT&E REQUIRED @ 80% CONFIDENCE RowFilter=Cost, NonCost VisibilityLevel=2 SelectedRows="ACE3695,Y","ACE4002,Y","ACE3250,Y","ACE3301,Y","ACE3308,Y","ACE3249,Y","ACE3247,Y","ACE3266,Y","ACE3264,Y","ACE3268,Y","ACE3270,Y","ACE3067,Y","ACE3066,Y","ACE3068,Y","ACE3075,Y","ACE3074,Y","ACE3076,Y","ACE3295,Y","ACE3297,Y","ACE3296,Y","ACE2881,Y","ACE2882,Y","ACE2883,Y","ACE2957,Y","ACE2958,Y","ACE2959,Y","ACE3048,Y","ACE3049,Y","ACE3050,Y","ACE3154,Y","ACE3155,Y","ACE3156,Y","ACE3102,Y","ACE3103,Y","ACE3104,Y","ACE3005,Y","ACE3006,Y","ACE3007,Y","ACE4136,Y","ACE4137,Y","ACE4138,Y","ACE4147,Y","ACE4148,Y","ACE4149,Y","ACE4153,Y","ACE4154,Y","ACE4155,Y","ACE4159,Y","ACE4160,Y","ACE4161,Y","ACE4165,Y","ACE4166,Y","ACE4167,Y","ACE4171,Y","ACE4172,Y","ACE4173,Y","ACE3787,Y","ACE3797,Y","ACE3807,Y","ACE3817,Y","ACE3827,Y","ACE3911,Y","ACE3916,Y","ACE3921,Y","ACE3926,Y","ACE3931,Y","ACE4240,Y","ACE4208,Y","ACE4213,Y","ACE4218,Y","ACE4223,Y","ACE4228,Y","FULL3600$,Y","ACE4090,Y","ACE3936,Y","ACE3236,Y","ACE3429,Y","ACE3172,Y","ACE4067,Y","ACE4066,Y","ACE4065,Y","ACE3495,Y","ACE3483,Y","ACE3596,Y","ACE3486,Y","ACE3496,Y","ACE3585,Y","ACE4084,Y","ACE3350,Y","ACE3360,Y","ACE3354,Y","ACE3356,Y","Monthly_Avg_Labor_Rate$,Y","ACE3362,Y","Proj1_IATCO%,Y","Proj1_Trg%,Y","Proj1_OSA%,Y","ACE4069,Y","ACE3576,Y","ACE3575,Y","ACE3574,Y","CSPU_FEE%,Y","ACE3598,Y","ACE2829,Y","ACE2830,Y","ACE2831,Y","ACE2832,Y","ACE2833,Y","ACE2835,Y","ACE2836,Y","ACE2846,Y","ACE2847,Y","ACE2848,Y","ACE2849,Y","ACE2850,Y","ACE2851,Y","ACE2852,Y","Proj1_SW_NoGrowth$,Y","SOFTWARE,Y","ACQ_SPT_CER$,Y","Adj_SE_dat,Y","Adj_SE_Proj1,Y","ACE3516,Y","ACE3523,Y","ACE3616,Y","ACE3625,Y","ACE3217,Y","CSWS_SPARE129$,Y","ACE3541,Y","MIT_LL$,Y","ACE3549,Y","ACE3538,Y","ACE3535,Y","ACE3527,Y","ACE3531,Y","ACE3530,Y","ACE3536,Y","ACE3528,Y" FirstYear=2003 LastYear=2013 TotalLocation=None DisplayAs=Areas DisplayIn3d=False DisplayFilteredBy=True ColorScheme=Rainbow Colors
Note on A9: Version=1.3 Type=Chart Style=SandChart Name=058A-6397-3C60-276B Description=Sand Chart Culture=en-US Timestamp=6/10/2009 11:43:57 AM Footprint=R10C4:R39C8 Locks=Title.Visibility,Title.Text,Title.Font,Title.Border,Title.Interior,Series.Type,Series.Color,Series.Pattern,Series.Effects,Series.LineWeight,Series.LineStyle,Series.MarkerStyle,Series.MarkerSize,XAxis.TitleText,XAxis.TitleFormat,XAxis.Line,XAxis.Labels,XAxis.Font,XAxis.NumberFormat,XAxis.Spacing,XAxis.TickMarks,XAxis.GridLines,XAxis.Crossing,XAxis.MinimumScale,XAxis.MaximumScale,YAxis.TitleText,YAxis.TitleFormat,YAxis.Line,YAxis.Labels,YAxis.Font,YAxis.NumberFormat,YAxis.Units,YAxis.TickMarks,YAxis.GridLines,YAxis.Crossing,YAxis.MinimumScale,YAxis.MaximumScale,Legend.Visibility,Legend.Position,Legend.Size,Legend.Font,Legend.Border,Legend.Interior,PlotArea.Position,PlotArea.Size,PlotArea.Border,PlotArea.Interior,Walls.Border,Walls.Interior
Note on A44: Version=1.3 Type=Table Style=PhasedCaseTable Name=058A-6397-07E1-A9E0 Description=Time Phased Table Culture=en-US Timestamp=6/10/2009 11:43:57 AM Footprint=R45C4:R49C8 Locks=

## Project #2 Sand 80 Un Bar
POST Report
Sand Chart for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit
Funding in TY $M, 2000 iterations
Tuesday, 23 June 2009, 3:07 pm
Sand Chart
Time Phased Results for Point Estimate
Funding in TY $M
| WBS | 2010 | 2011 | 2012 | 2013
ACE4228 | RDT&E REQUIRED @ 80% CONFIDENCE | 21.0139 | 27.8846 | 29.7141 | 10.6885
ACE4229 | RDT&E POINT ESTIMATE | 19.3422 | 21.5545 | 16.409
ACE4230 | RDT&E RISK DOLLARS TO 80% CONF | 1.6717 | 6.3301 | 13.3051 | 10.6885
Note on A1: Version=1.3 Type=SandChart
Note on A4: culture=en-US Timestamp=6/23/2009 3:07:44 PM Heading=Sand Chart for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit Inflation=ThenYear Cases="Sanitized ACE Example for Demos V1 08JUN2009.aceit,Point Estimate" SelectedRow=ACE4228,RDT&E REQUIRED @ 80% CONFIDENCE RowFilter=Cost, NonCost VisibilityLevel=2 SelectedRows="ACE3695,Y","ACE4002,Y","ACE3250,Y","ACE3301,Y","ACE3308,Y","ACE3249,Y","ACE3247,Y","ACE3266,Y","ACE3264,Y","ACE3268,Y","ACE3270,Y","ACE3067,Y","ACE3066,Y","ACE3068,Y","ACE3075,Y","ACE3074,Y","ACE3076,Y","ACE3295,Y","ACE3297,Y","ACE3296,Y","ACE2881,Y","ACE2882,Y","ACE2883,Y","ACE2957,Y","ACE2958,Y","ACE2959,Y","ACE3048,Y","ACE3049,Y","ACE3050,Y","ACE3154,Y","ACE3155,Y","ACE3156,Y","ACE3102,Y","ACE3103,Y","ACE3104,Y","ACE3005,Y","ACE3006,Y","ACE3007,Y","ACE4136,Y","ACE4137,Y","ACE4138,Y","ACE4147,Y","ACE4148,Y","ACE4149,Y","ACE4153,Y","ACE4154,Y","ACE4155,Y","ACE4159,Y","ACE4160,Y","ACE4161,Y","ACE4165,Y","ACE4166,Y","ACE4167,Y","ACE4171,Y","ACE4172,Y","ACE4173,Y","ACE3787,Y","ACE3797,Y","ACE3807,Y","ACE3817,Y","ACE3827,Y","ACE3911,Y","ACE3916,Y","ACE3921,Y","ACE3926,Y","ACE3931,Y","ACE4240,Y","ACE4208,Y","ACE4213,Y","ACE4218,Y","ACE4223,Y","ACE4228,Y","FULL3600$,Y","ACE4090,Y","ACE3936,Y","ACE3236,Y","ACE3429,Y","ACE3172,Y","ACE4067,Y","ACE4066,Y","ACE4065,Y","ACE3495,Y","ACE3483,Y","ACE3596,Y","ACE3486,Y","ACE3496,Y","ACE3585,Y","ACE4084,Y","ACE3350,Y","ACE3360,Y","ACE3354,Y","ACE3356,Y","Monthly_Avg_Labor_Rate$,Y","ACE3362,Y","Proj1_IATCO%,Y","Proj1_Trg%,Y","Proj1_OSA%,Y","ACE4069,Y","ACE3576,Y","ACE3575,Y","ACE3574,Y","CSPU_FEE%,Y","ACE3598,Y","ACE2829,Y","ACE2830,Y","ACE2831,Y","ACE2832,Y","ACE2833,Y","ACE2835,Y","ACE2836,Y","ACE2846,Y","ACE2847,Y","ACE2848,Y","ACE2849,Y","ACE2850,Y","ACE2851,Y","ACE2852,Y","Proj1_SW_NoGrowth$,Y","SOFTWARE,Y","ACQ_SPT_CER$,Y","Adj_SE_dat,Y","Adj_SE_Proj1,Y","ACE3516,Y","ACE3523,Y","ACE3616,Y","ACE3625,Y","ACE3217,Y","CSWS_SPARE129$,Y","ACE3541,Y","MIT_LL$,Y","ACE3549,Y","ACE3538,Y","ACE3535,Y","ACE3527,Y","ACE3531,Y","ACE3530,Y","ACE3536,Y","ACE3528,Y" FirstYear=2010 LastYear=2013 TotalLocation=None DisplayAs=Columns DisplayIn3d=False DisplayFilteredBy=True ColorScheme=Standard
Note on A9: Version=1.3 Type=Chart Style=SandChart Name=75AC-3D5C-0C74-76E1 Description=Sand Chart Culture=en-US Timestamp=6/23/2009 3:07:44 PM Footprint=R10C4:R39C8 Locks=Title.Visibility,Title.Text,Title.Font,Title.Border,Title.Interior,Series.Type,Series.Color,Series.Pattern,Series.Effects,Series.LineWeight,Series.LineStyle,Series.MarkerStyle,Series.MarkerSize,XAxis.TitleText,XAxis.TitleFormat,XAxis.Line,XAxis.Labels,XAxis.Font,XAxis.NumberFormat,XAxis.Spacing,XAxis.TickMarks,XAxis.GridLines,XAxis.Crossing,XAxis.MinimumScale,XAxis.MaximumScale,YAxis.TitleText,YAxis.TitleFormat,YAxis.Line,YAxis.Labels,YAxis.Font,YAxis.NumberFormat,YAxis.Units,YAxis.TickMarks,YAxis.GridLines,YAxis.Crossing,YAxis.MinimumScale,YAxis.MaximumScale,Legend.Visibility,Legend.Position,Legend.Size,Legend.Font,Legend.Border,Legend.Interior,PlotArea.Position,PlotArea.Size,PlotArea.Border,PlotArea.Interior,Walls.Border,Walls.Interior
Note on A44: Version=1.3 Type=Table Style=PhasedCaseTable Name=75AC-3D5C-2CD2-2322 Description=Time Phased Table Culture=en-US Timestamp=6/23/2009 3:07:44 PM Footprint=R45C4:R49C8 Locks=
Note on A50: Version=1.3 Type=Table Style=PhasedCaseTable Name=798E-634D-61E3-DCFA Description=Time Phased Table Culture=en-US Timestamp=6/23/2009 3:07:35 PM Footprint=R53C4:R55C8

## Project #2 RR Tornado
POST Report
Tornado Chart for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit
Funding in TY $M, Bounds based upon driver variable percentiles derived from 2000 iterations
Wednesday, 10 June 2009, 11:43 am
Tornado Chart
Drivers & Results
|  |  | Target Row Results |  |  | Risk Range Inputs
| Drivers (exlcuding Rollup, Zero Uncertainty) | Row | Delta | 15% | 85% | Point Estimate | 15% | 85%
| Acquisition Support (SE/PM, ST&E, Data) | 459 | 18.1746 | 54.5105 | 72.6851 | 13.5245 | 11.537 | 24.4604
| Subsystem #1 Hardware Material Cost (SEER-H) Per String | 384 | 16.9505 | 51.5813 | 68.5318 | 1.4539 | 0.72444 | 2.9161
| Subsystem #1 Hardware Development Labor Hours (SEER-H) | 383 | 13.7706 | 52.8959 | 66.6665 | 30000 | 13879.4875 | 64836.8082
| Avg Hourly Rate (Calculated from Actual Data Jan 2009) w/Travel, ODC | 395 | 9.3903 | 54.6101 | 64.0004 | 9.1751e-05 | 8.1326e-05 | 0.00011797
| Subsystem #3 SW Labor Hours | 375 | 8.0972 | 55.1172 | 63.2144 | 10000 | 3664.7574 | 27305.0674
| Project #2 IAT&CO % of HW & SW (Project #1 Actuals) | 405 | 7.6331 | 54.6709 | 62.3041 | 0.18 | 0.093747 | 0.34542
| Subsystem #2 HW Development Labor Hours (SEER-H) | 385 | 7.3725 | 54.5737 | 61.9461 | 24000 | 13988.4602 | 41172.2849
| Subsystem #1 SW Labor Hours | 373 | 5.6726 | 55.5635 | 61.2362 | 9000 | 3953.2159 | 20480.3128
| Subsystem #2 HW Material Cost (Actuals) | 386 | 5.0772 | 56.0361 | 61.1133 | 0.18446 | 0.060989 | 0.55725
| Subsystem #2 SW Labor Hours | 374 | 3.5853 | 56.1036 | 59.689 | 7000 | 3514.9157 | 13946.0324
| ETASS | 501 | 2.695 | 55.958 | 58.6529 | 9 | 6.6662 | 11.3328
| ETASS Labor Rate (Yearly) | 506 | 2.6932 | 55.9585 | 58.6516 | 2.2955 | 1.7005 | 2.8899
| Software Code Growth Factor (Holchin Study, Nominal Complexity, 60% Maturity) | 379 | 2.2222 | 56.1929 | 58.4151 | 1.33 | 1.1649 | 1.4951
| Subsystem #7 | 430 | 2.0739 | 56.5329 | 58.6068 | 0.18446 | 0.10925 | 0.31143
| MITRE | 498 | 1.7962 | 56.4081 | 58.2043 | 6 | 4.4456 | 7.5559
| MITRE Labor Rate (Yearly) | 503 | 1.7962 | 56.4075 | 58.2037 | 2.2955 | 1.7004 | 2.8904
| PASS Labor Rate (Yearly) | 505 | 1.7956 | 56.4082 | 58.2038 | 2.2955 | 1.7009 | 2.8905
| PASS | 500 | 1.7946 | 56.4083 | 58.2029 | 6 | 4.446 | 7.5536
| Project #2 Contract Award Fee @ 12% | 412 | 1.3992 | 56.6064 | 58.0056 | 0.12 | 0.10135 | 0.13866
| SCS Labor Rate (Yearly) | 504 | 0.89815 | 56.8565 | 57.7546 | 2.2955 | 1.7003 | 2.8903
| SCS | 499 | 0.89778 | 56.8568 | 57.7546 | 3 | 2.2226 | 3.7772
| Project #2 OSA % of HW - PROGRAM X Factor | 406 | 0.41415 | 57.0986 | 57.5128 | 0.1 | 0.084451 | 0.11554
| Project #2 MIT/LL Support Costt | 495 | 0.34256 | 57.1344 | 57.477 | 0.52668 | 0.39022 | 0.66306
| Project #1 Training % of PMP - PROGRAM X Factor | 402 | 0.25902 | 57.1762 | 57.4352 | 0.04 | 0.033779 | 0.046221
| Project #2 Travel Cost | 493 | 0.17124 | 57.2201 | 57.3914 | 0.26334 | 0.19514 | 0.33153
| Government Test Support - 17th TS | 306 | 0.14542 | 57.2614 | 57.4068 | 0.71152 | 0.64132 | 0.87151
| Project #2 PSE % of PMP - PROGRAM X Factor | 407 |  | 57.3057 | 57.3057 | 0.04 | 0.03378 | 0.046217
| Project #2 Spares % of PMP - PROGRAM X Factor | 408 |  | 57.3057 | 57.3057 | 0.1 | 0.084446 | 0.11555
Note on A1: Version=1.3 Type=TornadoChart
Note on A4: culture=en-US Timestamp=6/10/2009 11:43:58 AM Heading=Tornado Chart for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit PositiveAdjustment=10 NegativeAdjustment=10 UseRiskRange=True LowConfidenceLevel=15 AdjustForCorrelation=False DisplayCorrelationResults=False ShowRowNumbers=False Inflation=ThenYear Cases="Sanitized ACE Example for Demos V1 08JUN2009.aceit,Point Estimate" SelectedRow=ACE3429,Project #2 Total RowFilter=Cost, NonCost VariableFilter=NonRollup, AnyUncertain, DefinedUncertainty, Cost, NonCost, Phased, Constant ExcludeAboveInputsSection=False DriverCodes=ACE3077,ACE4067,ACE4066,ACE4065,ACE3596,ACE3486,ACE3496,ACE3585,ACE4084,ACE3356,Proj1_Trg%,ACE4069,ACE3576,ACE3575,ACE3574,ACE3598,ACE2852,ACE3516,ACE3538,ACE3535,ACE3478,ACE3474,ACE3475,ACE3473,ACE3531,ACE3530,ACE3536,ACE3528 Cutoff=7 DisplayAs=Bars DisplayIn3d=False DisplayFilteredBy=False ColorScheme=Rainbow Colors
Note on A9: Version=1.3 Type=Chart Style=TornadoChart Name=6EC0-FA90-4621-C094 Description=Tornado Chart Culture=en-US Timestamp=6/10/2009 11:43:59 AM Footprint=R10C4:R39C8 Locks=Title.Visibility,Title.Text,Title.Font,Title.Border,Title.Interior,Series.Type,Series.Color,Series.Pattern,Series.Effects,Series.LineWeight,Series.LineStyle,Series.MarkerStyle,Series.MarkerSize,XAxis.TitleText,XAxis.TitleFormat,XAxis.Line,XAxis.Labels,XAxis.Font,XAxis.NumberFormat,XAxis.Spacing,XAxis.TickMarks,XAxis.GridLines,XAxis.Crossing,XAxis.MinimumScale,XAxis.MaximumScale,YAxis.TitleText,YAxis.TitleFormat,YAxis.Line,YAxis.Labels,YAxis.Font,YAxis.NumberFormat,YAxis.Units,YAxis.TickMarks,YAxis.GridLines,YAxis.Crossing,YAxis.MinimumScale,YAxis.MaximumScale,Legend.Visibility,Legend.Position,Legend.Size,Legend.Font,Legend.Border,Legend.Interior,PlotArea.Position,PlotArea.Size,PlotArea.Border,PlotArea.Interior,Walls.Border,Walls.Interior
Note on A43: Version=1.3 Type=Table Style=VariableSensitivityTable Name=6EBE-983E-3BFC-6692 Description=Variable Sensitivity Table Culture=en-US Timestamp=6/10/2009 11:43:59 AM Footprint=R44C4:R73C11 Locks=

## Variance Analysis Chart
POST Report
Uncertainty Correlation Chart for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit
Costs in BY2005 $M, 2000 iterations
Tuesday, 23 June 2009, 3:47 pm
Uncertainty Correlation Chart
Uncertainty Correlation Analysis (correlation between target output and driver input uncertainty distributions)
| Drivers | Row | Std. Dev | CV | Par. Corr.
| Subsystem #1 Hardware Material Cost (SEER-H) Per String | 384 | 1.373 | 0.75361 | 0.70067
| Subsystem #1 Hardware Development Labor Hours (SEER-H) | 383 | 34096.3012 | 0.86146 | 0.63755
| Acquisition Support (SE/PM, ST&E, Data) | 459 | 6.9518 | 0.38866 | 0.53106
| Avg Hourly Rate (Calculated from Actual Data Jan 2009) w/Travel, ODC | 395 | 1.6569e-05 | 0.16732 | 0.52092
| Subsystem #3 SW Labor Hours | 375 | 19682.3454 | 1.2312 | 0.48015
| Project #2 IAT&CO % of HW & SW (Project #1 Actuals) | 405 | 0.15385 | 0.70082 | 0.46475
| Subsystem #2 HW Development Labor Hours (SEER-H) | 385 | 15384.3757 | 0.55964 | 0.41216
| Subsystem #1 SW Labor Hours | 373 | 11466.3605 | 0.93025 | 0.35591
| Subsystem #2 HW Material Cost (Actuals) | 386 | 0.44946 | 1.3833 | 0.32696
| Subsystem #2 SW Labor Hours | 374 | 6506.5426 | 0.74513 | 0.22228
| Software Code Growth Factor (Holchin Study, Nominal Complexity, 60% Maturity) | 379 | 0.14899 | 0.11202 | 0.17423
| Subsystem #7 | 430 | 0.11274 | 0.53802 | 0.17109
| ETASS Labor Rate (Yearly) | 506 | 0.57437 | 0.25021 | 0.13634
| ETASS | 501 | 2.2511 | 0.25013 | 0.11552
| MITRE | 498 | 1.5012 | 0.25021 | 0.09807
| MITRE Labor Rate (Yearly) | 503 | 0.57424 | 0.25014 | 0.087058
| PASS Labor Rate (Yearly) | 505 | 0.57438 | 0.25022 | 0.083485
| Project #2 Contract Award Fee @ 12% | 412 | 0.018002 | 0.15002 | 0.073863
| PASS | 500 | 1.5015 | 0.25024 | 0.065119
| SCS Labor Rate (Yearly) | 504 | 0.57412 | 0.25011 | 0.054783
| Government Test Support | 340 | 0.079981 | 0.19984 | 0.053004
| Project #2 Spares % of PMP - PROGRAM X Factor | 408 | 0.01501 | 0.1501 | 0.051432
| SCS | 499 | 0.75013 | 0.25004 | 0.043023
| Project #2 MIT/LL Support Costt | 495 | 0.13171 | 0.25006 | 0.01767
| Project #2 Travel Cost | 493 | 0.065861 | 0.25009 | 0.016722
| Government Test Support - 17th TS | 306 | 0.10702 | 0.14179 | 0.013078
| Subsystem #2 HW Material | 320 | 1.6286 | 1.4383 | 0.0037841
| Project #1 Training % of PMP - PROGRAM X Factor | 402 | 0.0060018 | 0.15004 | -0.0047887
| Project #2 OSA % of HW - PROGRAM X Factor | 406 | 0.015017 | 0.15017 | -0.0096799
| Project #2 PSE % of PMP - PROGRAM X Factor | 407 | 0.0060057 | 0.15014 | -0.024351
Rank Correlation Matrix
|  |  | Subsystem #1 Hardware Material Cost (SEER-H) Per String | Subsystem #1 Hardware Development Labor Hours (SEER-H) | Acquisition Support (SE/PM, ST&E, Data) | Avg Hourly Rate (Calculated from Actual Data Jan 2009) w/Travel, ODC | Subsystem #3 SW Labor Hours | Project #2 IAT&CO % of HW & SW (Project #1 Actuals) | Subsystem #2 HW Development Labor Hours (SEER-H) | Subsystem #1 SW Labor Hours | Subsystem #2 HW Material Cost (Actuals) | Subsystem #2 SW Labor Hours | Software Code Growth Factor (Holchin Study, Nominal Complexity, 60% Maturity) | Subsystem #7 | ETASS Labor Rate (Yearly) | ETASS | MITRE | MITRE Labor Rate (Yearly) | PASS Labor Rate (Yearly) | Project #2 Contract Award Fee @ 12% | PASS | SCS Labor Rate (Yearly) | Government Test Support | Project #2 Spares % of PMP - PROGRAM X Factor | SCS | Project #2 MIT/LL Support Costt | Project #2 Travel Cost | Government Test Support - 17th TS | Subsystem #2 HW Material | Project #1 Training % of PMP - PROGRAM X Factor | Project #2 OSA % of HW - PROGRAM X Factor | Project #2 PSE % of PMP - PROGRAM X Factor
|  | Row | 384 | 383 | 459 | 395 | 375 | 405 | 385 | 373 | 386 | 374 | 379 | 430 | 506 | 501 | 498 | 503 | 505 | 412 | 500 | 504 | 340 | 408 | 499 | 495 | 493 | 306 | 320 | 402 | 406 | 407
| Subsystem #1 Hardware Material Cost (SEER-H) Per String | 384 | 1 | -0.0079242 | 0.0083061 | -0.008722 | -0.0054299 | 0.029674 | -0.01003 | -0.011126 | 0.030525 | -0.01964 | -0.024213 | -0.0215 | 0.014079 | 9.5396e-05 | -0.014007 | 0.0088972 | 0.0257 | -0.0025882 | -0.020961 | 0.046599 | 0.0083337 | -0.024008 | -0.0072205 | -0.01915 | 0.020315 | 0.022797 | 0.0082395 | 0.0035989 | 0.032279 | 0.0076961
| Subsystem #1 Hardware Development Labor Hours (SEER-H) | 383 |  | 1 | 0.0070856 | 0.046018 | -0.018293 | -0.0066078 | -0.006919 | -0.028582 | 0.0068359 | 0.023474 | 0.04581 | 0.00061447 | -0.035023 | -0.001146 | 0.020823 | 0.022952 | -0.051399 | 0.00064686 | -0.00020749 | -0.0021152 | -0.011861 | 0.011395 | -0.01397 | -0.020993 | -0.00092657 | -0.033872 | 0.02145 | 0.0032095 | 0.034424 | -0.013586
| Acquisition Support (SE/PM, ST&E, Data) | 459 |  |  | 1 | 0.0081108 | 0.015314 | 0.00036533 | 0.017538 | 0.011178 | 0.00054352 | -0.020732 | -0.0236 | 0.03281 | 0.007764 | 0.020059 | 0.0041864 | -0.006372 | 0.023762 | -0.010114 | -0.027374 | 0.0056071 | 0.0029696 | 0.037058 | 0.036595 | 0.024406 | -0.02351 | 0.034995 | 0.043343 | -0.01316 | 0.0033871 | 0.013351
| Avg Hourly Rate (Calculated from Actual Data Jan 2009) w/Travel, ODC | 395 |  |  |  | 1 | 0.02155 | 0.034943 | 0.056836 | 0.008544 | -0.021908 | 0.0099597 | 0.013311 | 0.01378 | -0.00034321 | 0.025916 | 0.039993 | -0.027604 | 0.012531 | 0.023895 | 0.043954 | -0.023183 | 0.0016003 | 0.00039002 | 0.048171 | 0.0011107 | 0.034871 | 0.0015339 | -0.037109 | -0.0017692 | 0.029093 | 0.0094771
| Subsystem #3 SW Labor Hours | 375 |  |  |  |  | 1 | -0.023028 | 0.024982 | 0.00017317 | -0.031246 | 0.0093633 | 0.0087046 | -0.0032776 | 0.042054 | 0.018377 | -0.010274 | -0.0014703 | -0.011884 | -0.0060504 | 0.027092 | 0.0026286 | -0.0050194 | 0.023274 | 0.014367 | 0.020549 | 0.0094674 | 0.025857 | -0.040563 | -0.014227 | -0.025705 | 0.011297
| Project #2 IAT&CO % of HW & SW (Project #1 Actuals) | 405 | [5 empty] | 1 | 0.037608 | 0.016311 | 0.00096228 | -0.01201 | 0.016949 | 0.0077881 | -0.0021189 | 0.026676 | 0.0094934 | -0.015258 | -0.017639 | 0.010233 | 0.034829 | -0.00040249 | -0.01294 | -0.010899 | -0.047287 | -0.025631 | -0.02515 | 0.014143 | -0.011831 | -0.041676 | 0.00064514 | -0.0077264
| Subsystem #2 HW Development Labor Hours (SEER-H) | 385 | [6 empty] | 1 | 0.023599 | 0.005028 | -0.022935 | -0.003833 | 0.013582 | -0.023998 | 0.006129 | 0.012919 | 0.01063 | -0.021123 | 0.015366 | -0.0093461 | -0.034548 | 0.037789 | 0.024314 | -0.016093 | 0.020464 | -0.01072 | 0.020681 | -0.015105 | -0.010171 | -0.020651 | -0.012351
| Subsystem #1 SW Labor Hours | 373 | [7 empty] | 1 | -0.011429 | 0.039254 | 0.010356 | 0.0016078 | 0.014447 | -0.0037192 | 0.016494 | 0.022892 | 0.0013235 | 0.010893 | -0.0050211 | 0.0020941 | 0.0061516 | -0.021862 | 0.016032 | 0.02534 | 0.033594 | 0.0022446 | -0.010225 | 0.038108 | 0.0051056 | -0.017537
| Subsystem #2 HW Material Cost (Actuals) | 386 | [8 empty] | 1 | 0.010678 | -0.073018 | 0.0028379 | -0.01799 | 0.015661 | 0.0051669 | 0.0011098 | -0.018353 | 0.0094618 | -0.010356 | -0.0060141 | 0.0026431 | -0.014472 | -0.00057585 | -0.014018 | -0.010762 | -0.040677 | 0.014874 | -0.0019828 | 0.0072093 | 0.0013241
| Subsystem #2 SW Labor Hours | 374 | [9 empty] | 1 | -0.011318 | -0.0033178 | -0.0066226 | -0.016154 | 0.01572 | 0.014733 | 0.026885 | 0.029649 | -0.0041127 | -0.015668 | 0.001163 | 0.01214 | -0.031574 | 0.015854 | 0.0089183 | -0.007389 | 0.033974 | -0.027429 | -0.0036416 | -0.01618
| Software Code Growth Factor (Holchin Study, Nominal Complexity, 60% Maturity) | 379 | [10 empty] | 1 | 0.013626 | 0.013437 | 0.0039695 | -0.032062 | 0.015929 | 0.045903 | 0.0024787 | 0.021946 | 0.016093 | 0.018224 | -0.015685 | 0.0059678 | 0.0005697 | 0.013598 | 0.019328 | 0.0061099 | 0.025962 | -0.01269 | -0.018817
| Subsystem #7 | 430 | [11 empty] | 1 | 0.046891 | -0.016886 | -0.0018384 | -0.012957 | 0.011791 | 0.011752 | -0.027476 | -0.0085588 | -0.0067824 | 0.025934 | -0.03615 | -0.034276 | 0.051809 | -0.0011299 | 0.039985 | -0.041227 | -0.038593 | -0.049494
| ETASS Labor Rate (Yearly) | 506 | [12 empty] | 1 | 0.0090884 | -0.0047305 | 0.018836 | 0.0409 | 0.018393 | -0.003182 | -0.014974 | -0.022318 | -0.001625 | 0.0022301 | -0.023119 | 0.022631 | 0.0076824 | -0.016027 | 0.0046235 | -0.060009 | -0.026108
| ETASS | 501 | [13 empty] | 1 | 0.051473 | -0.013689 | -0.0049722 | 0.013518 | -0.027964 | 0.035874 | -0.0059379 | -0.016281 | 0.010389 | -0.017815 | -0.0079819 | -0.00091388 | 0.0039187 | 0.025228 | 0.013974 | 0.0073929
| MITRE | 498 | [14 empty] | 1 | -0.010824 | -0.0098705 | 0.018656 | 0.022643 | -0.0024205 | -0.012613 | -0.014731 | -0.00097154 | -0.0053708 | -0.0019071 | 0.0036286 | 0.011282 | 0.023071 | -0.010546 | 0.0091975
| MITRE Labor Rate (Yearly) | 503 | [15 empty] | 1 | 0.018256 | 0.00459 | -0.037601 | 0.0011667 | -0.01333 | 0.0034511 | -0.026816 | -0.01481 | -0.019434 | -0.0023352 | 0.015895 | -0.0013011 | -0.023093 | -0.061867
| PASS Labor Rate (Yearly) | 505 | [16 empty] | 1 | -0.017744 | -0.016953 | 8.3822e-05 | -0.025716 | -0.020334 | -0.032644 | 0.0039607 | 0.00011758 | 0.020328 | -0.04014 | -0.013913 | 0.027788 | -0.014041
| Project #2 Contract Award Fee @ 12% | 412 | [17 empty] | 1 | -0.013699 | -0.024767 | -0.017478 | -0.023814 | 0.026019 | 0.022102 | 0.014905 | 0.0643 | 0.0055543 | 0.0078296 | 0.0067382 | 0.0057164
| PASS | 500 | [18 empty] | 1 | 0.033405 | 0.0065559 | -0.039984 | -0.041177 | -0.009374 | -0.065408 | 0.0024887 | -0.047482 | -0.0055999 | -0.004875 | 0.0081927
| SCS Labor Rate (Yearly) | 504 | [19 empty] | 1 | -0.042193 | -0.0098195 | -0.034271 | 0.0047104 | -0.020904 | -0.0040885 | 0.043658 | 0.0185 | 0.010204 | 0.026675
| Government Test Support | 340 | [20 empty] | 1 | -0.016768 | 0.020399 | 0.0065673 | 0.0032459 | -0.0018959 | 0.0039219 | 0.028571 | -0.0038369 | 0.011057
| Project #2 Spares % of PMP - PROGRAM X Factor | 408 | [21 empty] | 1 | 0.0013964 | -0.037703 | 0.01607 | -0.011725 | 0.027505 | -0.021827 | 0.037311 | 0.014783
| SCS | 499 | [22 empty] | 1 | -0.031151 | 0.054927 | 0.0060541 | 0.022769 | 0.03696 | -0.017916 | 0.050031
| Project #2 MIT/LL Support Costt | 495 | [23 empty] | 1 | 0.031146 | -0.014161 | 0.015741 | 0.0090719 | 0.019297 | 0.0014106
| Project #2 Travel Cost | 493 | [24 empty] | 1 | 0.031061 | 0.014285 | 0.023013 | -0.040382 | 0.010785
| Government Test Support - 17th TS | 306 | [25 empty] | 1 | -0.0033887 | -0.0059341 | -0.0091761 | -0.015986
| Subsystem #2 HW Material | 320 | [26 empty] | 1 | 0.017313 | -0.018268 | -0.0048771
| Project #1 Training % of PMP - PROGRAM X Factor | 402 | [27 empty] | 1 | -0.0069485 | 0.011913
| Project #2 OSA % of HW - PROGRAM X Factor | 406 | [28 empty] | 1 | 0.0031953
| Project #2 PSE % of PMP - PROGRAM X Factor | 407 | [29 empty] | 1
Note on A1: Version=1.3 Type=VarianceChart
Note on A4: culture=en-US Timestamp=6/23/2009 3:47:03 PM Heading=Uncertainty Correlation Chart for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit ContributionForm=Complete ElementCorrelation=True DriverCorrelation=True CompleteCorrelationMethod=Rank ShowRowNumbers=False Cases="Sanitized ACE Example for Demos V1 08JUN2009.aceit,Point Estimate" SelectedRow=ACE3430,Project #2 RDT&E RowFilter=Cost, NonCost SelectedRows="ACE3695,Y","ACE4002,Y","ACE3250,Y","ACE3301,Y","ACE3308,Y","ACE3249,Y","ACE3247,Y","ACE3266,Y","ACE3264,Y","ACE3268,Y","ACE3270,Y","ACE3067,Y","ACE3066,Y","ACE3068,Y","ACE3075,Y","ACE3074,Y","ACE3076,Y","ACE3295,Y","ACE3297,Y","ACE3296,Y","ACE2881,Y","ACE2882,Y","ACE2883,Y","ACE2957,Y","ACE2958,Y","ACE2959,Y","ACE3048,Y","ACE3049,Y","ACE3050,Y","ACE3154,Y","ACE3155,Y","ACE3156,Y","ACE3102,Y","ACE3103,Y","ACE3104,Y","ACE3005,Y","ACE3006,Y","ACE3007,Y","ACE4136,Y","ACE4137,Y","ACE4138,Y","ACE4147,Y","ACE4148,Y","ACE4149,Y","ACE4153,Y","ACE4154,Y","ACE4155,Y","ACE4159,Y","ACE4160,Y","ACE4161,Y","ACE4165,Y","ACE4166,Y","ACE4167,Y","ACE4171,Y","ACE4172,Y","ACE4173,Y","ACE3787,Y","ACE3797,Y","ACE3807,Y","ACE3817,Y","ACE3827,Y","ACE3911,Y","ACE3916,Y","ACE3921,Y","ACE3926,Y","ACE3931,Y","ACE4240,Y","ACE4208,Y","ACE4213,Y","ACE4218,Y","ACE4223,Y","ACE4228,Y","FULL3600$,Y","ACE4090,Y","ACE3936,Y","ACE3236,Y","ACE3429,Y","ACE3172,Y","ACE4067,Y","ACE4066,Y","ACE4065,Y","ACE3495,Y","ACE3483,Y","ACE3596,Y","ACE3486,Y","ACE3496,Y","ACE3585,Y","ACE4084,Y","ACE3350,Y","ACE3360,Y","ACE3354,Y","ACE3356,Y","Monthly_Avg_Labor_Rate$,Y","ACE3362,Y","Proj1_IATCO%,Y","Proj1_Trg%,Y","Proj1_OSA%,Y","ACE4069,Y","ACE3576,Y","ACE3575,Y","ACE3574,Y","CSPU_FEE%,Y","ACE3598,Y","ACE2829,Y","ACE2830,Y","ACE2831,Y","ACE2832,Y","ACE2833,Y","ACE2835,Y","ACE2836,Y","ACE2846,Y","ACE2847,Y","ACE2848,Y","ACE2849,Y","ACE2850,Y","ACE2851,Y","ACE2852,Y","Proj1_SW_NoGrowth$,Y","SOFTWARE,Y","ACQ_SPT_CER$,Y","Adj_SE_dat,Y","Adj_SE_Proj1,Y","ACE3516,Y","ACE3523,Y","ACE3616,Y","ACE3625,Y","ACE3217,Y","CSWS_SPARE129$,Y","ACE3541,Y","MIT_LL$,Y","ACE3549,Y","ACE3538,Y","ACE3535,Y","ACE3527,Y","ACE3531,Y","ACE3530,Y","ACE3536,Y","ACE3528,Y" VariableFilter=Rollup, NonRollup, DefinedUncertainty, Cost, NonCost, Phased, Constant ExcludeAboveInputsSection=False DriverCodes=ACE3077,ACE3593,ACE3459,ACE4067,ACE4066,ACE4065,ACE3596,ACE3486,ACE3496,ACE3585,ACE4084,ACE3356,Proj1_Trg%,ACE4069,ACE3576,ACE3575,ACE3574,ACE3598,ACE2852,ACE3516,ACE3538,ACE3535,ACE3478,ACE3474,ACE3475,ACE3473,ACE3531,ACE3530,ACE3536,ACE3528 Cutoff=7 DisplayAs=Bars DisplayIn3d=False DisplayFilteredBy=False ColorScheme=Standard
Note on A9: Version=1.3 Type=Chart Style=VarianceChart Name=7CB0-527C-1B3E-A4D6 Description=Uncertainty Correlation Chart Culture=en-US Timestamp=6/23/2009 3:47:03 PM Footprint=R10C4:R39C8 Locks=Title.Visibility,Title.Text,Title.Font,Title.Border,Title.Interior,Series.Type,Series.Color,Series.Pattern,Series.Effects,Series.LineWeight,Series.LineStyle,Series.MarkerStyle,Series.MarkerSize,XAxis.TitleText,XAxis.TitleFormat,XAxis.Line,XAxis.Labels,XAxis.Font,XAxis.NumberFormat,XAxis.Spacing,XAxis.TickMarks,XAxis.GridLines,XAxis.Crossing,XAxis.MinimumScale,XAxis.MaximumScale,YAxis.TitleText,YAxis.TitleFormat,YAxis.Line,YAxis.Labels,YAxis.Font,YAxis.NumberFormat,YAxis.Units,YAxis.TickMarks,YAxis.GridLines,YAxis.Crossing,YAxis.MinimumScale,YAxis.MaximumScale,Legend.Visibility,Legend.Position,Legend.Size,Legend.Font,Legend.Border,Legend.Interior,PlotArea.Position,PlotArea.Size,PlotArea.Border,PlotArea.Interior,Walls.Border,Walls.Interior
Note on A43: Version=1.3 Type=Table Style=VarianceTable Name=7CB0-527C-4221-1C84 Description=Variance Table Culture=en-US Timestamp=6/23/2009 3:47:03 PM Footprint=R44C4:R74C8 Locks=
Note on A77: Version=1.3 Type=Table Style=CorrelationTable Name=7CBE-A062-60B5-1320 Description=Correlation Results Culture=en-US Timestamp=6/23/2009 3:47:03 PM Footprint=R78C4:R109C35 Locks=

## Project #2 Acq Sup S-Curve
POST Report
RI$K Chart for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit
Costs in $M (BY2005 Total), 2000 iterations
Wednesday, 10 June 2009, 11:43 am
RI$K Chart
RI$K Statistics in 5% intervals
| Cumulative Distribution Function | 0% | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% | 65% | 70% | 75% | 80% | 85% | 90% | 95%
| Cost Values | 4.7365 | 9.2438 | 10.5785 | 11.537 | 12.426 | 13.1938 | 13.8094 | 14.4699 | 15.1097 | 15.8011 | 16.5839 | 17.316 | 18.1877 | 18.981 | 20.0225 | 21.1412 | 22.4623 | 24.4604 | 26.779 | 31.0527
| Markers | 0%: Cost; 5%: Confidence
| Point Estimate | 0%: 13.5245; 5%: 27.93%
| Mean | 0%: 17.8867; 5%: 58.03%
| 50% Confidence Level | 0%: 16.5839; 5%: 50%
| 85% Confidence Level | 0%: 24.4604; 5%: 85%
Note on A1: Version=1.3 Type=RiskChart
Note on A4: culture=en-US Timestamp=6/10/2009 11:43:59 AM Heading=RI$K Chart for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit Appearance=CdfWithConfidenceMarkers ShowMethod=False ShowIterations=True ShowResultsType=True UseAllocatedResults=False ShowPointEstimate=True ShowMean=True IncludeComparativeMeans=False ShowAllocated=False ConfidenceLevel(0)=50 ConfidenceLabel(0)=50% Confidence Level ConfidenceLevel(1)=85 ConfidenceLabel(1)=85% Confidence Level Cases="Sanitized ACE Example for Demos V1 08JUN2009.aceit,Point Estimate" SelectedRow=ACE3516,"Acquisition Support (SE/PM, ST&E, Data)" RowFilter=Cost, NonCost BudgetRow=ACE3079,*Change Tracker from Prior Version ColorScheme=Standard
Note on A9: Version=1.3 Type=Chart Style=RiskChart Name=433F-96C2-44F4-52D1 Description=RI$K Chart Culture=en-US Timestamp=6/10/2009 11:43:59 AM Footprint=R10C4:R39C8 Locks=Title.Visibility,Title.Text,Title.Font,Title.Border,Title.Interior,Series.Type,Series.Color,Series.Pattern,Series.Effects,Series.LineWeight,Series.LineStyle,Series.MarkerStyle,Series.MarkerSize,XAxis.TitleText,XAxis.TitleFormat,XAxis.Line,XAxis.Labels,XAxis.Font,XAxis.NumberFormat,XAxis.Spacing,XAxis.TickMarks,XAxis.GridLines,XAxis.Crossing,XAxis.MinimumScale,XAxis.MaximumScale,YAxis.TitleText,YAxis.TitleFormat,YAxis.Line,YAxis.Labels,YAxis.Font,YAxis.NumberFormat,YAxis.Units,YAxis.TickMarks,YAxis.GridLines,YAxis.Crossing,YAxis.MinimumScale,YAxis.MaximumScale,Legend.Visibility,Legend.Position,Legend.Size,Legend.Font,Legend.Border,Legend.Interior,PlotArea.Position,PlotArea.Size,PlotArea.Border,PlotArea.Interior,Walls.Border,Walls.Interior
Note on A44: Version=1.3 Type=Table Style=RiskCostsForConfidenceTable Name=433F-96C2-79C3-D505 Description=RI$K Costs for Confidences Table Culture=en-US Timestamp=6/10/2009 11:43:59 AM Footprint=R45C4:R46C24 Locks=
Note on A47: Version=1.3 Type=Table Style=RiskConfidenceLevelsTable Name=433F-96C2-4C2A-E8A4 Description=RI$K Confidence Levels Table Culture=en-US Timestamp=6/10/2009 11:43:59 AM Footprint=R48C4:R52C6 Locks=

## Project #2 HW Mat S-Curve
POST Report
RI$K Chart for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit
Costs in $M (BY2005 Total), 2000 iterations
Wednesday, 10 June 2009, 11:43 am
RI$K Chart
RI$K Statistics in 5% intervals
| Cumulative Distribution Function | 0% | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% | 65% | 70% | 75% | 80% | 85% | 90% | 95%
| Cost Values | 0.14717 | 0.4814 | 0.61462 | 0.72444 | 0.8261 | 0.92404 | 1.0227 | 1.1225 | 1.2259 | 1.3361 | 1.4536 | 1.5818 | 1.7236 | 1.8838 | 2.067 | 2.2874 | 2.5582 | 2.9161 | 3.4395 | 4.3907
| Markers | 0%: Cost; 5%: Confidence
| Point Estimate | 0%: 1.4539; 5%: 50.01%
| Mean | 0%: 1.8219; 5%: 63.15%
| 50% Confidence Level | 0%: 1.4536; 5%: 50%
| 85% Confidence Level | 0%: 2.9161; 5%: 85%
Note on A1: Version=1.3 Type=RiskChart
Note on A4: culture=en-US Timestamp=6/10/2009 11:43:59 AM Heading=RI$K Chart for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit Appearance=CdfWithConfidenceMarkers ShowMethod=False ShowIterations=True ShowResultsType=True UseAllocatedResults=False ShowPointEstimate=True ShowMean=True IncludeComparativeMeans=False ShowAllocated=False ConfidenceLevel(0)=50 ConfidenceLabel(0)=50% Confidence Level ConfidenceLevel(1)=85 ConfidenceLabel(1)=85% Confidence Level Cases="Sanitized ACE Example for Demos V1 08JUN2009.aceit,Point Estimate" SelectedRow=ACE3496,Subsystem #1 Hardware Material Cost (SEER-H) Per String RowFilter=Cost, NonCost BudgetRow=ACE3079,*Change Tracker from Prior Version ColorScheme=Standard
Note on A9: Version=1.3 Type=Chart Style=RiskChart Name=433F-96C2-44F4-52D1 Description=RI$K Chart Culture=en-US Timestamp=6/10/2009 11:43:59 AM Footprint=R10C4:R39C8 Locks=Title.Visibility,Title.Text,Title.Font,Title.Border,Title.Interior,Series.Type,Series.Color,Series.Pattern,Series.Effects,Series.LineWeight,Series.LineStyle,Series.MarkerStyle,Series.MarkerSize,XAxis.TitleText,XAxis.TitleFormat,XAxis.Line,XAxis.Labels,XAxis.Font,XAxis.NumberFormat,XAxis.Spacing,XAxis.TickMarks,XAxis.GridLines,XAxis.Crossing,XAxis.MinimumScale,XAxis.MaximumScale,YAxis.TitleText,YAxis.TitleFormat,YAxis.Line,YAxis.Labels,YAxis.Font,YAxis.NumberFormat,YAxis.Units,YAxis.TickMarks,YAxis.GridLines,YAxis.Crossing,YAxis.MinimumScale,YAxis.MaximumScale,Legend.Visibility,Legend.Position,Legend.Size,Legend.Font,Legend.Border,Legend.Interior,PlotArea.Position,PlotArea.Size,PlotArea.Border,PlotArea.Interior,Walls.Border,Walls.Interior
Note on A44: Version=1.3 Type=Table Style=RiskCostsForConfidenceTable Name=433F-96C2-79C3-D505 Description=RI$K Costs for Confidences Table Culture=en-US Timestamp=6/10/2009 11:43:59 AM Footprint=R45C4:R46C24 Locks=
Note on A47: Version=1.3 Type=Table Style=RiskConfidenceLevelsTable Name=433F-96C2-4C2A-E8A4 Description=RI$K Confidence Levels Table Culture=en-US Timestamp=6/10/2009 11:43:59 AM Footprint=R48C4:R52C6 Locks=

## Project #2 HW Labor S-Curve
POST Report
RI$K Chart for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit
Costs in $M (BY2005 Total), 2000 iterations
Wednesday, 10 June 2009, 11:44 am
RI$K Chart
RI$K Statistics in 5% intervals
| Cumulative Distribution Function | 0% | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% | 65% | 70% | 75% | 80% | 85% | 90% | 95%
| Cost Values | 3528.7112 | 10183.0138 | 12314.1492 | 13988.4602 | 15490.3922 | 16892.4748 | 18268.7423 | 19637.4636 | 21028.7094 | 22479.1969 | 23995.9284 | 25624.3017 | 27382.4128 | 29335.4088 | 31539.0542 | 34100.0487 | 37202.0485 | 41172.2849 | 46778.3496 | 56560.5387
| Markers | 0%: Cost; 5%: Confidence
| Point Estimate | 0%: 24000; 5%: 50.01%
| Mean | 0%: 27489.9713; 5%: 60.3%
| 50% Confidence Level | 0%: 23995.9284; 5%: 50%
| 85% Confidence Level | 0%: 41172.2849; 5%: 85%
Note on A1: Version=1.3 Type=RiskChart
Note on A4: culture=en-US Timestamp=6/10/2009 11:44:04 AM Heading=RI$K Chart for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit Appearance=CdfWithConfidenceMarkers ShowMethod=False ShowIterations=True ShowResultsType=True UseAllocatedResults=False ShowPointEstimate=True ShowMean=True IncludeComparativeMeans=False ShowAllocated=False ConfidenceLevel(0)=50 ConfidenceLabel(0)=50% Confidence Level ConfidenceLevel(1)=85 ConfidenceLabel(1)=85% Confidence Level Cases="Sanitized ACE Example for Demos V1 08JUN2009.aceit,Point Estimate" SelectedRow=ACE3585,Subsystem #2 HW Development Labor Hours (SEER-H) RowFilter=Cost, NonCost ColorScheme=Standard
Note on A9: Version=1.3 Type=Chart Style=RiskChart Name=433F-96C2-44F4-52D1 Description=RI$K Chart Culture=en-US Timestamp=6/10/2009 11:44:04 AM Footprint=R10C4:R39C8 Locks=Title.Visibility,Title.Text,Title.Font,Title.Border,Title.Interior,Series.Type,Series.Color,Series.Pattern,Series.Effects,Series.LineWeight,Series.LineStyle,Series.MarkerStyle,Series.MarkerSize,XAxis.TitleText,XAxis.TitleFormat,XAxis.Line,XAxis.Labels,XAxis.Font,XAxis.NumberFormat,XAxis.Spacing,XAxis.TickMarks,XAxis.GridLines,XAxis.Crossing,XAxis.MinimumScale,XAxis.MaximumScale,YAxis.TitleText,YAxis.TitleFormat,YAxis.Line,YAxis.Labels,YAxis.Font,YAxis.NumberFormat,YAxis.Units,YAxis.TickMarks,YAxis.GridLines,YAxis.Crossing,YAxis.MinimumScale,YAxis.MaximumScale,Legend.Visibility,Legend.Position,Legend.Size,Legend.Font,Legend.Border,Legend.Interior,PlotArea.Position,PlotArea.Size,PlotArea.Border,PlotArea.Interior,Walls.Border,Walls.Interior
Note on A44: Version=1.3 Type=Table Style=RiskCostsForConfidenceTable Name=433F-96C2-79C3-D505 Description=RI$K Costs for Confidences Table Culture=en-US Timestamp=6/10/2009 11:44:04 AM Footprint=R45C4:R46C24 Locks=
Note on A47: Version=1.3 Type=Table Style=RiskConfidenceLevelsTable Name=433F-96C2-4C2A-E8A4 Description=RI$K Confidence Levels Table Culture=en-US Timestamp=6/10/2009 11:44:04 AM Footprint=R48C4:R52C6 Locks=

## Project #2 Labor Rate S-Curve
POST Report
RI$K Chart for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit
Costs in $M (BY2005 Total), 2000 iterations
Wednesday, 10 June 2009, 11:44 am
RI$K Chart
RI$K Statistics in 5% intervals
| Cumulative Distribution Function | 0% | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% | 65% | 70% | 75% | 80% | 85% | 90% | 95%
| Cost Values | 6.3068e-05 | 7.3421e-05 | 7.7882e-05 | 8.1326e-05 | 8.4206e-05 | 8.6764e-05 | 8.9074e-05 | 9.1188e-05 | 9.3225e-05 | 9.5326e-05 | 9.7535e-05 | 9.9853e-05 | 0.00010231 | 0.00010492 | 0.00010773 | 0.00011078 | 0.00011416 | 0.00011797 | 0.00012253 | 0.00012846
| Markers | 0%: Cost; 5%: Confidence
| Point Estimate | 0%: 9.1751e-05; 5%: 36.38%
| Mean | 0%: 9.9029e-05; 5%: 53.26%
| 50% Confidence Level | 0%: 9.7535e-05; 5%: 50%
| 85% Confidence Level | 0%: 0.00011797; 5%: 85%
Note on A1: Version=1.3 Type=RiskChart
Note on A4: culture=en-US Timestamp=6/10/2009 11:44:05 AM Heading=RI$K Chart for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit Appearance=CdfWithConfidenceMarkers ShowMethod=False ShowIterations=True ShowResultsType=True UseAllocatedResults=False ShowPointEstimate=True ShowMean=True IncludeComparativeMeans=False ShowAllocated=False ConfidenceLevel(0)=50 ConfidenceLabel(0)=50% Confidence Level ConfidenceLevel(1)=85 ConfidenceLabel(1)=85% Confidence Level Cases="Sanitized ACE Example for Demos V1 08JUN2009.aceit,Point Estimate" SelectedRow=ACE3356,"Avg Hourly Rate (Calculated from Actual Data Jan 2009) w/Travel, ODC" RowFilter=Cost, NonCost BudgetRow=ACE3079,*Change Tracker from Prior Version ColorScheme=Standard
Note on A9: Version=1.3 Type=Chart Style=RiskChart Name=433F-96C2-44F4-52D1 Description=RI$K Chart Culture=en-US Timestamp=6/10/2009 11:44:05 AM Footprint=R10C4:R39C8 Locks=Title.Visibility,Title.Text,Title.Font,Title.Border,Title.Interior,Series.Type,Series.Color,Series.Pattern,Series.Effects,Series.LineWeight,Series.LineStyle,Series.MarkerStyle,Series.MarkerSize,XAxis.TitleText,XAxis.TitleFormat,XAxis.Line,XAxis.Labels,XAxis.Font,XAxis.NumberFormat,XAxis.Spacing,XAxis.TickMarks,XAxis.GridLines,XAxis.Crossing,XAxis.MinimumScale,XAxis.MaximumScale,YAxis.TitleText,YAxis.TitleFormat,YAxis.Line,YAxis.Labels,YAxis.Font,YAxis.NumberFormat,YAxis.Units,YAxis.TickMarks,YAxis.GridLines,YAxis.Crossing,YAxis.MinimumScale,YAxis.MaximumScale,Legend.Visibility,Legend.Position,Legend.Size,Legend.Font,Legend.Border,Legend.Interior,PlotArea.Position,PlotArea.Size,PlotArea.Border,PlotArea.Interior,Walls.Border,Walls.Interior
Note on A44: Version=1.3 Type=Table Style=RiskCostsForConfidenceTable Name=433F-96C2-79C3-D505 Description=RI$K Costs for Confidences Table Culture=en-US Timestamp=6/10/2009 11:44:05 AM Footprint=R45C4:R46C24 Locks=
Note on A47: Version=1.3 Type=Table Style=RiskConfidenceLevelsTable Name=433F-96C2-4C2A-E8A4 Description=RI$K Confidence Levels Table Culture=en-US Timestamp=6/10/2009 11:44:05 AM Footprint=R48C4:R52C6 Locks=

## Project #2 SW Labor S-Curve
POST Report
RI$K Chart for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit
Costs in $M (BY2005 Total), 2000 iterations
Wednesday, 10 June 2009, 11:44 am
RI$K Chart
RI$K Statistics in 5% intervals
| Cumulative Distribution Function | 0% | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% | 65% | 70% | 75% | 80% | 85% | 90% | 95%
| Cost Values | 324.507 | 2032.4191 | 2886.0758 | 3664.7574 | 4425.5248 | 5203.8314 | 6016.763 | 6885.1211 | 7824.4535 | 8853.6429 | 9998.7415 | 11294.502 | 12787.6006 | 14523.8549 | 16618.9525 | 19227.5301 | 22606.2364 | 27305.0674 | 34599.6384 | 49138.6849
| Markers | 0%: Cost; 5%: Confidence
| Point Estimate | 0%: 10000; 5%: 50.01%
| Mean | 0%: 15985.7594; 5%: 68.6%
| 50% Confidence Level | 0%: 9998.7415; 5%: 50%
| 85% Confidence Level | 0%: 27305.0674; 5%: 85%
Note on A1: Version=1.3 Type=RiskChart
Note on A4: culture=en-US Timestamp=6/10/2009 11:44:05 AM Heading=RI$K Chart for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit Appearance=CdfWithConfidenceMarkers ShowMethod=False ShowIterations=True ShowResultsType=True UseAllocatedResults=False ShowPointEstimate=True ShowMean=True IncludeComparativeMeans=False ShowAllocated=False ConfidenceLevel(0)=50 ConfidenceLabel(0)=50% Confidence Level ConfidenceLevel(1)=85 ConfidenceLabel(1)=85% Confidence Level Cases="Sanitized ACE Example for Demos V1 08JUN2009.aceit,Point Estimate" SelectedRow=ACE4065,Subsystem #3 SW Labor Hours RowFilter=Cost, NonCost ColorScheme=Standard
Note on A9: Version=1.3 Type=Chart Style=RiskChart Name=433F-96C2-44F4-52D1 Description=RI$K Chart Culture=en-US Timestamp=6/10/2009 11:44:05 AM Footprint=R10C4:R39C8 Locks=Title.Visibility,Title.Text,Title.Font,Title.Border,Title.Interior,Series.Type,Series.Color,Series.Pattern,Series.Effects,Series.LineWeight,Series.LineStyle,Series.MarkerStyle,Series.MarkerSize,XAxis.TitleText,XAxis.TitleFormat,XAxis.Line,XAxis.Labels,XAxis.Font,XAxis.NumberFormat,XAxis.Spacing,XAxis.TickMarks,XAxis.GridLines,XAxis.Crossing,XAxis.MinimumScale,XAxis.MaximumScale,YAxis.TitleText,YAxis.TitleFormat,YAxis.Line,YAxis.Labels,YAxis.Font,YAxis.NumberFormat,YAxis.Units,YAxis.TickMarks,YAxis.GridLines,YAxis.Crossing,YAxis.MinimumScale,YAxis.MaximumScale,Legend.Visibility,Legend.Position,Legend.Size,Legend.Font,Legend.Border,Legend.Interior,PlotArea.Position,PlotArea.Size,PlotArea.Border,PlotArea.Interior,Walls.Border,Walls.Interior
Note on A44: Version=1.3 Type=Table Style=RiskCostsForConfidenceTable Name=433F-96C2-79C3-D505 Description=RI$K Costs for Confidences Table Culture=en-US Timestamp=6/10/2009 11:44:05 AM Footprint=R45C4:R46C24 Locks=
Note on A47: Version=1.3 Type=Table Style=RiskConfidenceLevelsTable Name=433F-96C2-4C2A-E8A4 Description=RI$K Confidence Levels Table Culture=en-US Timestamp=6/10/2009 11:44:05 AM Footprint=R48C4:R52C6 Locks=

## Project #2 IATCO Labor S-Curve
POST Report
RI$K Chart for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit
Costs in $M (BY2005 Total), 2000 iterations
Wednesday, 10 June 2009, 11:44 am
RI$K Chart
RI$K Statistics in 5% intervals
| Cumulative Distribution Function | 0% | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% | 65% | 70% | 75% | 80% | 85% | 90% | 95%
| Cost Values | 0.018525 | 0.063911 | 0.080366 | 0.093747 | 0.10599 | 0.11778 | 0.12944 | 0.1412 | 0.1535 | 0.16632 | 0.18 | 0.19482 | 0.21113 | 0.22941 | 0.25043 | 0.27512 | 0.30569 | 0.34542 | 0.40306 | 0.50682
| Markers | 0%: Cost; 5%: Confidence
| Point Estimate | 0%: 0.18; 5%: 50%
| Mean | 0%: 0.21953; 5%: 62.39%
| 50% Confidence Level | 0%: 0.18; 5%: 50%
| 85% Confidence Level | 0%: 0.34542; 5%: 85%
Note on A1: Version=1.3 Type=RiskChart
Note on A4: culture=en-US Timestamp=6/10/2009 11:44:06 AM Heading=RI$K Chart for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit Appearance=CdfWithConfidenceMarkers ShowMethod=False ShowIterations=True ShowResultsType=True UseAllocatedResults=False ShowPointEstimate=True ShowMean=True IncludeComparativeMeans=False ShowAllocated=False ConfidenceLevel(0)=50 ConfidenceLabel(0)=50% Confidence Level ConfidenceLevel(1)=85 ConfidenceLabel(1)=85% Confidence Level Cases="Sanitized ACE Example for Demos V1 08JUN2009.aceit,Point Estimate" SelectedRow=ACE4069,Project #2 IAT&CO % of HW & SW (Project #1 Actuals) RowFilter=Cost, NonCost ColorScheme=Standard
Note on A9: Version=1.3 Type=Chart Style=RiskChart Name=433F-96C2-44F4-52D1 Description=RI$K Chart Culture=en-US Timestamp=6/10/2009 11:44:06 AM Footprint=R10C4:R39C8 Locks=Title.Visibility,Title.Text,Title.Font,Title.Border,Title.Interior,Series.Type,Series.Color,Series.Pattern,Series.Effects,Series.LineWeight,Series.LineStyle,Series.MarkerStyle,Series.MarkerSize,XAxis.TitleText,XAxis.TitleFormat,XAxis.Line,XAxis.Labels,XAxis.Font,XAxis.NumberFormat,XAxis.Spacing,XAxis.TickMarks,XAxis.GridLines,XAxis.Crossing,XAxis.MinimumScale,XAxis.MaximumScale,YAxis.TitleText,YAxis.TitleFormat,YAxis.Line,YAxis.Labels,YAxis.Font,YAxis.NumberFormat,YAxis.Units,YAxis.TickMarks,YAxis.GridLines,YAxis.Crossing,YAxis.MinimumScale,YAxis.MaximumScale,Legend.Visibility,Legend.Position,Legend.Size,Legend.Font,Legend.Border,Legend.Interior,PlotArea.Position,PlotArea.Size,PlotArea.Border,PlotArea.Interior,Walls.Border,Walls.Interior
Note on A44: Version=1.3 Type=Table Style=RiskCostsForConfidenceTable Name=433F-96C2-79C3-D505 Description=RI$K Costs for Confidences Table Culture=en-US Timestamp=6/10/2009 11:44:06 AM Footprint=R45C4:R46C24 Locks=
Note on A47: Version=1.3 Type=Table Style=RiskConfidenceLevelsTable Name=433F-96C2-4C2A-E8A4 Description=RI$K Confidence Levels Table Culture=en-US Timestamp=6/10/2009 11:44:06 AM Footprint=R48C4:R52C6 Locks=

## Project #2 BY S-Curve
POST Report
RI$K Chart for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit
Costs in $M (BY2005 Total), 2000 iterations
Wednesday, 10 June 2009, 11:44 am
RI$K Chart
RI$K Statistics in 5% intervals
| Cumulative Distribution Function | 0% | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% | 65% | 70% | 75% | 80% | 85% | 90% | 95%
| Cost Values | 26.8685 | 40.4081 | 43.9645 | 46.7954 | 49.3097 | 51.3932 | 53.1971 | 55.1049 | 56.782 | 58.4248 | 60.6847 | 62.9148 | 65.0666 | 67.7413 | 70.6215 | 73.7417 | 77.9477 | 82.5971 | 88.3731 | 101.7724
| Markers | 0%: Cost; 5%: Confidence
| Point Estimate | 0%: 50.3466; 5%: 22.2%
| Mean | 0%: 64.4976; 5%: 58.32%
| 50% Confidence Level | 0%: 60.6847; 5%: 50%
| 80% Confidence Level | 0%: 77.9477; 5%: 80%
| Budget | 0%: 48.957; 5%: 19.3%
Note on A1: Version=1.3 Type=RiskChart
Note on A4: culture=en-US Timestamp=6/10/2009 11:44:06 AM Heading=RI$K Chart for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit Appearance=CdfWithConfidenceMarkers ShowMethod=False ShowIterations=True ShowResultsType=True UseAllocatedResults=False ShowPointEstimate=True ShowMean=True IncludeComparativeMeans=False ShowAllocated=False ConfidenceLevel(0)=50 ConfidenceLabel(0)=50% Confidence Level ConfidenceLevel(1)=80 ConfidenceLabel(1)=80% Confidence Level Cases="Sanitized ACE Example for Demos V1 08JUN2009.aceit,Point Estimate" SelectedRow=ACE3430,Project #2 RDT&E RowFilter=Cost, NonCost BudgetRow=ACE4090,RDTE APPROVED FUNDING (PROJECT #2 FALLOUT) ColorScheme=Standard
Note on A9: Version=1.3 Type=Chart Style=RiskChart Name=200E-B210-0636-1A12 Description=RI$K Chart Culture=en-US Timestamp=6/10/2009 11:44:06 AM Footprint=R10C4:R39C8 Locks=Title.Visibility,Title.Text,Title.Font,Title.Border,Title.Interior,Series.Type,Series.Color,Series.Pattern,Series.Effects,Series.LineWeight,Series.LineStyle,Series.MarkerStyle,Series.MarkerSize,XAxis.TitleText,XAxis.TitleFormat,XAxis.Line,XAxis.Labels,XAxis.Font,XAxis.NumberFormat,XAxis.Spacing,XAxis.TickMarks,XAxis.GridLines,XAxis.Crossing,XAxis.MinimumScale,XAxis.MaximumScale,YAxis.TitleText,YAxis.TitleFormat,YAxis.Line,YAxis.Labels,YAxis.Font,YAxis.NumberFormat,YAxis.Units,YAxis.TickMarks,YAxis.GridLines,YAxis.Crossing,YAxis.MinimumScale,YAxis.MaximumScale,Legend.Visibility,Legend.Position,Legend.Size,Legend.Font,Legend.Border,Legend.Interior,PlotArea.Position,PlotArea.Size,PlotArea.Border,PlotArea.Interior,Walls.Border,Walls.Interior
Note on A44: Version=1.3 Type=Table Style=RiskCostsForConfidenceTable Name=200E-B210-4E59-5BB5 Description=RI$K Costs for Confidences Table Culture=en-US Timestamp=6/10/2009 11:44:06 AM Footprint=R45C4:R46C24 Locks=
Note on A47: Version=1.3 Type=Table Style=RiskConfidenceLevelsTable Name=200E-B210-1394-FC50 Description=RI$K Confidence Levels Table Culture=en-US Timestamp=6/10/2009 11:44:06 AM Footprint=R48C4:R53C6 Locks=

## Project #2 TY S-Curve
POST Report
RI$K Chart for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit
Funding Requirement in $M (TY Total), 2000 iterations
Wednesday, 10 June 2009, 11:44 am
RI$K Chart
RI$K Statistics in 5% intervals
| Cumulative Distribution Function | 0% | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% | 65% | 70% | 75% | 80% | 85% | 90% | 95%
| Cost Values | 30.5823 | 45.9934 | 50.0414 | 53.2637 | 56.1254 | 58.497 | 60.5502 | 62.7217 | 64.6306 | 66.5005 | 69.0728 | 71.611 | 74.0603 | 77.1047 | 80.383 | 83.9345 | 88.7219 | 94.014 | 100.5884 | 115.8397
| Markers | 0%: Cost; 5%: Confidence
| Point Estimate | 0%: 57.3057; 5%: 22.2%
| Mean | 0%: 73.4126; 5%: 58.32%
| 50% Confidence Level | 0%: 69.0728; 5%: 50%
| 80% Confidence Level | 0%: 88.7219; 5%: 80%
Note on A1: Version=1.3 Type=RiskChart
Note on A4: culture=en-US Timestamp=6/10/2009 11:44:06 AM Heading=RI$K Chart for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit Appearance=CdfWithConfidenceMarkers ShowMethod=False ShowIterations=True ShowResultsType=True UseAllocatedResults=False ShowPointEstimate=True ShowMean=True IncludeComparativeMeans=False ShowAllocated=False ConfidenceLevel(0)=50 ConfidenceLabel(0)=50% Confidence Level ConfidenceLevel(1)=80 ConfidenceLabel(1)=80% Confidence Level Inflation=ThenYear Cases="Sanitized ACE Example for Demos V1 08JUN2009.aceit,Point Estimate" SelectedRow=ACE3430,Project #2 RDT&E RowFilter=Cost, NonCost ColorScheme=Standard
Note on A9: Version=1.3 Type=Chart Style=RiskChart Name=200E-B210-0636-1A12 Description=RI$K Chart Culture=en-US Timestamp=6/10/2009 11:44:07 AM Footprint=R10C4:R39C8 Locks=Title.Visibility,Title.Text,Title.Font,Title.Border,Title.Interior,Series.Type,Series.Color,Series.Pattern,Series.Effects,Series.LineWeight,Series.LineStyle,Series.MarkerStyle,Series.MarkerSize,XAxis.TitleText,XAxis.TitleFormat,XAxis.Line,XAxis.Labels,XAxis.Font,XAxis.NumberFormat,XAxis.Spacing,XAxis.TickMarks,XAxis.GridLines,XAxis.Crossing,XAxis.MinimumScale,XAxis.MaximumScale,YAxis.TitleText,YAxis.TitleFormat,YAxis.Line,YAxis.Labels,YAxis.Font,YAxis.NumberFormat,YAxis.Units,YAxis.TickMarks,YAxis.GridLines,YAxis.Crossing,YAxis.MinimumScale,YAxis.MaximumScale,Legend.Visibility,Legend.Position,Legend.Size,Legend.Font,Legend.Border,Legend.Interior,PlotArea.Position,PlotArea.Size,PlotArea.Border,PlotArea.Interior,Walls.Border,Walls.Interior
Note on A44: Version=1.3 Type=Table Style=RiskCostsForConfidenceTable Name=200E-B210-4E59-5BB5 Description=RI$K Costs for Confidences Table Culture=en-US Timestamp=6/10/2009 11:44:07 AM Footprint=R45C4:R46C24 Locks=
Note on A47: Version=1.3 Type=Table Style=RiskConfidenceLevelsTable Name=200E-B210-1394-FC50 Description=RI$K Confidence Levels Table Culture=en-US Timestamp=6/10/2009 11:44:07 AM Footprint=R48C4:R52C6 Locks=

## Project #2 Acq Sup PDF
POST Report
RI$K Chart for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit
Costs in $M (BY2005 Total), 2000 iterations, 100 bins
Wednesday, 10 June 2009, 11:44 am
RI$K Chart
RI$K Statistics in 100 bins
| Cost Values | 4.7365 | 5.3707 | 6.0048 | 6.639 | 7.2731 | 7.9073 | 8.5414 | 9.1756 | 9.8097 | 10.4438 | 11.078 | 11.7121 | 12.3463 | 12.9804 | 13.6146 | 14.2487 | 14.8829 | 15.517 | 16.1512 | 16.7853 | 17.4194 | 18.0536 | 18.6877 | 19.3219 | 19.956 | 20.5902 | 21.2243 | 21.8585 | 22.4926 | 23.1267 | 23.7609 | 24.395 | 25.0292 | 25.6633 | 26.2975 | 26.9316 | 27.5658 | 28.1999 | 28.8341 | 29.4682 | 30.1023 | 30.7365 | 31.3706 | 32.0048 | 32.6389 | 33.2731 | 33.9072 | 34.5414 | 35.1755 | 35.8096 | 36.4438 | 37.0779 | 37.7121 | 38.3462 | 38.9804 | 39.6145 | 40.2487 | 40.8828 | 41.517 | 42.1511 | 42.7852 | 43.4194 | 44.0535 | 44.6877 | 45.3218 | 45.956 | 46.5901 | 47.2243 | 47.8584 | 48.4925 | 49.1267 | 49.7608 | 50.395 | 51.0291 | 51.6633 | 52.2974 | 52.9316 | 53.5657 | 54.1999 | 54.834 | 55.4681 | 56.1023 | 56.7364 | 57.3706 | 58.0047 | 58.6389 | 59.273 | 59.9072 | 60.5413 | 61.1755 | 61.8096 | 62.4437 | 63.0779 | 63.712 | 64.3462 | 64.9803 | 65.6145 | 66.2486 | 66.8828 | 67.5169
| Cumulative Distribution Function |  | 0.1646% | 0.3328% | 0.7158% | 1.451% | 2.362% | 3.433% | 4.893% | 7.395% | 9.495% | 12.12% | 16.07% | 19.22% | 23.43% | 28.52% | 33.21% | 37.86% | 42.97% | 46.82% | 51.21% | 55.5% | 59.18% | 63.31% | 66.31% | 69.65% | 72.76% | 75.32% | 77.8% | 80.21% | 81.9% | 83.43% | 84.76% | 86.65% | 88.57% | 89.31% | 90.18% | 91.03% | 91.87% | 92.83% | 93.33% | 93.8% | 94.61% | 95.42% | 95.83% | 96.02% | 96.4% | 96.64% | 96.98% | 97.16% | 97.53% | 97.72% | 97.99% | 98.18% | 98.33% | 98.48% | 98.69% | 98.94% | 99.08% | 99.11% | 99.21% | 99.39% | 99.45% | 99.51% | 99.59% | 99.61% | 99.71% | 99.74% | 99.75% | 99.76% | 99.78% | 99.81% | 99.86% | 99.88% | 99.89% | 99.89% | 99.9% | 99.91% | 99.92% | 99.92% | 99.93% | 99.93% | 99.93% | 99.93% | 99.94% | 99.94% | 99.94% | 99.94% | 99.95% | 99.95% | 99.95% | 99.95% | 99.96% | 99.96% | 99.96% | 99.96% | 99.97% | 99.97% | 99.97% | 99.97% | 100%
| Probability Histogram |  | 0.1646% | 0.1682% | 0.383% | 0.7347% | 0.9118% | 1.071% | 1.46% | 2.502% | 2.1% | 2.623% | 3.949% | 3.154% | 4.209% | 5.088% | 4.691% | 4.656% | 5.103% | 3.855% | 4.39% | 4.29% | 3.679% | 4.133% | 3.001% | 3.336% | 3.109% | 2.564% | 2.473% | 2.411% | 1.691% | 1.528% | 1.329% | 1.896% | 1.914% | 0.7469% | 0.8652% | 0.8529% | 0.8389% | 0.959% | 0.5005% | 0.4692% | 0.8064% | 0.8125% | 0.4097% | 0.1957% | 0.3754% | 0.2418% | 0.3392% | 0.1804% | 0.3697% | 0.1903% | 0.2689% | 0.1923% | 0.145% | 0.1571% | 0.2064% | 0.2472% | 0.1427% | 0.0286% | 0.0961% | 0.1865% | 0.0626% | 0.0561% | 0.0786% | 0.0206% | 0.0961% | 0.0309% | 0.0137% | 0.0138% | 0.0175% | 0.0294% | 0.0488% | 0.0206% | 0.0069% | 0.0072% | 0.0069% | 0.0069% | 0.0072% | 0.0069% | 0.0042% | 0.0023% | 0.0026% | 0.0023% | 0.0023% | 0.0027% | 0.0023% | 0.0023% | 0.0026% | 0.0023% | 0.0023% | 0.0027% | 0.0023% | 0.0022% | 0.0027% | 0.0023% | 0.0027% | 0.0023% | 0.0023% | 0.0026% | 0.0273%
Note on A1: Version=1.3 Type=RiskChart
Note on A4: culture=en-US Timestamp=6/10/2009 11:44:07 AM Heading=RI$K Chart for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit Appearance=HistogramWithCdf ShowMethod=False ShowIterations=True ShowResultsType=True UseAllocatedResults=False Cases="Sanitized ACE Example for Demos V1 08JUN2009.aceit,Point Estimate" SelectedRow=ACE3516,"Acquisition Support (SE/PM, ST&E, Data)" RowFilter=Cost, NonCost BudgetRow=ACE3079,*Change Tracker from Prior Version ColorScheme=Standard
Note on A9: Version=1.3 Type=Chart Style=RiskChart Name=433F-96C2-44F4-52D1 Description=RI$K Chart Culture=en-US Timestamp=6/10/2009 11:44:07 AM Footprint=R10C4:R39C8 Locks=
Note on A44: Version=1.3 Type=Table Style=RiskCostsInBinsTable Name=433F-96C2-79C3-D505 Description=RI$K Costs in Bins Table Culture=en-US Timestamp=6/10/2009 11:44:07 AM Footprint=R45C4:R47C104 Locks=
Note on A48: Version=1.3 Type=Table Style=RiskConfidenceLevelsTable Name=433F-96C2-4C2A-E8A4 Description=RI$K Confidence Levels Table Culture=en-US Timestamp=6/8/2009 2:33:00 PM Footprint=R48C4:R52C6 Locks=

## Project #2 HW Mat PDF
POST Report
RI$K Chart for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit
Costs in $M (BY2005 Total), 2000 iterations, 100 bins
Wednesday, 10 June 2009, 11:44 am
RI$K Chart
RI$K Statistics in 100 bins
| Cost Values | 0.14717 | 0.30087 | 0.45456 | 0.60826 | 0.76196 | 0.91566 | 1.0694 | 1.223 | 1.3767 | 1.5304 | 1.6841 | 1.8378 | 1.9915 | 2.1452 | 2.2989 | 2.4526 | 2.6063 | 2.76 | 2.9137 | 3.0674 | 3.2211 | 3.3748 | 3.5285 | 3.6822 | 3.8359 | 3.9896 | 4.1433 | 4.297 | 4.4507 | 4.6044 | 4.7581 | 4.9118 | 5.0655 | 5.2192 | 5.3729 | 5.5266 | 5.6803 | 5.834 | 5.9877 | 6.1414 | 6.2951 | 6.4488 | 6.6025 | 6.7561 | 6.9098 | 7.0635 | 7.2172 | 7.3709 | 7.5246 | 7.6783 | 7.832 | 7.9857 | 8.1394 | 8.2931 | 8.4468 | 8.6005 | 8.7542 | 8.9079 | 9.0616 | 9.2153 | 9.369 | 9.5227 | 9.6764 | 9.8301 | 9.9838 | 10.1375 | 10.2912 | 10.4449 | 10.5986 | 10.7523 | 10.906 | 11.0597 | 11.2134 | 11.3671 | 11.5208 | 11.6745 | 11.8282 | 11.9819 | 12.1355 | 12.2892 | 12.4429 | 12.5966 | 12.7503 | 12.904 | 13.0577 | 13.2114 | 13.3651 | 13.5188 | 13.6725 | 13.8262 | 13.9799 | 14.1336 | 14.2873 | 14.441 | 14.5947 | 14.7484 | 14.9021 | 15.0558 | 15.2095 | 15.3632
| Cumulative Distribution Function |  | 0.9741% | 4.184% | 9.722% | 16.81% | 24.58% | 32.38% | 39.86% | 46.78% | 53.03% | 58.66% | 63.66% | 68.04% | 71.89% | 75.24% | 78.17% | 80.78% | 83.01% | 84.97% | 86.69% | 88.17% | 89.5% | 90.66% | 91.66% | 92.55% | 93.36% | 94.06% | 94.69% | 95.19% | 95.67% | 96.12% | 96.5% | 96.86% | 97.13% | 97.43% | 97.65% | 97.87% | 98.07% | 98.22% | 98.39% | 98.54% | 98.66% | 98.77% | 98.9% | 98.98% | 99.07% | 99.13% | 99.21% | 99.27% | 99.34% | 99.39% | 99.42% | 99.48% | 99.51% | 99.54% | 99.58% | 99.63% | 99.65% | 99.66% | 99.68% | 99.7% | 99.73% | 99.78% | 99.8% | 99.81% | 99.83% | 99.83% | 99.84% | 99.84% | 99.85% | 99.85% | 99.86% | 99.86% | 99.87% | 99.87% | 99.88% | 99.89% | 99.9% | 99.91% | 99.91% | 99.92% | 99.93% | 99.93% | 99.93% | 99.94% | 99.94% | 99.94% | 99.94% | 99.95% | 99.95% | 99.95% | 99.95% | 99.96% | 99.96% | 99.96% | 99.96% | 99.97% | 99.97% | 99.97% | 100%
| Probability Histogram |  | 0.9741% | 3.21% | 5.537% | 7.087% | 7.767% | 7.804% | 7.482% | 6.914% | 6.256% | 5.632% | 4.996% | 4.378% | 3.851% | 3.355% | 2.931% | 2.602% | 2.237% | 1.955% | 1.723% | 1.477% | 1.332% | 1.155% | 1.009% | 0.8896% | 0.8038% | 0.7038% | 0.6286% | 0.5001% | 0.483% | 0.4494% | 0.373% | 0.3605% | 0.2693% | 0.3052% | 0.2228% | 0.2167% | 0.201% | 0.1514% | 0.1675% | 0.1461% | 0.1221% | 0.1163% | 0.1213% | 0.0874% | 0.0873% | 0.0557% | 0.0802% | 0.0598% | 0.0786% | 0.0469% | 0.0275% | 0.0595% | 0.0309% | 0.034% | 0.0412% | 0.0465% | 0.0164% | 0.016% | 0.0183% | 0.0226% | 0.0251% | 0.0477% | 0.0183% | 0.018% | 0.0133% | 0.005% | 0.0053% | 0.005% | 0.0053% | 0.005% | 0.0049% | 0.0054% | 0.0049% | 0.0054% | 0.0072% | 0.0084% | 0.0084% | 0.0088% | 0.0084% | 0.0084% | 0.0041% | 0.0027% | 0.0027% | 0.0027% | 0.0026% | 0.0027% | 0.0027% | 0.0026% | 0.0027% | 0.0027% | 0.0027% | 0.0026% | 0.0027% | 0.0027% | 0.0026% | 0.0027% | 0.0027% | 0.0026% | 0.0277%
Note on A1: Version=1.3 Type=RiskChart
Note on A4: culture=en-US Timestamp=6/10/2009 11:44:08 AM Heading=RI$K Chart for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit Appearance=HistogramWithCdf ShowMethod=False ShowIterations=True ShowResultsType=True UseAllocatedResults=False Cases="Sanitized ACE Example for Demos V1 08JUN2009.aceit,Point Estimate" SelectedRow=ACE3496,Subsystem #1 Hardware Material Cost (SEER-H) Per String RowFilter=Cost, NonCost BudgetRow=ACE3079,*Change Tracker from Prior Version ColorScheme=Standard
Note on A9: Version=1.3 Type=Chart Style=RiskChart Name=433F-96C2-44F4-52D1 Description=RI$K Chart Culture=en-US Timestamp=6/10/2009 11:44:08 AM Footprint=R10C4:R39C8 Locks=
Note on A44: Version=1.3 Type=Table Style=RiskCostsInBinsTable Name=433F-96C2-79C3-D505 Description=RI$K Costs in Bins Table Culture=en-US Timestamp=6/10/2009 11:44:08 AM Footprint=R45C4:R47C104 Locks=
Note on A48: Version=1.3 Type=Table Style=RiskConfidenceLevelsTable Name=433F-96C2-4C2A-E8A4 Description=RI$K Confidence Levels Table Culture=en-US Timestamp=6/8/2009 2:22:27 PM Footprint=R48C4:R52C6 Locks=

## Project #2 HW Labor PDF
POST Report
RI$K Chart for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit
Costs in $M (BY2005 Total), 2000 iterations, 100 bins
Wednesday, 10 June 2009, 11:44 am
RI$K Chart
RI$K Statistics in 100 bins
| Cost Values | 3528.7112 | 5134.7358 | 6740.7605 | 8346.7851 | 9952.8097 | 11558.8344 | 13164.859 | 14770.8836 | 16376.9082 | 17982.9329 | 19588.9575 | 21194.9821 | 22801.0067 | 24407.0314 | 26013.056 | 27619.0806 | 29225.1052 | 30831.1299 | 32437.1545 | 34043.1791 | 35649.2037 | 37255.2284 | 38861.253 | 40467.2776 | 42073.3022 | 43679.3269 | 45285.3515 | 46891.3761 | 48497.4007 | 50103.4254 | 51709.45 | 53315.4746 | 54921.4993 | 56527.5239 | 58133.5485 | 59739.5731 | 61345.5978 | 62951.6224 | 64557.647 | 66163.6716 | 67769.6963 | 69375.7209 | 70981.7455 | 72587.7701 | 74193.7948 | 75799.8194 | 77405.844 | 79011.8686 | 80617.8933 | 82223.9179 | 83829.9425 | 85435.9671 | 87041.9918 | 88648.0164 | 90254.041 | 91860.0656 | 93466.0903 | 95072.1149 | 96678.1395 | 98284.1642 | 99890.1888 | 101496.2134 | 103102.238 | 104708.2627 | 106314.2873 | 107920.3119 | 109526.3365 | 111132.3612 | 112738.3858 | 114344.4104 | 115950.435 | 117556.4597 | 119162.4843 | 120768.5089 | 122374.5335 | 123980.5582 | 125586.5828 | 127192.6074 | 128798.632 | 130404.6567 | 132010.6813 | 133616.7059 | 135222.7305 | 136828.7552 | 138434.7798 | 140040.8044 | 141646.8291 | 143252.8537 | 144858.8783 | 146464.9029 | 148070.9276 | 149676.9522 | 151282.9768 | 152889.0014 | 154495.0261 | 156101.0507 | 157707.0753 | 159313.0999 | 160919.1246 | 162525.1492
| Cumulative Distribution Function |  | 0.1612% | 0.7242% | 2.109% | 4.532% | 8.014% | 12.45% | 17.57% | 23.16% | 28.98% | 34.82% | 40.56% | 46.07% | 51.27% | 56.15% | 60.61% | 64.72% | 68.47% | 71.84% | 74.91% | 77.63% | 80.08% | 82.24% | 84.23% | 85.94% | 87.5% | 88.86% | 90.09% | 91.16% | 92.12% | 92.99% | 93.74% | 94.4% | 94.99% | 95.53% | 96.02% | 96.43% | 96.8% | 97.12% | 97.41% | 97.69% | 97.91% | 98.12% | 98.32% | 98.49% | 98.65% | 98.78% | 98.88% | 99.01% | 99.1% | 99.19% | 99.28% | 99.32% | 99.38% | 99.47% | 99.5% | 99.53% | 99.6% | 99.64% | 99.67% | 99.7% | 99.72% | 99.74% | 99.76% | 99.77% | 99.81% | 99.83% | 99.84% | 99.86% | 99.87% | 99.88% | 99.88% | 99.89% | 99.89% | 99.9% | 99.9% | 99.91% | 99.91% | 99.92% | 99.92% | 99.92% | 99.93% | 99.93% | 99.93% | 99.94% | 99.94% | 99.94% | 99.94% | 99.95% | 99.95% | 99.95% | 99.95% | 99.96% | 99.96% | 99.96% | 99.96% | 99.97% | 99.97% | 99.97% | 99.98%
| Probability Histogram |  | 0.1612% | 0.563% | 1.384% | 2.423% | 3.483% | 4.432% | 5.123% | 5.594% | 5.819% | 5.838% | 5.738% | 5.508% | 5.206% | 4.875% | 4.464% | 4.104% | 3.755% | 3.368% | 3.071% | 2.718% | 2.454% | 2.163% | 1.99% | 1.708% | 1.561% | 1.357% | 1.234% | 1.07% | 0.9568% | 0.8689% | 0.75% | 0.6573% | 0.5943% | 0.5364% | 0.4875% | 0.4192% | 0.3628% | 0.3235% | 0.2865% | 0.2857% | 0.2155% | 0.214% | 0.1984% | 0.1663% | 0.1648% | 0.1255% | 0.0996% | 0.1312% | 0.0877% | 0.0969% | 0.0843% | 0.0397% | 0.0664% | 0.085% | 0.0306% | 0.032% | 0.0729% | 0.0358% | 0.0294% | 0.0267% | 0.0259% | 0.0183% | 0.0172% | 0.0168% | 0.0397% | 0.0198% | 0.0115% | 0.011% | 0.0115% | 0.0091% | 0.005% | 0.0049% | 0.0046% | 0.005% | 0.0049% | 0.0046% | 0.005% | 0.0049% | 0.0046% | 0.005% | 0.0026% | 0.0027% | 0.0027% | 0.0026% | 0.0027% | 0.0027% | 0.0027% | 0.0026% | 0.0027% | 0.0027% | 0.0026% | 0.0027% | 0.0023% | 0.0027% | 0.0026% | 0.0027% | 0.0027% | 0.0026% | 0.0027%
Note on A1: Version=1.3 Type=RiskChart
Note on A4: culture=en-US Timestamp=6/10/2009 11:44:09 AM Heading=RI$K Chart for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit Appearance=HistogramWithCdf ShowMethod=False ShowIterations=True ShowResultsType=True UseAllocatedResults=False Cases="Sanitized ACE Example for Demos V1 08JUN2009.aceit,Point Estimate" SelectedRow=ACE3585,Subsystem #2 HW Development Labor Hours (SEER-H) RowFilter=Cost, NonCost BudgetRow=ACE3079,*Change Tracker from Prior Version ColorScheme=Standard
Note on A9: Version=1.3 Type=Chart Style=RiskChart Name=433F-96C2-44F4-52D1 Description=RI$K Chart Culture=en-US Timestamp=6/10/2009 11:44:09 AM Footprint=R10C4:R39C8 Locks=
Note on A44: Version=1.3 Type=Table Style=RiskCostsInBinsTable Name=433F-96C2-79C3-D505 Description=RI$K Costs in Bins Table Culture=en-US Timestamp=6/10/2009 11:44:09 AM Footprint=R45C4:R47C104 Locks=
Note on A48: Version=1.3 Type=Table Style=RiskConfidenceLevelsTable Name=433F-96C2-4C2A-E8A4 Description=RI$K Confidence Levels Table Culture=en-US Timestamp=6/8/2009 2:22:28 PM Footprint=R48C4:R52C6 Locks=

## Project #2 Labor Rate PDF
POST Report
RI$K Chart for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit
Costs in $M (BY2005 Total), 2000 iterations, 100 bins
Wednesday, 10 June 2009, 11:44 am
RI$K Chart
RI$K Statistics in 100 bins
| Cost Values | 6.3068e-05 | 6.3868e-05 | 6.4668e-05 | 6.5469e-05 | 6.6269e-05 | 6.7069e-05 | 6.787e-05 | 6.867e-05 | 6.947e-05 | 7.0271e-05 | 7.1071e-05 | 7.1871e-05 | 7.2672e-05 | 7.3472e-05 | 7.4272e-05 | 7.5073e-05 | 7.5873e-05 | 7.6673e-05 | 7.7474e-05 | 7.8274e-05 | 7.9074e-05 | 7.9875e-05 | 8.0675e-05 | 8.1475e-05 | 8.2276e-05 | 8.3076e-05 | 8.3876e-05 | 8.4677e-05 | 8.5477e-05 | 8.6277e-05 | 8.7078e-05 | 8.7878e-05 | 8.8678e-05 | 8.9479e-05 | 9.0279e-05 | 9.1079e-05 | 9.188e-05 | 9.268e-05 | 9.348e-05 | 9.4281e-05 | 9.5081e-05 | 9.5881e-05 | 9.6682e-05 | 9.7482e-05 | 9.8282e-05 | 9.9083e-05 | 9.9883e-05 | 0.00010068 | 0.00010148 | 0.00010228 | 0.00010308 | 0.00010388 | 0.00010468 | 0.00010549 | 0.00010629 | 0.00010709 | 0.00010789 | 0.00010869 | 0.00010949 | 0.00011029 | 0.00011109 | 0.00011189 | 0.00011269 | 0.00011349 | 0.00011429 | 0.00011509 | 0.00011589 | 0.00011669 | 0.00011749 | 0.00011829 | 0.00011909 | 0.00011989 | 0.00012069 | 0.00012149 | 0.00012229 | 0.00012309 | 0.00012389 | 0.00012469 | 0.00012549 | 0.00012629 | 0.00012709 | 0.00012789 | 0.00012869 | 0.0001295 | 0.0001303 | 0.0001311 | 0.0001319 | 0.0001327 | 0.0001335 | 0.0001343 | 0.0001351 | 0.0001359 | 0.0001367 | 0.0001375 | 0.0001383 | 0.0001391 | 0.0001399 | 0.0001407 | 0.0001415 | 0.0001423
| Cumulative Distribution Function |  | 0.1005% | 0.1955% | 0.3408% | 0.5629% | 0.873% | 1.186% | 1.584% | 2.043% | 2.506% | 3.073% | 3.691% | 4.352% | 5.082% | 5.846% | 6.655% | 7.545% | 8.505% | 9.495% | 10.54% | 11.62% | 12.77% | 14% | 15.24% | 16.58% | 17.95% | 19.38% | 20.88% | 22.41% | 24.01% | 25.64% | 27.38% | 29.11% | 30.91% | 32.8% | 34.72% | 36.7% | 38.7% | 40.63% | 42.53% | 44.42% | 46.28% | 48.11% | 49.87% | 51.64% | 53.38% | 55.05% | 56.7% | 58.35% | 59.92% | 61.51% | 63.06% | 64.56% | 66.02% | 67.47% | 68.87% | 70.26% | 71.62% | 72.92% | 74.22% | 75.49% | 76.7% | 77.92% | 79.07% | 80.19% | 81.3% | 82.35% | 83.38% | 84.38% | 85.36% | 86.31% | 87.23% | 88.11% | 88.96% | 89.77% | 90.55% | 91.3% | 92.03% | 92.71% | 93.37% | 94.03% | 94.6% | 95.18% | 95.71% | 96.23% | 96.67% | 97.14% | 97.53% | 97.9% | 98.26% | 98.58% | 98.84% | 99.12% | 99.33% | 99.54% | 99.67% | 99.78% | 99.9% | 99.94% | 100%
| Probability Histogram |  | 0.1005% | 0.095% | 0.1453% | 0.2221% | 0.3101% | 0.3128% | 0.3986% | 0.4589% | 0.4631% | 0.5665% | 0.6184% | 0.6603% | 0.7301% | 0.7638% | 0.8098% | 0.8896% | 0.9602% | 0.9895% | 1.042% | 1.085% | 1.144% | 1.232% | 1.245% | 1.339% | 1.365% | 1.437% | 1.495% | 1.534% | 1.595% | 1.629% | 1.742% | 1.731% | 1.799% | 1.887% | 1.921% | 1.982% | 1.997% | 1.934% | 1.9% | 1.884% | 1.863% | 1.83% | 1.758% | 1.769% | 1.746% | 1.664% | 1.653% | 1.656% | 1.57% | 1.584% | 1.552% | 1.499% | 1.459% | 1.45% | 1.406% | 1.387% | 1.364% | 1.291% | 1.306% | 1.266% | 1.212% | 1.218% | 1.149% | 1.126% | 1.112% | 1.043% | 1.039% | 0.9968% | 0.9781% | 0.9456% | 0.9293% | 0.8774% | 0.8461% | 0.8136% | 0.7763% | 0.7485% | 0.7313% | 0.6843% | 0.6535% | 0.6633% | 0.5681% | 0.5825% | 0.5287% | 0.5199% | 0.4395% | 0.4684% | 0.3952% | 0.37% | 0.3598% | 0.32% | 0.2632% | 0.2728% | 0.2079% | 0.2106% | 0.1323% | 0.1126% | 0.119% | 0.0442% | 0.0563%
Note on A1: Version=1.3 Type=RiskChart
Note on A4: culture=en-US Timestamp=6/10/2009 11:44:09 AM Heading=RI$K Chart for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit Appearance=HistogramWithCdf ShowMethod=False ShowIterations=True ShowResultsType=True UseAllocatedResults=False Cases="Sanitized ACE Example for Demos V1 08JUN2009.aceit,Point Estimate" SelectedRow=ACE3356,"Avg Hourly Rate (Calculated from Actual Data Jan 2009) w/Travel, ODC" RowFilter=Cost, NonCost BudgetRow=ACE3079,*Change Tracker from Prior Version ColorScheme=Standard
Note on A9: Version=1.3 Type=Chart Style=RiskChart Name=433F-96C2-44F4-52D1 Description=RI$K Chart Culture=en-US Timestamp=6/10/2009 11:44:10 AM Footprint=R10C4:R39C8 Locks=
Note on A44: Version=1.3 Type=Table Style=RiskCostsInBinsTable Name=433F-96C2-79C3-D505 Description=RI$K Costs in Bins Table Culture=en-US Timestamp=6/10/2009 11:44:10 AM Footprint=R45C4:R47C104 Locks=
Note on A48: Version=1.3 Type=Table Style=RiskConfidenceLevelsTable Name=433F-96C2-4C2A-E8A4 Description=RI$K Confidence Levels Table Culture=en-US Timestamp=6/8/2009 2:22:29 PM Footprint=R48C4:R52C6 Locks=

## Project #2 IATCO Labor PDF
POST Report
RI$K Chart for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit
Costs in $M (BY2005 Total), 2000 iterations, 100 bins
Wednesday, 10 June 2009, 11:44 am
RI$K Chart
RI$K Statistics in 100 bins
| Cost Values | 0.018525 | 0.036843 | 0.055162 | 0.07348 | 0.091798 | 0.11012 | 0.12843 | 0.14675 | 0.16507 | 0.18339 | 0.20171 | 0.22002 | 0.23834 | 0.25666 | 0.27498 | 0.2933 | 0.31162 | 0.32993 | 0.34825 | 0.36657 | 0.38489 | 0.40321 | 0.42152 | 0.43984 | 0.45816 | 0.47648 | 0.4948 | 0.51311 | 0.53143 | 0.54975 | 0.56807 | 0.58639 | 0.60471 | 0.62302 | 0.64134 | 0.65966 | 0.67798 | 0.6963 | 0.71461 | 0.73293 | 0.75125 | 0.76957 | 0.78789 | 0.8062 | 0.82452 | 0.84284 | 0.86116 | 0.87948 | 0.89779 | 0.91611 | 0.93443 | 0.95275 | 0.97107 | 0.98939 | 1.0077 | 1.026 | 1.0443 | 1.0627 | 1.081 | 1.0993 | 1.1176 | 1.1359 | 1.1542 | 1.1726 | 1.1909 | 1.2092 | 1.2275 | 1.2458 | 1.2642 | 1.2825 | 1.3008 | 1.3191 | 1.3374 | 1.3557 | 1.3741 | 1.3924 | 1.4107 | 1.429 | 1.4473 | 1.4657 | 1.484 | 1.5023 | 1.5206 | 1.5389 | 1.5572 | 1.5756 | 1.5939 | 1.6122 | 1.6305 | 1.6488 | 1.6672 | 1.6855 | 1.7038 | 1.7221 | 1.7404 | 1.7587 | 1.7771 | 1.7954 | 1.8137 | 1.832
| Cumulative Distribution Function |  | 0.6075% | 2.997% | 7.74% | 14.24% | 21.74% | 29.6% | 37.28% | 44.52% | 51.19% | 57.19% | 62.53% | 67.22% | 71.35% | 74.97% | 78.1% | 80.84% | 83.23% | 85.29% | 87.07% | 88.64% | 90.02% | 91.18% | 92.2% | 93.14% | 93.93% | 94.62% | 95.2% | 95.74% | 96.21% | 96.6% | 96.96% | 97.29% | 97.59% | 97.82% | 98.04% | 98.25% | 98.43% | 98.59% | 98.72% | 98.84% | 98.97% | 99.04% | 99.14% | 99.24% | 99.3% | 99.37% | 99.41% | 99.48% | 99.52% | 99.55% | 99.58% | 99.61% | 99.64% | 99.67% | 99.7% | 99.72% | 99.74% | 99.76% | 99.78% | 99.8% | 99.81% | 99.83% | 99.84% | 99.84% | 99.85% | 99.86% | 99.87% | 99.88% | 99.89% | 99.9% | 99.91% | 99.91% | 99.92% | 99.93% | 99.93% | 99.93% | 99.93% | 99.93% | 99.94% | 99.94% | 99.94% | 99.94% | 99.94% | 99.95% | 99.95% | 99.95% | 99.95% | 99.95% | 99.96% | 99.96% | 99.96% | 99.96% | 99.96% | 99.97% | 99.97% | 99.97% | 99.97% | 99.97% | 100%
| Probability Histogram |  | 0.6075% | 2.389% | 4.744% | 6.496% | 7.501% | 7.862% | 7.681% | 7.237% | 6.67% | 6.005% | 5.335% | 4.689% | 4.133% | 3.622% | 3.127% | 2.746% | 2.388% | 2.059% | 1.774% | 1.571% | 1.382% | 1.157% | 1.024% | 0.9354% | 0.7915% | 0.6935% | 0.5833% | 0.5344% | 0.4692% | 0.393% | 0.3593% | 0.3273% | 0.3052% | 0.2266% | 0.2235% | 0.2106% | 0.1808% | 0.1541% | 0.1331% | 0.1194% | 0.1278% | 0.0706% | 0.1003% | 0.0965% | 0.0615% | 0.0721% | 0.0434% | 0.0691% | 0.0389% | 0.0286% | 0.0275% | 0.0316% | 0.0325% | 0.0324% | 0.0259% | 0.026% | 0.0198% | 0.0202% | 0.018% | 0.016% | 0.0156% | 0.0134% | 0.0084% | 0.0084% | 0.0083% | 0.0084% | 0.0084% | 0.0088% | 0.0088% | 0.0091% | 0.0088% | 0.0092% | 0.0087% | 0.0035% | 0.0019% | 0.0019% | 0.0019% | 0.0019% | 0.0019% | 0.0019% | 0.0023% | 0.0019% | 0.0019% | 0.0019% | 0.0019% | 0.0019% | 0.0019% | 0.002% | 0.0019% | 0.0019% | 0.0019% | 0.0019% | 0.0019% | 0.0023% | 0.0019% | 0.0019% | 0.0019% | 0.0019% | 0.0269%
Note on A1: Version=1.3 Type=RiskChart
Note on A4: culture=en-US Timestamp=6/10/2009 11:44:10 AM Heading=RI$K Chart for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit Appearance=HistogramWithCdf ShowMethod=False ShowIterations=True ShowResultsType=True UseAllocatedResults=False Cases="Sanitized ACE Example for Demos V1 08JUN2009.aceit,Point Estimate" SelectedRow=ACE4069,Project #2 IAT&CO % of HW & SW (Project #1 Actuals) RowFilter=Cost, NonCost BudgetRow=ACE3079,*Change Tracker from Prior Version ColorScheme=Standard
Note on A9: Version=1.3 Type=Chart Style=RiskChart Name=433F-96C2-44F4-52D1 Description=RI$K Chart Culture=en-US Timestamp=6/10/2009 11:44:11 AM Footprint=R10C4:R39C8 Locks=
Note on A44: Version=1.3 Type=Table Style=RiskCostsInBinsTable Name=433F-96C2-79C3-D505 Description=RI$K Costs in Bins Table Culture=en-US Timestamp=6/10/2009 11:44:11 AM Footprint=R45C4:R47C104 Locks=
Note on A48: Version=1.3 Type=Table Style=RiskConfidenceLevelsTable Name=433F-96C2-4C2A-E8A4 Description=RI$K Confidence Levels Table Culture=en-US Timestamp=6/8/2009 2:22:30 PM Footprint=R48C4:R52C6 Locks=

## No App Corr
POST Report
Correlation Report for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit
Costs in BY2005 $M, 2000 iterations
Wednesday, 10 June 2009, 11:44 am
Pearson Correlation Matrix
|  |  | Subsystem #1 HW Labor | Subsystem #1 HW Material | Subsystem #2 HW Labor | Subsystem #2 HW Material | Subsystem #1 SW | Subsystem #2 SW | Subsystem #3 SW | Integration Assembly Test & Checkout
|  | Row | 316 | 317 | 319 | 320 | 322 | 323 | 324 | 325
| Subsystem #1 HW Labor | 316 | 1 | -0.0098154 | 0.065863 | 0.039121 | 0.021906 | 0.055434 | 0.030269 | 0.22982
| Subsystem #1 HW Material | 317 |  | 1 | -0.026675 | 0.023894 | -0.0033088 | -0.024339 | 0.017205 | 0.27308
| Subsystem #2 HW Labor | 319 |  |  | 1 | -0.023267 | 0.11107 | 0.050932 | 0.056558 | 0.1791
| Subsystem #2 HW Material | 320 |  |  |  | 1 | -0.03195 | -0.0039803 | -0.020821 | 0.11259
| Subsystem #1 SW | 322 |  |  |  |  | 1 | 0.094088 | 0.060675 | 0.15738
| Subsystem #2 SW | 323 | [5 empty] | 1 | 0.081909 | 0.11929
| Subsystem #3 SW | 324 | [6 empty] | 1 | 0.19439
| Integration Assembly Test & Checkout | 325 | [7 empty] | 1
Note on A1: Version=1.3 Type=CorrelationReport
Note on A4: culture=en-US Timestamp=6/10/2009 11:44:49 AM Heading=Correlation Report for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit Cases="Sanitized ACE Example for Demos V1 08JUN2009.aceit,Point Estimate" RowFilter=Cost, NonCost VisibilityLevel=7 ExcludeParents=True SelectedRows="ACE3430,N","ACE3471,N","ACE3431,Y"
Note on A11: Version=1.3 Type=Table Style=CorrelationTable Name=3EAB-ACD9-3134-9687 Description=Correlation Results Culture=en-US Timestamp=6/10/2009 11:44:49 AM Footprint=R12C4:R21C13 Locks=

## App Corr 0.5
POST Report
Correlation Report for Point Estimate in Sanitized ACE Example for Demos App Corr V1 08JUN2009.aceit
Costs in BY2005 $M, 2000 iterations
Monday, 08 June 2009, 3:09 pm
Pearson Correlation Matrix
|  |  | Subsystem #1 HW Labor | Subsystem #1 HW Material | Subsystem #2 HW Labor | Subsystem #2 HW Material | Subsystem #1 SW | Subsystem #2 SW | Subsystem #3 SW | Integration Assembly Test & Checkout
|  | Row | 316 | 317 | 319 | 320 | 322 | 323 | 324 | 325
| Subsystem #1 HW Labor | 316 | 1 | 0.4127 | 0.45691 | 0.32642 | 0.42113 | 0.45525 | 0.34097 | 0.45818
| Subsystem #1 HW Material | 317 |  | 1 | 0.3889 | 0.37325 | 0.40535 | 0.38329 | 0.38644 | 0.48523
| Subsystem #2 HW Labor | 319 |  |  | 1 | 0.30507 | 0.47483 | 0.468 | 0.3707 | 0.44019
| Subsystem #2 HW Material | 320 |  |  |  | 1 | 0.30854 | 0.30022 | 0.26865 | 0.30371
| Subsystem #1 SW | 322 |  |  |  |  | 1 | 0.45234 | 0.42838 | 0.43033
| Subsystem #2 SW | 323 | [5 empty] | 1 | 0.41039 | 0.43773
| Subsystem #3 SW | 324 | [6 empty] | 1 | 0.4986
| Integration Assembly Test & Checkout | 325 | [7 empty] | 1
Note on A1: Version=1.3 Type=CorrelationReport
Note on A4: culture=en-US Timestamp=6/8/2009 3:09:00 PM Heading=Correlation Report for Point Estimate in Sanitized ACE Example for Demos App Corr V1 08JUN2009.aceit Cases="Sanitized ACE Example for Demos App Corr V1 08JUN2009.aceit,Point Estimate" RowFilter=Cost, NonCost VisibilityLevel=7 ExcludeParents=True SelectedRows="ACE3431,Y"
Note on A11: Version=1.3 Type=Table Style=CorrelationTable Name=3EAB-ACD9-3134-9687 Description=Correlation Results Culture=en-US Timestamp=6/8/2009 3:09:00 PM Footprint=R12C4:R21C13 Locks=

## Project #2 Risk Alloc
POST Report
RI$K Allocation Report for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit
Costs in BY2005 $M, 2000 iterations
Wednesday, 10 June 2009, 11:45 am
Results allocated from 'Level 2 WBS Elements', in 5% intervals
| Costs in BY2005 $M | [5 empty] | Allocated Results
| WBS | Point Estimate | Confidence | Mean | Std Dev | CV | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% | 65% | 70% | 75% | 80% | 85% | 90% | 95%
ACE3429 | Project #2 Total | 50.3466 | 22.2% | 64.4976 | 19.3256 | 0.29963 | 40.4081 | 43.9645 | 46.7954 | 49.3097 | 51.3932 | 53.1971 | 55.1049 | 56.782 | 58.4248 | 60.6847 | 62.9148 | 65.0666 | 67.7413 | 70.6215 | 73.7417 | 77.9477 | 82.5971 | 88.3731 | 101.7724
ACE3430 | Project #2 RDT&E | 50.3466 | 22.2% | 64.4976 | 19.3256 | 0.29963 | 40.4081 | 43.9645 | 46.7954 | 49.3097 | 51.3932 | 53.1971 | 55.1049 | 56.782 | 58.4248 | 60.6847 | 62.9148 | 65.0666 | 67.7413 | 70.6215 | 73.7417 | 77.9477 | 82.5971 | 88.3731 | 101.7724
ACE3471 | Contract Costs | 33.5002 | 22.09% | 46.304 | 17.3996 | 0.37577 | 26.4222 | 29.1886 | 31.4548 | 33.5227 | 35.1522 | 36.6393 | 38.1179 | 39.4799 | 40.8752 | 42.7087 | 44.5448 | 46.3537 | 48.7051 | 51.1395 | 53.8223 | 57.4291 | 61.5471 | 66.5544 | 78.8331
ACE3431 | Prime Mission Product | 14.851 | 21.84% | 21.3387 | 8.6998 | 0.4077 | 12.1913 | 13.4283 | 14.5075 | 15.4188 | 16.1391 | 16.8191 | 17.4828 | 18.1156 | 18.6893 | 19.5089 | 20.4273 | 21.2472 | 22.4527 | 23.5414 | 24.9244 | 26.5828 | 28.4939 | 30.9079 | 36.2695
ACE3472 | Hardware | 9.4129 | 30.62% | 12.5853 | 5.6052 | 0.44538 | 7.5568 | 8.4034 | 9.0789 | 9.6331 | 10.0813 | 10.4842 | 10.8532 | 11.2099 | 11.5106 | 11.8851 | 12.3771 | 12.8199 | 13.4831 | 14.0734 | 14.7032 | 15.4667 | 16.4522 | 17.3237 | 19.3571
ACE3594 | Subsystem #1 HW | 6.5719 | 38.62% | 8.7159 | 4.9984 | 0.57348 | 5.2096 | 5.7672 | 6.248 | 6.6301 | 6.9553 | 7.2624 | 7.5326 | 7.7901 | 7.9991 | 8.2632 | 8.5903 | 8.9101 | 9.3614 | 9.8224 | 10.2388 | 10.7443 | 11.3967 | 11.9502 | 13.1706
ACE3569 | Subsystem #1 HW Labor | 2.7525 | 46.79% | 3.9296 | 3.4959 | 0.88962 | 2.3449 | 2.6002 | 2.8071 | 2.9866 | 3.1246 | 3.2343 | 3.3592 | 3.4577 | 3.5672 | 3.6734 | 3.8317 | 4.0082 | 4.2021 | 4.3913 | 4.5471 | 4.8308 | 5.1768 | 5.468 | 6.0748
ACE3570 | Subsystem #1 HW Material | 3.8193 | 50.01% | 4.7862 | 3.607 | 0.75361 | 2.8646 | 3.167 | 3.441 | 3.6435 | 3.8307 | 4.0281 | 4.1734 | 4.3324 | 4.432 | 4.5898 | 4.7586 | 4.9019 | 5.1592 | 5.4311 | 5.6917 | 5.9135 | 6.22 | 6.4823 | 7.0958
ACE3595 | Subsystem #2 | 2.841 | 38.05% | 3.8694 | 2.2945 | 0.59299 | 2.3472 | 2.6362 | 2.8308 | 3.0029 | 3.126 | 3.2218 | 3.3206 | 3.4198 | 3.5115 | 3.6219 | 3.7868 | 3.9098 | 4.1217 | 4.2509 | 4.4644 | 4.7223 | 5.0554 | 5.3735 | 6.1865
ACE3592 | Subsystem #2 HW Labor | 2.202 | 45.59% | 2.7371 | 1.6547 | 0.60453 | 1.5904 | 1.8236 | 1.981 | 2.1139 | 2.2238 | 2.3046 | 2.3974 | 2.4928 | 2.5813 | 2.6755 | 2.7971 | 2.8947 | 3.0261 | 3.1042 | 3.2655 | 3.4437 | 3.6335 | 3.7723 | 4.2317
ACE3593 | Subsystem #2 HW Material | 0.63902 | 50.73% | 1.1323 | 1.6286 | 1.4383 | 0.75682 | 0.81263 | 0.84981 | 0.88904 | 0.90219 | 0.91716 | 0.92315 | 0.92702 | 0.93019 | 0.9464 | 0.98964 | 1.0151 | 1.0956 | 1.1467 | 1.199 | 1.2786 | 1.4219 | 1.6011 | 1.9548
ACE4087 | Software | 3.1727 | 32.75% | 4.9065 | 3.4874 | 0.71077 | 2.7357 | 2.9721 | 3.2058 | 3.3823 | 3.5586 | 3.7171 | 3.8756 | 4.0217 | 4.1574 | 4.3908 | 4.571 | 4.7295 | 5.0184 | 5.2223 | 5.566 | 6.0477 | 6.4892 | 7.3269 | 9.1248
ACE3440 | Subsystem #1 SW | 1.0983 | 47.55% | 1.6332 | 1.5964 | 0.97752 | 0.87719 | 0.95637 | 1.0483 | 1.1121 | 1.1734 | 1.236 | 1.2919 | 1.3497 | 1.3913 | 1.4667 | 1.5282 | 1.5823 | 1.6857 | 1.7574 | 1.8815 | 2.0639 | 2.2064 | 2.4956 | 3.1507
ACE4088 | Subsystem #2 SW | 0.8542 | 46.98% | 1.1502 | 0.9004 | 0.7828 | 0.60935 | 0.68824 | 0.7541 | 0.81104 | 0.85166 | 0.88817 | 0.93012 | 0.97022 | 1.0174 | 1.0825 | 1.1414 | 1.1947 | 1.2481 | 1.3031 | 1.3722 | 1.4544 | 1.5645 | 1.7077 | 2.0323
ACE4089 | Subsystem #3 SW | 1.2203 | 48.44% | 2.1231 | 2.7553 | 1.2978 | 1.2492 | 1.3275 | 1.4034 | 1.4592 | 1.5335 | 1.5929 | 1.6536 | 1.7018 | 1.7487 | 1.8416 | 1.9013 | 1.9525 | 2.0846 | 2.1618 | 2.3122 | 2.5295 | 2.7183 | 3.1236 | 3.9417
ACE3441 | Integration Assembly Test & Checkout | 2.2654 | 36.55% | 3.8469 | 3.1539 | 0.81986 | 1.8988 | 2.0528 | 2.2229 | 2.4034 | 2.4992 | 2.6179 | 2.754 | 2.884 | 3.0213 | 3.233 | 3.4793 | 3.6979 | 3.9512 | 4.2457 | 4.6552 | 5.0684 | 5.5526 | 6.2574 | 7.7877
ACE3442 | Acquisition Support (SEPM, ST&E, DATA) | 13.5245 | 27.93% | 17.8867 | 6.9518 | 0.38866 | 10.2857 | 11.4044 | 12.2817 | 13.1273 | 13.7553 | 14.2959 | 14.874 | 15.3585 | 15.9413 | 16.6892 | 17.3124 | 18.0385 | 18.8379 | 19.786 | 20.6837 | 21.9815 | 23.6323 | 25.3709 | 30.1529
ACE3444 | Training | 0.59404 | 24.25% | 0.85312 | 0.37441 | 0.43887 | 0.4635 | 0.51488 | 0.55814 | 0.60552 | 0.62991 | 0.66373 | 0.68925 | 0.71865 | 0.74692 | 0.78096 | 0.81113 | 0.84799 | 0.89691 | 0.94259 | 0.9892 | 1.0789 | 1.1477 | 1.2511 | 1.4976
ACE3445 | Peculiar Support Equipment (PSE)
ACE3446 | Operational Site Activation | 0.94129 | 33.91% | 1.2601 | 0.5997 | 0.47593 | 0.64406 | 0.71761 | 0.78243 | 0.84325 | 0.89356 | 0.94217 | 0.98856 | 1.0373 | 1.0934 | 1.1539 | 1.2071 | 1.2695 | 1.3361 | 1.4173 | 1.4875 | 1.6145 | 1.7334 | 1.8883 | 2.2658
ACE3449 | Developmental Spares [Covered in HW]
ACE3562 | Contractor Fee | 3.5893 | 25.52% | 4.9654 | 2.0535 | 0.41356 | 2.8377 | 3.1233 | 3.325 | 3.5278 | 3.7343 | 3.9184 | 4.0833 | 4.2498 | 4.4043 | 4.5757 | 4.7868 | 4.9506 | 5.1816 | 5.4523 | 5.7375 | 6.1715 | 6.5398 | 7.1362 | 8.6473
ACE3451 | Government Costs | 16.8464 | 34.63% | 18.1936 | 2.9345 | 0.1613 | 13.9858 | 14.7759 | 15.3407 | 15.787 | 16.241 | 16.5578 | 16.987 | 17.3021 | 17.5496 | 17.9761 | 18.37 | 18.7129 | 19.0362 | 19.482 | 19.9194 | 20.5186 | 21.05 | 21.8187 | 22.9393
ACE3452 | Program Office Support | 11.0365 | 51.78% | 11.0282 | 2.1117 | 0.19148 | 8.6455 | 9.1249 | 9.4582 | 9.7068 | 9.9982 | 10.2153 | 10.4781 | 10.6782 | 10.8382 | 11.0608 | 11.2652 | 11.4439 | 11.6028 | 11.8183 | 12.0541 | 12.3106 | 12.6125 | 12.9382 | 13.2747
ACE3453 | MITRE | 2.7591 | 53.97% | 2.7563 | 0.986 | 0.35773 | 2.1499 | 2.2779 | 2.3574 | 2.4259 | 2.4959 | 2.5674 | 2.624 | 2.6758 | 2.7164 | 2.7705 | 2.8075 | 2.8655 | 2.9202 | 2.9594 | 3.0136 | 3.0788 | 3.1488 | 3.2228 | 3.2894
ACE3455 | SCS | 1.3796 | 54.42% | 1.377 | 0.49296 | 0.358 | 1.0803 | 1.156 | 1.2011 | 1.2264 | 1.2528 | 1.2798 | 1.3112 | 1.3266 | 1.3473 | 1.3678 | 1.4062 | 1.4161 | 1.4336 | 1.4559 | 1.4868 | 1.5238 | 1.5787 | 1.6198 | 1.6673
ACE3456 | PASS | 2.7591 | 53.7% | 2.7555 | 0.99122 | 0.35973 | 2.206 | 2.2975 | 2.3615 | 2.3971 | 2.4723 | 2.5268 | 2.607 | 2.6692 | 2.7133 | 2.7698 | 2.8208 | 2.8703 | 2.9064 | 2.9622 | 3.0079 | 3.0657 | 3.114 | 3.2108 | 3.3262
ACE3457 | ETASS | 4.1387 | 53.44% | 4.1394 | 1.4839 | 0.35848 | 3.2093 | 3.3934 | 3.5383 | 3.6574 | 3.7772 | 3.8414 | 3.9359 | 4.0065 | 4.0613 | 4.1527 | 4.2307 | 4.292 | 4.3425 | 4.4408 | 4.5459 | 4.6423 | 4.771 | 4.8847 | 4.9918
ACE3533 | MIT/LL Support | 0.52668 | 50% | 0.52669 | 0.13171 | 0.25006 | 0.36396 | 0.40484 | 0.43118 | 0.4513 | 0.46864 | 0.48164 | 0.49669 | 0.50919 | 0.51979 | 0.53389 | 0.54711 | 0.55926 | 0.56911 | 0.58252 | 0.59402 | 0.6098 | 0.61887 | 0.64074 | 0.65277
ACE3458 | Travel | 0.26334 | 49.98% | 0.26335 | 0.065861 | 0.25009 | 0.18216 | 0.2025 | 0.21562 | 0.22568 | 0.23432 | 0.24081 | 0.24838 | 0.2546 | 0.2599 | 0.26698 | 0.27356 | 0.27964 | 0.28454 | 0.29128 | 0.29696 | 0.3049 | 0.30944 | 0.32026 | 0.32633
ACE3459 | Government Test Support | 0.35576 | 31.51% | 0.40023 | 0.079981 | 0.19984 | 0.31583 | 0.33255 | 0.34365 | 0.35391 | 0.3607 | 0.36579 | 0.37606 | 0.38371 | 0.38746 | 0.39446 | 0.4028 | 0.41207 | 0.41762 | 0.42636 | 0.43543 | 0.44874 | 0.45792 | 0.47706 | 0.48829
ACE3460 | Assessments (ESC 3%) | 1.3705 | 22.2% | 1.7557 | 0.52606 | 0.29963 | 1.3159 | 1.3843 | 1.4374 | 1.4836 | 1.5218 | 1.5438 | 1.5831 | 1.6091 | 1.629 | 1.6807 | 1.7281 | 1.7683 | 1.8106 | 1.8698 | 1.9213 | 2.0111 | 2.0719 | 2.1868 | 2.4086
ACE3461 | Withholds (SMC/SAF 7%) | 3.2937 | 22.2% | 4.2195 | 1.2643 | 0.29963 | 3.1625 | 3.3268 | 3.4546 | 3.5657 | 3.6574 | 3.7104 | 3.8047 | 3.8673 | 3.9151 | 4.0393 | 4.1532 | 4.2497 | 4.3515 | 4.4937 | 4.6175 | 4.8334 | 4.9794 | 5.2557 | 5.7886
Note on A1: Version=1.3 Type=RiskAllocationReport
Note on A4: culture=en-US Timestamp=6/10/2009 11:45:23 AM Heading=RI$K Allocation Report for Point Estimate in Sanitized ACE Example for Demos V1 08JUN2009.aceit Cases="Sanitized ACE Example for Demos V1 08JUN2009.aceit,Point Estimate" RowFilter=All SelectedRows="ACE3429,Y"
Note on A11: Version=1.3 Type=Table Style=RiskAllocationTable Name=3DEC-7D21-0D3A-7450 Description=RI$K Allocation Table Culture=en-US Timestamp=6/10/2009 11:45:23 AM Footprint=R12C4:R46C28 Locks=