## Table of Contents
Power Generation Plant Estimate
Table of Contents
Summary Results in BY $K | WBS Cost Summary BY$K
Summary Results in TY $K | WBS Cost Summary TY$K
Total Estimate Chart in BY $K | BY Summary Chart
Total Estimate Chart in TY $K | TY Summary Chart
POM Report in TY $K | Budget POM TY$K
Ground Rules and Assumptions | Ground & Assumptions
Estimate Details
RDT&E Phase
1.1.1.1 RD HW Structure | 1.1.1.1
1.1.1.2 RD HW CCC | 1.1.1.2
1.1.1.3 RD HW Engine | 1.1.1.3
1.1.2.1 RD SW CSCI1 | 1.1.2.1
1.1.2.2 RD SW CSCI2 | 1.1.2.2
1.1.2.3 RD SW CSCI3 | 1.1.2.3
1.1.3.1 RD I&A Check-out | 1.1.3.1
1.1.3.2 RD HW/SW Integration | 1.1.3.2
1.1.3.3 RD Tooling | 1.1.3.3
1.2 RD SEPM | 1.2
1.2 RD Training | 1.3
1.2 RD Data | 1.4
1.2 RD Systems Test | 1.5
Procurement Phase
2.1.1.1 Proc HW Structure | 2.1.1.1
2.1.1.2 Proc HW CCC | 2.1.1.2
2.1.1.3 Proc HW Engine | 2.1.1.3
2.1.2 Proc SW | 2.1.2
2.1.3 Proc Integration | 2.1.3
2.2 Proc SEPM | 2.2
2.3 Proc Other | 2.3
OM Phase
3.1 Unit Level Maintenance | 3.1
3.2.1 Software Maintenance Support | 3.2.1
3.1 Software Upgrade | 3.2.2
Reference Tables
Inflation Tables | Inflation Tables

## WBS Cost Summary BY$K
| Results |  | Base Year | 2014 | Units | $K
WBS/Item Number | * Power Plant System Estimate | Approp | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034 | Phased Total
| POWER GENERATION PLANT |  | 0 | 19428.7977 | 33248.6527 | 23297.9078 | 22539.9135 | 20664.1021 | 5883.4345 | 3235.0746 | 49306.6869 | 44718.9239 | 64128.3212 | 82746.3618 | 83517.5048 | 5971.0018 | 17584.0074 | 5971.0018 | 5971.0018 | 16422.7068 | 5971.0018 | 5671.0018 | 14777.5363 | 4921.0018 | 600 | 0 | 0 | 536575.943
1 | RDT&E |  | 0 | 19428.7977 | 33248.6527 | 23297.9078 | 22539.9135 | 20664.1021 | 5883.4345 | 3235.0746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128297.8829
1.1 | Prime Mission Product |  | 0 | 17416.9694 | 24530.7304 | 13574.0713 | 15163.21 | 16640.4457 | 3817.2732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91142.7
1.1.1 | Hardware (HW) |  | 0 | 17416.9694 | 14547.7594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31964.7288
1.1.1.1 | Structure | RDTEA | 0 | 13611.2133 | 9856.3959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23467.6092
1.1.1.2 | Cables, Conduits, and Connectors (CCC) | RDTEA | 0 | 105.9031 | 2012.1596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2118.0628
1.1.1.3 | Engine (with learning) | RDTEA | 0 | 3699.853 | 2679.2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6379.0569
1.1.2 | Software (SW) |  | 0 | 0 | 9982.971 | 13574.0713 | 15152.976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38710.0184
1.1.2.1 | CSCI1 | RDTEA | 0 | 0 | 9982.971 | 100.8381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10083.8091
1.1.2.2 | CSCI2 | RDTEA | 0 | 0 | 0 | 11504.2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11504.2025
1.1.2.3 | CSCI3 | RDTEA | 0 | 0 | 0 | 1969.0308 | 15152.976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17122.0068
1.1.3 | Integration and Assembly (I&A) |  | 0 | 0 | 0 | 0 | 10.234 | 16640.4457 | 3817.2732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20467.9528
1.1.3.1 | I&A Check-Out | RDTEA | 0 | 0 | 0 | 0 | 3.655 | 5943.0163 | 1363.3119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7309.9832
1.1.3.2 | HW/SW Integration | RDTEA | 0 | 0 | 0 | 0 | 5.117 | 8320.2228 | 1908.6366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10233.9764
1.1.3.3 | Tooling and Test Equipment | RDTEA | 0 | 0 | 0 | 0 | 1.462 | 2377.2065 | 545.3247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2923.9933
1.2 | SEPM (RDT&E) | RDTEA | 0 | 1969.4234 | 8534.168 | 9518.8797 | 7221.2191 | 3938.8468 | 1312.9489 | 328.2372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32823.7231
1.3 | Training | RDTEA | 0 | 0 | 0 | 0 | 0 | 0 | 191.7884 | 767.1535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 958.9419
1.4 | Data | RDTEA | 0 | 42.4048 | 183.7543 | 204.9568 | 155.4844 | 84.8097 | 28.2699 | 7.0675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 706.7475
1.5 | System Test and Evaluation (ST&E) | RDTEA | 0 | 0 | 0 | 0 | 0 | 0 | 533.1541 | 2132.6164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2665.7705
2 | Procurement |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49306.6869 | 40547.922 | 59657.3194 | 77825.3599 | 78146.5029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 305483.7911
2.1 | Manufacturing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35208.2335 | 28830.3088 | 42856.4477 | 56131.3018 | 56499.3738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 219525.6655
2.1.1 | Hardware (HW) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25566.7224 | 25069.8337 | 37266.4763 | 37028.5177 | 49129.8902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174061.4403
2.1.1.1 | Structure | OPA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18210.8647 | 18210.8647 | 27316.2971 | 27316.2971 | 36421.7294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127476.0531
2.1.1.2 | Cables, Conduits, and Connectors (CCC) | OPA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1643.6167 | 1643.6167 | 2465.425 | 2465.425 | 3287.2334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11505.3169
2.1.1.3 | Engine (with learning) | OPA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5712.241 | 5215.3523 | 7484.7541 | 7246.7955 | 9420.9274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35080.0703
2.1.2 | Software |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5806.5028 | 0 | 0 | 13548.5064 | 0 | [12 empty] | 19355.0092
2.1.2.1 | Software Site Activation | OPA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5806.5028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5806.5028
2.1.2.2 | Software Upgrade | OPA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13548.5064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13548.5064
2.1.3 | Integration | OPA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3835.0084 | 3760.4751 | 5589.9714 | 5554.2777 | 7369.4835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26109.216
2.2 | SEPM (Procurement) | OPA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13027.0464 | 10667.2142 | 15856.8857 | 20768.5817 | 20904.7683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81224.4962
2.3 | Other | OPA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1071.407 | 1050.399 | 943.986 | 925.4765 | 742.3609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4733.6294
3 | Operations and Support |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4171.0018 | 4471.0018 | 4921.0018 | 5371.0018 | 5971.0018 | 17584.0074 | 5971.0018 | 5971.0018 | 16422.7068 | 5971.0018 | 5671.0018 | 14777.5363 | 4921.0018 | 600 | 0 | 0 | 102794.2689
3.1 | Unit Level Maintenance | OMA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 600 | 1050 | 1500 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 1800 | 1500 | 1050 | 600 | 0 | 0 | 21000
3.2 | Software Maintenance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3871.0018 | 3871.0018 | 3871.0018 | 3871.0018 | 3871.0018 | 15484.0074 | 3871.0018 | 3871.0018 | 14322.7068 | 3871.0018 | 3871.0018 | 13277.5363 | 3871.0018 | 0 | 0 | 0 | 81794.2689
3.2.1 | Software Maintenance Support | OMA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3871.0018 | 3871.0018 | 3871.0018 | 3871.0018 | 3871.0018 | 3871.0018 | 3871.0018 | 3871.0018 | 3871.0018 | 3871.0018 | 3871.0018 | 3871.0018 | 3871.0018 | 0 | 0 | 0 | 50323.0239
3.2.2 | Software Maintenance Upgrade | OMA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11613.0055 | 0 | 0 | 10451.705 | 0 | 0 | 9406.5345 | 0 | 0 | 0 | 0 | 31471.245

## WBS Cost Summary TY$K
| Results |  | Then Year |  | Units | $K
|  | RDTEA TY Factors | 0.95196 | 0.97078 | 0.98643 | 1.0048 | 1.0312 | 1.0537 | 1.0747 | 1.0962 | 1.1181 | 1.1405 | 1.1633 | 1.1866 | 1.2103 | 1.2345 | 1.2592 | 1.2844 | 1.3101 | 1.3363 | 1.363 | 1.3902 | 1.418 | 1.4464 | 1.4753 | 1.5048 | 1.5349
|  | OPA TY Factors | 0.95817 | 0.97541 | 0.9907 | 1.0149 | 1.0371 | 1.0555 | 1.0765 | 1.0981 | 1.12 | 1.1424 | 1.1653 | 1.1886 | 1.2123 | 1.2366 | 1.2613 | 1.2866 | 1.3123 | 1.3385 | 1.3653 | 1.3926 | 1.4205 | 1.4489 | 1.4778 | 1.5074 | 1.5376
| OMA | TY Factors | 0.94875 | 0.96953 | 0.98362 | 0.99756 | 1.0184 | 1.0336 | 1.0539 | 1.075 | 1.0965 | 1.1184 | 1.1408 | 1.1636 | 1.1869 | 1.2106 | 1.2348 | 1.2595 | 1.2847 | 1.3104 | 1.3366 | 1.3633 | 1.3906 | 1.4184 | 1.4468 | 1.4757 | 1.5052
WBS/Item Number | * Power Plant System Estimate | Approp | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | Phased Total
0 | POWER GENERATION PLANT |  | 0 | 18861.1659 | 32797.5683 | 23410.4181 | 23242.6449 | 21773.1445 | 6322.9312 | 3546.2716 | 55224.6036 | 50987.8056 | 74617.4353 | 98227.5171 | 101115.495 | 7228.5689 | 21713.1666 | 7520.6034 | 7671.0153 | 21520.4103 | 7980.9247 | 7731.5388 | 20549.8371 | 6980.074 | 868.0763 | 0 | 0 | 619891.2164
1 | RDT&E |  | 0 | 18861.1659 | 32797.5683 | 23410.4181 | 23242.6449 | 21773.1445 | 6322.9312 | 3546.2716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129954.1444
1.1 | Prime Mission Product |  | 0 | 16908.1153 | 24197.922 | 13639.6233 | 15635.9564 | 17533.5384 | 4102.4262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92017.5815
1.1.1 | Hardware (HW) |  | 0 | 16908.1153 | 14350.3899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31258.5052
1.1.1.1 | Structure | RDTEA | 0 | 13213.5481 | 9722.6741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22936.2222
1.1.1.2 | Cables, Conduits, and Connectors (CCC) | RDTEA | 0 | 102.8091 | 1984.8606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2087.6697
1.1.1.3 | Engine (with learning) | RDTEA | 0 | 3591.7581 | 2642.8551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6234.6132
1.1.2 | Software (SW) |  | 0 | 0 | 9847.5321 | 13639.6233 | 15625.4034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39112.5587
1.1.2.1 | CSCI1 | RDTEA | 0 | 0 | 9847.5321 | 101.3251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9948.8571
1.1.2.2 | CSCI2 | RDTEA | 0 | 0 | 0 | 11559.7586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11559.7586
1.1.2.3 | CSCI3 | RDTEA | 0 | 0 | 0 | 1978.5396 | 15625.4034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17603.943
1.1.3 | Integration and Assembly (I&A) |  | 0 | 0 | 0 | 0 | 10.553 | 17533.5384 | 4102.4262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21646.5176
1.1.3.1 | I&A Check-Out | RDTEA | 0 | 0 | 0 | 0 | 3.7689 | 6261.978 | 1465.1522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7730.8991
1.1.3.2 | HW/SW Integration | RDTEA | 0 | 0 | 0 | 0 | 5.2765 | 8766.7692 | 2051.2131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10823.2588
1.1.3.3 | Tooling and Test Equipment | RDTEA | 0 | 0 | 0 | 0 | 1.5076 | 2504.7912 | 586.0609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3092.3597
1.2 | SEPM (RDT&E) | RDTEA | 0 | 1911.8847 | 8418.3849 | 9564.8483 | 7446.3565 | 4150.2447 | 1411.0271 | 359.8119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33262.5581
1.3 | Training | RDTEA | 0 | 0 | 0 | 0 | 0 | 0 | 206.1151 | 840.9496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1047.0647
1.4 | Data | RDTEA | 0 | 41.1659 | 181.2613 | 205.9465 | 160.332 | 89.3614 | 30.3817 | 7.7473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 716.1963
1.5 | System Test and Evaluation (ST&E) | RDTEA | 0 | 0 | 0 | 0 | 0 | 0 | 572.9811 | 2337.7628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2910.7439
2 | Procurement |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55224.6036 | 46322.8787 | 69516.974 | 92501.4251 | 94740.7878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 358306.6692
2.1 | Manufacturing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39434.0172 | 32936.4078 | 49939.3971 | 66716.3687 | 68496.9254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 257523.1162
2.1.1 | Hardware (HW) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28635.3069 | 28640.3546 | 43425.5627 | 44011.2408 | 59562.5438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204275.0088
2.1.1.1 | Structure | OPA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20396.5801 | 20804.5107 | 31830.9025 | 32467.5197 | 44155.8254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149655.3384
2.1.1.2 | Cables, Conduits, and Connectors (CCC) | OPA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840.8878 | 1877.7055 | 2872.8895 | 2930.3473 | 3985.2721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13507.1023
2.1.1.3 | Engine (with learning) | OPA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6397.839 | 5958.1384 | 8721.7707 | 8613.3738 | 11421.4462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41112.5681
2.1.2 | Software |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6503.4143 | 0 | 0 | 16103.4418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22606.8561
2.1.2.1 | Software Site Activation | OPA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6503.4143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6503.4143
2.1.2.2 | Software Upgrade | OPA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16103.4418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16103.4418
2.1.3 | Integration | OPA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4295.296 | 4296.0532 | 6513.8344 | 6601.6861 | 8934.3816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30641.2513
2.2 | SEPM (Procurement) | OPA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14590.5864 | 12186.4709 | 18477.5769 | 24685.0564 | 25343.8624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95283.553
2.3 | Other | OPA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 1200 | 1100 | 1100 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5500
3 | Operations and Support |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4664.9269 | 5100.4612 | 5726.092 | 6374.7073 | 7228.5689 | 21713.1666 | 7520.6034 | 7671.0153 | 21520.4103 | 7980.9247 | 7731.5388 | 20549.8371 | 6980.074 | 868.0763 | 0 | 0 | 131630.4027
3.1 | Unit Level Maintenance | OMA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 335.5256 | 684.4723 | 1221.783 | 1780.3124 | 2542.286 | 2593.1319 | 2644.9945 | 2697.8944 | 2751.8522 | 2806.8894 | 2454.0232 | 2085.9198 | 1489.3467 | 868.0763 | 0 | 0 | 26956.5076
3.2 | Software Maintenance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4329.4012 | 4415.989 | 4504.309 | 4594.3949 | 4686.2828 | 19120.0347 | 4875.6089 | 4973.121 | 18768.5581 | 5174.0353 | 5277.5156 | 18463.9173 | 5490.7273 | 0 | 0 | 0 | 104673.8951
3.2.1 | Software Maintenance Support | OMA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4329.4012 | 4415.989 | 4504.309 | 4594.3949 | 4686.2828 | 4780.0087 | 4875.6089 | 4973.121 | 5072.5833 | 5174.0353 | 5277.5156 | 5383.0663 | 5490.7273 | 0 | 0 | 0 | 63557.0432
3.2.2 | Software Maintenance Upgrade | OMA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14340.0261 | 0 | 0 | 13695.9748 | 0 | 0 | 13080.851 | 0 | 0 | 0 | 0 | 41116.8519

## BY Summary Chart
Base Year 2014 $K | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034
POWER GENERATION PLANT | 0 | 19428.7977 | 33248.6527 | 23297.9078 | 22539.9135 | 20664.1021 | 5883.4345 | 3235.0746 | 49306.6869 | 44718.9239 | 64128.3212 | 82746.3618 | 83517.5048 | 5971.0018 | 17584.0074 | 5971.0018 | 5971.0018 | 16422.7068 | 5971.0018 | 5671.0018 | 14777.5363 | 4921.0018 | 600 | 0 | 0

## TY Summary Chart
Then Year $K | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034
POWER GENERATION PLANT | 0 | 18861.1659 | 32797.5683 | 23410.4181 | 23242.6449 | 21773.1445 | 6322.9312 | 3546.2716 | 55224.6036 | 50987.8056 | 74617.4353 | 98227.5171 | 101115.495 | 7228.5689 | 21713.1666 | 7520.6034 | 7671.0153 | 21520.4103 | 7980.9247 | 7731.5388 | 20549.8371 | 6980.074 | 868.0763 | 0 | 0

## Budget POM TY$K
| Results |  | Then Year |  | Units | $K
WBS/Item Number | * Power Plant System Estimate | SUNK Prior | SUNK PY 2015 | BUDGET BY1/CY2016 | BUDGET BY2 2017 | POM FY2018 | POM FY2019 | POM FY2020 | POM FY2021 | POM FY2022 | POM FY2023 | To Complete | Total
| POWER GENERATION PLANT | 98311.7972 | 21773.1445 | 6322.9312 | 3546.2716 | 55224.6036 | 50987.8056 | 74617.4353 | 98227.5171 | 101115.495 | 7228.5689 | 102535.6465 | 619891.2164
1 | RDT&E | 98311.7972 | 21773.1445 | 6322.9312 | 3546.2716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129954.1444
1.1 | Prime Mission Product | 70381.6169 | 17533.5384 | 4102.4262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92017.5815
1.1.1 | Hardware (HW) | 31258.5052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31258.5052
1.1.1.1 | Structure | 22936.2222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22936.2222
1.1.1.2 | Cables, Conduits, and Connectors (CCC) | 2087.6697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2087.6697
1.1.1.3 | Engine (with learning) | 6234.6132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6234.6132
1.1.2 | Software (SW) | 39112.5587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39112.5587
1.1.2.1 | CSCI1 | 9948.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9948.8571
1.1.2.2 | CSCI2 | 11559.7586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11559.7586
1.1.2.3 | CSCI3 | 17603.943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17603.943
1.1.3 | Integration and Assembly (I&A) | 10.553 | 17533.5384 | 4102.4262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21646.5176
1.1.3.1 | I&A Check-Out | 3.7689 | 6261.978 | 1465.1522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7730.8991
1.1.3.2 | HW/SW Integration | 5.2765 | 8766.7692 | 2051.2131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10823.2588
1.1.3.3 | Tooling and Test Equipment | 1.5076 | 2504.7912 | 586.0609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3092.3597
1.2 | SEPM (RDT&E) | 27341.4744 | 4150.2447 | 1411.0271 | 359.8119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33262.5581
1.3 | Training | 0 | 0 | 206.1151 | 840.9496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1047.0647
1.4 | Data | 588.7059 | 89.3614 | 30.3817 | 7.7473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 716.1963
1.5 | System Test and Evaluation (ST&E) | 0 | 0 | 572.9811 | 2337.7628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2910.7439
2 | Procurement | 0 | 0 | 0 | 0 | 55224.6036 | 46322.8787 | 69516.974 | 92501.4251 | 94740.7878 | 0 | 0 | 358306.6692
2.1 | Manufacturing | 0 | 0 | 0 | 0 | 39434.0172 | 32936.4078 | 49939.3971 | 66716.3687 | 68496.9254 | 0 | 0 | 257523.1162
2.1.1 | Hardware (HW) | 0 | 0 | 0 | 0 | 28635.3069 | 28640.3546 | 43425.5627 | 44011.2408 | 59562.5438 | 0 | 0 | 204275.0088
2.1.1.1 | Structure | 0 | 0 | 0 | 0 | 20396.5801 | 20804.5107 | 31830.9025 | 32467.5197 | 44155.8254 | 0 | 0 | 149655.3384
2.1.1.2 | Cables, Conduits, and Connectors (CCC) | 0 | 0 | 0 | 0 | 1840.8878 | 1877.7055 | 2872.8895 | 2930.3473 | 3985.2721 | 0 | 0 | 13507.1023
2.1.1.3 | Engine (with learning) | 0 | 0 | 0 | 0 | 6397.839 | 5958.1384 | 8721.7707 | 8613.3738 | 11421.4462 | 0 | 0 | 41112.5681
2.1.2 | Software | 0 | 0 | 0 | 0 | 6503.4143 | 0 | 0 | 16103.4418 | 0 | 0 | 0 | 22606.8561
2.1.2.1 | Software Site Activation | 0 | 0 | 0 | 0 | 6503.4143 | 0 | 0 | 0 | 0 | 0 | 0 | 6503.4143
2.1.2.2 | Software Upgrade | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16103.4418 | 0 | 0 | 0 | 16103.4418
2.1.3 | Integration | 0 | 0 | 0 | 0 | 4295.296 | 4296.0532 | 6513.8344 | 6601.6861 | 8934.3816 | 0 | 0 | 30641.2513
2.2 | SEPM (Procurement) | 0 | 0 | 0 | 0 | 14590.5864 | 12186.4709 | 18477.5769 | 24685.0564 | 25343.8624 | 0 | 0 | 95283.553
2.3 | Other | 0 | 0 | 0 | 0 | 1200 | 1200 | 1100 | 1100 | 900 | 0 | 0 | 5500
3 | Operations and Support | 0 | 0 | 0 | 0 | 0 | 4664.9269 | 5100.4612 | 5726.092 | 6374.7073 | 7228.5689 | 102535.6465 | 131630.4027
3.1 | Unit Level Maintenance | 0 | 0 | 0 | 0 | 0 | 335.5256 | 684.4723 | 1221.783 | 1780.3124 | 2542.286 | 20392.1283 | 26956.5076
3.2 | Software Maintenance | 0 | 0 | 0 | 0 | 0 | 4329.4012 | 4415.989 | 4504.309 | 4594.3949 | 4686.2828 | 82143.5182 | 104673.8951
3.2.1 | Software Maintenance Support | 0 | 0 | 0 | 0 | 0 | 4329.4012 | 4415.989 | 4504.309 | 4594.3949 | 4686.2828 | 41026.6663 | 63557.0432
3.2.2 | Software Maintenance Upgrade | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41116.8519 | 41116.8519

## TY Budget Chart
Then Year $K | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034 | Total
POWER GENERATION PLANT | 0 | 18861.1659 | 32797.5683 | 23410.4181 | 23242.6449 | 21773.1445 | 6322.9312 | 3546.2716 | 55224.6036 | 50987.8056 | 74617.4353 | 98227.5171 | 101115.495 | 7228.5689 | 21713.1666 | 7520.6034 | 7671.0153 | 21520.4103 | 7980.9247 | 7731.5388 | 20549.8371 | 6980.074 | 868.0763 | 0 | 0 | 619891.2164
RDT&E | 0 | 18861.1659 | 32797.5683 | 23410.4181 | 23242.6449 | 21773.1445 | 6322.9312 | 3546.2716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129954.1444
Procurement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55224.6036 | 46322.8787 | 69516.974 | 92501.4251 | 94740.7878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 358306.6692
Operations and Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4664.9269 | 5100.4612 | 5726.092 | 6374.7073 | 7228.5689 | 21713.1666 | 7520.6034 | 7671.0153 | 21520.4103 | 7980.9247 | 7731.5388 | 20549.8371 | 6980.074 | 868.0763 | 0 | 0 | 131630.4027
PROGRAM BUDGET | 0 | 19000 | 33000 | 24000 | 24000 | 24000 | 20000 | 20000 | 40000 | 45000 | 65000 | 95000 | 95000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 1000 | 0 | 0 | 640000
RDTE BUDGET |  | 19000 | 33000 | 24000 | 24000 | 24000 | 20000 | 20000 | [17 empty] | 164000
PROCUREMENT BUDGET | [8 empty] | 40000 | 40000 | 60000 | 90000 | 90000 | [12 empty] | 320000
OM BUDGET | [9 empty] | 5000 | 5000 | 5000 | 5000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 1000 | 0 | 0 | 156000

## Ground & Assumptions
POWER GENERATION PLANT
Ground Rules and Assumptions for the Estimate
Master Schedule Elements | Starting Schedule Link Description | Start Date |  |  |  | End Date |  |  |  | Link | Duration |  |  |  | Comments
|  | Excel Start Date Formula | Excel Calculate Start Date | ACE Calculate Start Date | Start Date Used in Estimate | Excel End Date Formula | Excel Calculate End Date | ACE Calculate End Date | End Date Used in Estimate | Schedule link in Months | Excel Duration Formula | Excel Duration in Months | ACE Duration in Months | Duration Used in Estimate
Hardware Development | None | Raw Input | 2011-03-01 | 2011-03-01 | 2011-03-01 | EDATE(C7,J7) | 2012-09-01 | 2012-09-01 | 2012-09-01 |  |  | 18 | 18 | 18
Cables Conduits and Connectors | 12 months prior to HW Dev End Date | EDATE(H7,K8) | 2011-09-01 | 2011-09-01 | 2011-09-01 | E7 | 2012-09-01 | 2012-09-01 | 2012-09-01 | -12
CSCI 1 | 6 months prior to HW Dev End Date | EDATE(H7,K9) | 2012-03-01 | 2012-03-01 | 2012-03-01 | EDATE(D9,M9) | 2012-11-01 | 2012-11-02 | 2012-11-01 | -6 | DAYS360(D9,H9)/30 | 8.0468 | 8 | 8 | Duration Calculated from Level of Effort (see WBS Estimate Sheet)
CSCI 2 | Starts At CSCI1 Complete | H9 | 2012-11-01 | 2012-11-02 | 2012-11-01 | EDATE(D10,M10) | 2013-08-01 | 2013-08-07 | 2013-08-01 |  | DAYS360(D10,H10)/30 | 9.1803 | 9.2 | 9.2 | Duration Calculated from Level of Effort (see WBS Estimate Sheet)
CSCI 3 | Starts At CSCI2 Complete | H10 | 2013-08-01 | 2013-08-07 | 2013-08-01 | EDATE(D11,M11) | 2014-09-01 | 2014-09-26 | 2014-09-01 |  | DAYS360(D11,H11)/30 | 13.6633 | 13.7 | 13.7 | Duration Calculated from Level of Effort (see WBS Estimate Sheet)
Integration & Assembly | Starts At CSCI3 Complete | H11 | 2014-09-01 | 2014-09-26 | 2014-09-01 | EDATE(D12,M12) | 2016-07-01 | 2016-07-26 | 2016-07-26 |  | DAYS360(D12,H12)/30 | 22.8333 | 22 | 22 | Adjust - Excel Date math based on avg 360 year - ACE uses 365 day calendar
SEPM | HW Start Date | D7 | 2011-03-01 | 2011-03-01 | 2011-03-01 | H16 | 2017-07-01 | 2017-07-26 | 2017-07-26
Training | Starts At I&A Complete | H12 | 2016-07-01 | 2016-07-26 | 2016-07-26 | H16 | 2017-07-01 | 2017-07-26 | 2017-07-26
Data | HW Start Date | D7 | 2011-03-01 | 2011-03-01 | 2011-03-01 | H16 | 2017-07-01 | 2017-07-26 | 2017-07-26
System Test and Evaluation | Starts At I&A Complete | H12 | 2016-07-01 | 2016-07-26 | 2016-07-26 | EDATE(D16,M16) | 2017-07-01 | 2017-07-26 | 2017-07-26 |  | DAYS360(D16,H16)/30 | 12 | 12 | 12
EMD Schedule | Total Schedule across RD Activities | D7 | 2011-03-01 | 2011-03-01 | 2011-03-01 | H16 | 2017-07-01 | 2017-07-26 | 2017-07-26 |  |  | 76.8333 | 82.9
Quantities | Total or Annual | Total | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034
Development Engine Quantity | Total | 10
Procurement Engine Quantity | Annual | 70 | [8 empty] | 10 | 10 | 15 | 15 | 20
Fielded Engine Quantity | Annual |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 35 | 50 | 70 | 70 | 70 | 70 | 70 | 70 | 60 | 50 | 35 | 20 | 0 | 0
Procurement Engine Fiscal Year: First/Last Finder |  |  | No | No | No | No | No | No | No | No | 2018 | 2019 | 2020 | 2021 | 2022 | No | No | No | No | No | No | No | No | No | No | No | No
OM Engine Fiscal Year: First/Last Finder |  |  | No | No | No | No | No | No | No | No | No | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | No | No
Engine Operational Life | Total | 10 | Manually Adjust Fielded quantity equations to reflect these Rules
Lag between Procurement and Fielding in Years | Total | 1
Technical Characteristics | Value
Material Weights
Structure Weight in Lbs | 1275
Cable Weight in Lbs | 495
Engine Characteristics
Engine kHp per Ton | 2
Engine Type (Oil=1, Coal=0) | 1
Engine Learning Slope | 0.95
Hardware Input
Development to Production Step Factor | 0.776
Software SLOC
CSCI 1 SLOC | 55000
CSCI 2 SLOC | 62000
CSCI 3 SLOC | 89000
Total SLOC | 206000
Staffing
Hours Per Month | 160
Formulas:
Excel Calculate End Date = EDATE([Start Date Used in Estimate],[Excel Duration in Months])
Excel Calculate End Date = [Excel Calculate End Date, row above]
End Date Used in Estimate = EDATE([Start Date Used in Estimate],[Excel Duration in Months])
End Date Used in Estimate = [End Date Used in Estimate, row above]
Excel Calculate Start Date = EDATE([Excel Calculate End Date, row above],[Link])
Excel Calculate Start Date = EDATE(H7,[Link])
Start Date Used in Estimate = EDATE([End Date Used in Estimate, row above],[Link])
Start Date Used in Estimate = EDATE(J7,[Link])
Note on J9: Cyrulik, Melissa SB Tecolote: This End Date is different than the end Date Calculated by ACE Using the Days360 function divided by a 30 average month produces a different result than ACE which is based on a full calendar
Note on J10: Cyrulik, Melissa SB Tecolote: This End Date is different than the end Date Calculated by ACE Using the Days360 function divided by a 30 average month produces a different result than ACE which is based on a full calendar
Note on J11: Cyrulik, Melissa SB Tecolote: This End Date is different than the end Date Calculated by ACE Using the Days360 function divided by a 30 average month produces a different result than ACE which is based on a full calendar
Note on J12: Cyrulik, Melissa SB Tecolote: As the project schedule moves through the elements in the estimate there is a cumulative effect of the schedule difference between Excel and ACE. For I&A the end date is manually set to the date calculated by ACE to make the schedule of the subsequent WBS line up with the ACE schedule results.

## 1.1.1.1
POWER GENERATION PLANT
WBS Element: |  |  | 1.1.1.1
Hardware (HW) Structure
WBS/CES Definition: |  | Prime Mission Product Subsystem Hardware Structure. The hardware structure and associated resource components of the power generation plant.
Appropriations: |  | RDTEA
WBS Summary |  | $K
|  | Approp | Total | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034
Structure |  | RDTEA | 23467.6092 | 0 | 13611.2133 | 9856.3959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost Build Up
Assumptions |  | Hardware Development Period of Performance 01Mar2011 to 01Sep2012
Methodology
| 1 | Structure Cost based on Structure Weight.
| 2 | CER Cost=15510.4*StrucWgt in Base Year 2005 $
| 3 | StrucWgt = Structure Weight in lbs of 1275
| 4 | Derive Phasing Method from front loaded Beta curve 60/40 with medium peakness
Inputs |  |  | Value | Cost Type | FY | Units | BY2014$K
|  | Structure Cost | 19775760 | BY | 2005 | $ | 23467.6092
|  | Structure Weight in Lbs | 1275
|  | Milestone Start Date | 2011-03-01
|  | Milestone Finish Date | 2012-09-01
|  | Calculated Duration in Months | 18
|  |  |  | From | To | Factor
|  | Cost Adjustments | BYtoBY | 2005 | 2014 | 1.1867
|  | RDTEA | BYtoBY | 2014 | 2005 | 0.84268
|  |  |  | 2010-10-01 | 2011-10-01 | 2012-10-01 | 2013-10-01 | 2014-10-01 | 2015-10-01 | 2016-10-01 | 2017-10-01 | 2018-10-01 | 2019-10-01 | 2020-10-01 | 2021-10-01 | 2022-10-01 | 2023-10-01 | 2024-10-01 | 2025-10-01 | 2026-10-01 | 2027-10-02 | 2028-10-02 | 2029-10-03 | 2030-10-04 | 2031-10-05 | 2032-10-05 | 2033-10-06 | 2034-10-07
Phasing |  |  |  | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034 | Total
|  |  | Months | 2011-10-01: 7.1333; 2012-10-01: 11 | 18.1333
|  |  | Percent Per Year | 2011-10-01: 0.58; 2012-10-01: 0.42 | 1
Notes For Common Estimate Changes:
If the Milestone Schedule changes, Start/Finish Dates are altered in any way the Months per year and Percent Per Year annual values must be manually updated
1. Update the Months per year values
2. Change the percent per year to reflect the months change and any change to the annual expenditure rate
If the expenditure rate changes, default based on a front loaded Beta Curve the Percent Per Year annual values must be manually updated
If a different Structure CER is desired the equation used in the Structure Input Section must be updated: new inputs might be required

## 1.1.1.2
POWER GENERATION PLANT
WBS Element: |  |  | 1.1.1.2
Hardware (HW) Cables, Conduit, and Connectors (CCC)
WBS/CES Definition: |  | Prime Mission Product Subsystem Hardware Cables, Conduits and Connectors. The hardware cables conduits and connectors and associated resource components of the power generation plant.
Appropriations: |  | RDTEA
WBS Summary |  | $K
|  | Approp | Total | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034
Cables, Conduit, and Connectors (CCC) |  | RDTEA | 2118.0628 | 0 | 105.9031 | 2012.1596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost Build Up
Assumptions |  | CCC Development Period of Performance is one year. To be completed the same time as the Hardware Structure 01Sep2012
Methodology
| 1 | CCC Cost based on CCC Weight.
| 2 | CER Cost=(15032.9 + 3575.4 * CccWgt) in Base Year 2005 $
| 3 | CCCWgt = Cable, Conduit and Connectors Weight in lbs of 495
| 4 | Derive Phasing Method from front loaded Beta curve 60/40 with medium peakness
Inputs |  |  | Value | Cost Type | FY | Units | BY2014$K
|  | CCC Cost | 1784855.9 | BY | 2005 | $ | 2118.0628
|  | CCC Weight in Lbs | 495
|  | Milestone Start Date | 2011-09-01
|  | Milestone Finish Date | 2012-09-01
|  | Calculated Duration in Months | 12
|  |  |  | From | To | Factor
|  | Cost Adjustments | BYtoBY | 2005 | 2014 | 1.1867
|  | RDTEA | BYtoBY | 2014 | 2005 | 0.84268
|  |  |  | 2010-10-01 | 2011-10-01 | 2012-10-01 | 2013-10-01 | 2014-10-01 | 2015-10-01 | 2016-10-01 | 2017-10-01 | 2018-10-01 | 2019-10-01 | 2020-10-01 | 2021-10-01 | 2022-10-01 | 2023-10-01 | 2024-10-01 | 2025-10-01 | 2026-10-01 | 2027-10-01 | 2028-10-01 | 2029-10-01 | 2030-10-01 | 2031-10-01 | 2032-10-01 | 2033-10-01 | 2034-10-01
Phasing |  |  |  | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034 | Total
|  |  | Months | 2011-10-01: 1; 2012-10-01: 11 | 12
|  |  | Percent Per Year | 2011-10-01: 0.05; 2012-10-01: 0.95 | 1
Notes For Common Estimate Changes:
If the Milestone Schedule changes, Start/Finish Dates are altered in any way the Months per year and Percent Per Year annual values must be manually updated
1. Update the Months per year values
2. Change the percent per year to reflect the months change and any change to the annual expenditure rate
If the expenditure rate changes, default based on a front loaded Beta Curve the Percent Per Year annual values must be manually updated
If a different CCC CER is desired the equation used in the CCC Input Section must be updated: new inputs might be required

## 1.1.1.3
POWER GENERATION PLANT
WBS Element: |  |  | 1.1.1.3
Hardware (HW) Engine
WBS/CES Definition: |  | Engine: The means for generating and delivering power in the required quantities and rates to the plant system.
Appropriations: |  | RDTEA
WBS Summary |  | $K
|  | Approp | Total | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034
Engine |  | RDTEA | 6379.0569 | 0 | 3699.853 | 2679.2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost Build Up
Assumptions |  | Engine Development Period of Performance 01Mar2011 to 01Sep2012
Methodology
| 1 | Engine Cost based on multi variable equation.
| 2 | Engine T1 Cost=370.4 * kHpPerTon ^ 0.8747 * 0.878 ^ Oil in Base Year 2010 $K
| 3 | kHpPerTon = k Horse Power per Ton = 2
| 4 | Oil is a Dummy variable Oil=1, Coal=0. Default Technical Baseline is Oil Engine.
| 5 | Derive Phasing Method from front loaded Beta curve 60/40 with medium peakness
| 6 | There are 10 units planned for R&D
Inputs |  |  | Value | Cost Type | FY | Units | BY2014$K
|  | Engine T1 Cost | 596.316 | BY | 2010 | $K | 6379.0569
|  | Engine Horse Power per Ton | 2
|  | Engine Type Oil=1, Coal=0 | 1
|  | Development Quantity | 10
|  | Milestone Start Date | 2011-03-01
|  | Milestone Finish Date | 2012-09-01
|  | Calculated Duration in Months | 18
|  |  |  | From | To | Factor
|  | Cost Adjustments | BYtoBY | 2010 | 2014 | 1.0697
|  | RDTEA | BYtoBY | 2014 | 2010 | 0.9348
|  |  |  | 2010-10-01 | 2011-10-01 | 2012-10-01 | 2013-10-01 | 2014-10-01 | 2015-10-01 | 2016-10-01 | 2017-10-01 | 2018-10-01 | 2019-10-01 | 2020-10-01 | 2021-10-01 | 2022-10-01 | 2023-10-01 | 2024-10-01 | 2025-10-01 | 2026-10-01 | 2027-10-01 | 2028-10-01 | 2029-10-01 | 2030-10-01 | 2031-10-01 | 2032-10-01 | 2033-10-01 | 2034-10-01
Phasing |  |  |  | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034 | Total
|  |  | Months | 2011-10-01: 7.1333; 2012-10-01: 11 | 18.1333
|  |  | Percent Per Year | 2011-10-01: 0.58; 2012-10-01: 0.42 | 1
Notes For Common Estimate Changes:
The same Engine Unit Cost CER is used in the Development and Production portions of the estimate. If the CER used for 2.1.1.3 is changed, the CER used here in 1.1.1.3 should be changed as well
If the Milestone Schedule changes, Start/Finish Dates are altered in any way the Months per year and Percent Per Year annual values must be manually updated
1. Update the Months per year values
2. Change the percent per year to reflect the months change and any change to the annual expenditure rate
If the expenditure rate changes, default based on a front loaded Beta Curve the Percent Per Year annual values must be manually updated

## 1.1.2.1
POWER GENERATION PLANT
WBS Element: |  |  | 1.1.2.1
Software (SW) CSCI1
WBS/CES Definition: |  | Computer Software Configuration Item (CSCI) 1. An aggregation of software or any of its discrete portions that satisfies an end use function and has been designated by the Government or Contractor, if the Government did not specify, for configuration management. CSCIs are the major software products of a system acquisition, which are developed in accordance with standard DoD or commercial practices and processes.
Appropriations: |  | RDTEA
WBS Summary |  | $K
|  | Approp | Total | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034
CSCI1 |  | RDTEA | 10083.8091 | 0 | 0 | 9982.971 | 100.8381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost Build Up
Assumptions |  | Software CSCI1 Development Period of Performance starts 6 months before Hardware Development End (01Mar2012).
Software CSCI1 Development Duration Estimate 8 months (02Nov2012).
Methodology
| 1 | Engineering Build Up of Total Development SW Development Cost = Labor Rate*Work Hours per Month * CSCI Size
| 2 | Average Software Labor Rate per Hour $220 Base Year 2005 $
| 3 | Hours per Person Month is 160
| 4 | Software Person Months Based on COCOMO Equation 2.94 *(SLOC/1000)^1.1
| 5 | CSCI1 Software Lines of Code (SLOC) 55000
| 6 | Duration calculated based on 30 person Staff Level
| 7 | Derive Phasing Method from front loaded Beta curve 60/40 with medium peakness
Inputs |  |  | Value | Cost Type | FY | Units | BY2014$K
|  | CSCI1 Cost | 10083.8091 |  |  |  | 10083.8091
|  | Software Wrap Rate | 220 | BY | 2005 | $ | 0.26107
|  | CSCI1 SLOC | 55000
|  | CSCI1 Software Person Months | 241.405
|  | Hours per Person Month | 160
|  | Staff Level for Software Dev | 30
|  | Duration Months | 8.0468
|  | Milestone Start Date | 2012-03-01
|  | Milestone Finish Date | 2012-11-01
|  | Calculated Duration in Months | 8
|  |  |  | From | To | Factor
|  | Cost Adjustments | BYtoBY | 2005 | 2014 | 1.1867
|  | RDTEA | BYtoBY | 2014 | 2005 | 0.84268
|  |  |  | 2010-10-01 | 2011-10-01 | 2012-10-01 | 2013-10-01 | 2014-10-01 | 2015-10-01 | 2016-10-01 | 2017-10-01 | 2018-10-01 | 2019-10-01 | 2020-10-01 | 2021-10-01 | 2022-10-01 | 2023-10-01 | 2024-10-01 | 2025-10-01 | 2026-10-01 | 2027-10-01 | 2028-10-01 | 2029-10-01 | 2030-10-01 | 2031-10-01 | 2032-10-01 | 2033-10-01 | 2034-10-01
Phasing |  |  |  | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034 | Total
|  |  | Months | 2012-10-01: 7.1333; 2013-10-01: 0.86667 | 8
|  |  | Percent Per Year | 2012-10-01: 0.99; 2013-10-01: 0.01 | 1
Notes For Common Estimate Changes:
If the Milestone Schedule changes, Start/Finish Dates are altered in any way the Months per year and Percent Per Year annual values must be manually updated
1. Update the Months per year values
2. Change the percent per year to reflect the months change and any change to the annual expenditure rate
If the expenditure rate changes, default based on a front loaded Beta Curve the Percent Per Year annual values must be manually updated
If a different Software Person Months CER is desired the equation used in the CSCI3 Software Person Months Input Section must be updated: new inputs might be required

## 1.1.2.2
POWER GENERATION PLANT
WBS Element: |  |  | 1.1.2.2
Software (SW) CSCI2
WBS/CES Definition: |  | Computer Software Configuration Item (CSCI) 2. An aggregation of software or any of its discrete portions that satisfies an end use function and has been designated by the Government or Contractor, if the Government did not specify, for configuration management. CSCIs are the major software products of a system acquisition, which are developed in accordance with standard DoD or commercial practices and processes.
Appropriations: |  | RDTEA
WBS Summary |  | $K
|  | Approp | Total | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034
CSCI2 |  | RDTEA | 11504.2025 | 0 | 0 | 0 | 11504.2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost Build Up
Assumptions |  | Software CSCI2 Development Period of Performance starts when the CSCI1 is complete (02Nov2012).
Software CSCI2 Development Duration Estimate 9.2 months (07Aug2013).
Methodology
| 1 | Engineering Build Up of Total Development SW Development Cost = Labor Rate*Work Hours per Month * CSCI Size
| 2 | Average Software Labor Rate per Hour $220 Base Year 2005 $
| 3 | Hours per Person Month is 160
| 4 | Software Person Months Based on COCOMO Equation 2.94 *(SLOC/1000)^1.1
| 5 | CSCI2 Software Lines of Code (SLOC) 62000
| 6 | Duration calculated based on 30 person Staff Level
| 7 | Derive Phasing Method from front loaded Beta curve 60/40 with medium peakness
Inputs |  |  | Value | Cost Type | FY | Units | BY2014$K
|  | CSCI2 Cost | 11504.2025 |  |  |  | 11504.2025
|  | Software Wrap Rate | 220 | BY | 2005 | $ | 0.26107
|  | CSCI2 SLOC | 62000
|  | CSCI2 Software Person Months | 275.409
|  | Hours per Person Month | 160
|  | Staff Level for Software Dev | 30
|  | Duration Months | 9.1803
|  | Milestone Start Date | 2012-11-01
|  | Milestone Finish Date | 2013-08-01
|  | Calculated Duration in Months | 9
|  |  |  | From | To | Factor
|  | Cost Adjustments | BYtoBY | 2005 | 2014 | 1.1867
|  | RDTEA | BYtoBY | 2014 | 2005 | 0.84268
|  |  |  | 2010-10-01 | 2011-10-01 | 2012-10-01 | 2013-10-01 | 2014-10-01 | 2015-10-01 | 2016-10-01 | 2017-10-01 | 2018-10-01 | 2019-10-01 | 2020-10-01 | 2021-10-01 | 2022-10-01 | 2023-10-01 | 2024-10-01 | 2025-10-01 | 2026-10-01 | 2027-10-01 | 2028-10-01 | 2029-10-01 | 2030-10-01 | 2031-10-01 | 2032-10-01 | 2033-10-01 | 2034-10-01
Phasing |  |  |  | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034 | Total
|  |  | Months | 2013-10-01: 9.1 | 9.1
|  |  | Percent Per Year | [25 empty] | 1 | bar: 2013-10-01
Notes For Common Estimate Changes:
If the Milestone Schedule changes, Start/Finish Dates are altered in any way the Months per year and Percent Per Year annual values must be manually updated
1. Update the Months per year values
2. Change the percent per year to reflect the months change and any change to the annual expenditure rate
If the expenditure rate changes, default based on a front loaded Beta Curve the Percent Per Year annual values must be manually updated
If a different Software Person Months CER is desired the equation used in the CSCI2 Software Person Months Input Section must be updated: new inputs might be required

## 1.1.2.3
POWER GENERATION PLANT
WBS Element: |  |  | 1.1.2.3
Software (SW) CSCI3
WBS/CES Definition: |  | Computer Software Configuration Item (CSCI) 3. An aggregation of software or any of its discrete portions that satisfies an end use function and has been designated by the Government or Contractor, if the Government did not specify, for configuration management. CSCIs are the major software products of a system acquisition, which are developed in accordance with standard DoD or commercial practices and processes.
Appropriations: |  | RDTEA
WBS Summary |  | $K
|  | Approp | Total | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034
CSCI3 |  | RDTEA | 17122.0068 | 0 | 0 | 0 | 1969.0308 | 15152.976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost Build Up
Assumptions |  | Software CSCI3 Development Period of Performance starts when the CSCI2 is complete (07Aug2013).
Software CSCI3 Development Duration Estimate 13.7 months (End Date Estimated 26Sep2014).
Methodology
| 1 | Engineering Build Up of Total Development SW Development Cost = Labor Rate*Work Hours per Month * CSCI Size
| 2 | Average Software Labor Rate per Hour $220 Base Year 2005 $
| 3 | Hours per Person Month is 160
| 4 | Software Person Months Based on COCOMO Equation 2.94 *(SLOC/1000)^1.1
| 5 | CSCI3 Software Lines of Code (SLOC) 89000
| 6 | Duration calculated based on 30 person Staff Level
| 7 | Derive Phasing Method from front loaded Beta curve 60/40 with medium peakness
Inputs |  |  | Value | Cost Type | FY | Units | BY2014$K
|  | CSCI3 Cost | 17122.0068 |  |  |  | 17122.0068
|  | Software Wrap Rate | 220 | BY | 2005 | $ | 0.26107
|  | CSCI3 SLOC | 89000
|  | CSCI3 Software Person Months | 409.8985
|  | Hours per Person Month | 160
|  | Staff Level for Software Dev | 30
|  | Duration Months | 13.6633
|  | Milestone Start Date | 2013-08-01
|  | Milestone Finish Date | 2014-09-01
|  | Calculated Duration in Months | 13
|  |  |  | From | To | Factor
|  | Cost Adjustments | BYtoBY | 2005 | 2014 | 1.1867
|  | RDTEA | BYtoBY | 2014 | 2005 | 0.84268
|  |  |  | 2010-10-01 | 2011-10-01 | 2012-10-01 | 2013-10-01 | 2014-10-01 | 2015-10-01 | 2016-10-01 | 2017-10-01 | 2018-10-01 | 2019-10-01 | 2020-10-01 | 2021-10-01 | 2022-10-01 | 2023-10-01 | 2024-10-01 | 2025-10-01 | 2026-10-01 | 2027-10-01 | 2028-10-01 | 2029-10-01 | 2030-10-01 | 2031-10-01 | 2032-10-01 | 2033-10-01 | 2034-10-01
Phasing |  |  |  | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034 | Total
|  |  | Months | 2013-10-01: 2.0333; 2014-10-01: 11 | 13.0333
|  |  | Percent Per Year | 2013-10-01: 0.115; 2014-10-01: 0.885 | 1
Notes For Common Estimate Changes:
If the Milestone Schedule changes, Start/Finish Dates are altered in any way the Months per year and Percent Per Year annual values must be manually updated
1. Update the Months per year values
2. Change the percent per year to reflect the months change and any change to the annual expenditure rate
If the expenditure rate changes, default based on a front loaded Beta Curve the Percent Per Year annual values must be manually updated
If a different Software Person Months CER is desired the equation used in the CSCI3 Software Person Months Input Section must be updated: new inputs might be required

## 1.1.3.1
POWER GENERATION PLANT
WBS Element: |  |  | 1.1.3.1
I&A Check-out
WBS/CES Definition: |  | Subsystem Test and Checkout. The resources specifically related to evaluating the CSCIs and hardware operation as a subsystem. (ANSI/IEEE 12207)
Appropriations: |  | RDTEA
WBS Summary |  | $K
|  | Approp | Total | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034
I&A Check-out |  | RDTEA | 7309.9832 | 0 | 0 | 0 | 0 | 3.655 | 5943.0163 | 1363.3119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost Build Up
Assumptions |  | I&A Check out Period of Performance starts when the CSCI3 is complete (26Sep2014).
I&A Check out Duration Estimate 22 months (End Date Estimated 26Jul2016).
Methodology
| 1 | Engineering Build Up of Total I&A Check-out Development Cost = Labor Rate*Work Hours per Month * Integration Duration * Checkout Staff Level
| 2 | Average Check-out Staff Labor Rate per Hour $175 Base Year 2005 $
| 3 | Hours per Person Month is 160
| 4 | Duration 22 Months
| 5 | 10 person Staff Level
| 6 | Derive Phasing Method from front loaded Beta curve 60/40 with medium peakness
Inputs |  |  | Value | Cost Type | FY | Units | BY2014$K
|  | I&A Check-out Cost | 7309.9832 |  |  |  | 7309.9832
|  | Software Wrap Rate | 175 | BY | 2005 | $ | 0.20767
|  | Hours per Person Month | 160
|  | Staff Level for I&A Check-out | 10
|  | Duration Months | 22
|  | Milestone Start Date | 2014-09-01
|  | Milestone Finish Date | 2016-07-26
|  | Calculated Duration in Months | 22.8333
|  |  |  | From | To | Factor
|  | Cost Adjustments | BYtoBY | 2005 | 2014 | 1.1867
|  | RDTEA | BYtoBY | 2014 | 2005 | 0.84268
|  |  |  | 2010-10-01 | 2011-10-01 | 2012-10-01 | 2013-10-01 | 2014-10-01 | 2015-10-01 | 2016-10-01 | 2017-10-01 | 2018-10-01 | 2019-10-01 | 2020-10-01 | 2021-10-01 | 2022-10-01 | 2023-10-01 | 2024-10-01 | 2025-10-01 | 2026-10-01 | 2027-10-01 | 2028-10-01 | 2029-10-01 | 2030-10-01 | 2031-10-01 | 2032-10-01 | 2033-10-01 | 2034-10-01
Phasing |  |  |  | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034 | Total
|  |  | Months | 2014-10-01: 1; 2015-10-01: 12; 2016-10-01: 9.7667 | 22.7667
|  |  | Percent Per Year | 2014-10-01: 0.0005; 2015-10-01: 0.813; 2016-10-01: 0.1865 | 1
Notes For Common Estimate Changes:
If the Milestone Schedule changes, Start/Finish Dates are altered in any way the Months per year and Percent Per Year annual values must be manually updated
1. Update the Months per year values
2. Change the percent per year to reflect the months change and any change to the annual expenditure rate
If the expenditure rate changes, default based on a front loaded Beta Curve the Percent Per Year annual values must be manually updated

## 1.1.3.2
POWER GENERATION PLANT
WBS Element: |  |  | 1.1.3.2
HW/SW Integration
WBS/CES Definition: |  | Subsystem Integration, Assembly. The resources specifically related to evaluating the CSCIs and hardware operation as a subsystem. (ANSI/IEEE 12207)
Appropriations: |  | RDTEA
WBS Summary |  | $K
|  | Approp | Total | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034
HW/SW Integration |  | RDTEA | 10233.9764 | 0 | 0 | 0 | 0 | 5.117 | 8320.2228 | 1908.6366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost Build Up
Assumptions |  | HW/SW Integration Period of Performance starts when the CSCI3 is complete (26Sep2014).
HW/SW Integration Duration Estimate 22 months (End Date Estimated 26Jul2016).
Period of performance dates align with other I&A activities.
Methodology
| 1 | Engineering Build Up of Total HW/SW Integration Development Cost = Labor Rate*Work Hours per Month * Integration Duration * I&A Staff Level
| 2 | Average Integration Staff Labor Rate per Hour $175 Base Year 2005 $
| 3 | Hours per Person Month is 160
| 4 | Duration 22 Months
| 5 | 14 person Staff Level
| 6 | Derive Phasing Method from front loaded Beta curve 60/40 with medium peakness
Inputs |  |  | Value | Cost Type | FY | Units | BY2014$K
|  | HW/SW Integration Cost | 10233.9764 |  |  |  | 10233.9764
|  | Software Wrap Rate | 175 | BY | 2005 | $ | 0.20767
|  | Hours per Person Month | 160
|  | Staff Level for Hw/SW Integ | 14
|  | Duration Months | 22
|  | Milestone Start Date | 2014-09-01
|  | Milestone Finish Date | 2016-07-26
|  | Calculated Duration in Months | 22.8333
|  |  |  | From | To | Factor
|  | Cost Adjustments | BYtoBY | 2005 | 2014 | 1.1867
|  | RDTEA | BYtoBY | 2014 | 2005 | 0.84268
|  |  |  | 2010-10-01 | 2011-10-01 | 2012-10-01 | 2013-10-01 | 2014-10-01 | 2015-10-01 | 2016-10-01 | 2017-10-01 | 2018-10-01 | 2019-10-01 | 2020-10-01 | 2021-10-01 | 2022-10-01 | 2023-10-01 | 2024-10-01 | 2025-10-01 | 2026-10-01 | 2027-10-01 | 2028-10-01 | 2029-10-01 | 2030-10-01 | 2031-10-01 | 2032-10-01 | 2033-10-01 | 2034-10-01
Phasing |  |  |  | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034 | Total
|  |  | Months | 2014-10-01: 1; 2015-10-01: 12; 2016-10-01: 9.7667 | 22.7667
|  |  | Percent Per Year | 2014-10-01: 0.0005; 2015-10-01: 0.813; 2016-10-01: 0.1865 | 1
Notes For Common Estimate Changes:
If the Milestone Schedule changes, Start/Finish Dates are altered in any way the Months per year and Percent Per Year annual values must be manually updated
1. Update the Months per year values
2. Change the percent per year to reflect the months change and any change to the annual expenditure rate
If the expenditure rate changes, default based on a front loaded Beta Curve the Percent Per Year annual values must be manually updated

## 1.1.3.3
POWER GENERATION PLANT
WBS Element: |  |  | 1.1.3.3
Tooling and Test Equipment
WBS/CES Definition: |  | Tooling This element includes the costs of planning, design, fabrication, assembly, installation, modification, maintenance, and rework of all tools, inspection equipment, and test equipment supporting the development of a specified system component. It includes that time expended in determining tool, inspection, and test equipment requirements; planning of fabrication and testing operations; maintaining tool records; scheduling and control of all tools orders; and programming and preparing software for all numerically controlled machine tools used in development of a system component. It includes the costs of new materials used in the fabrication, assembly, installation, modification, and maintenance and rework of dies, jigs, fixtures, inspection equipment, handling equipment, work platforms, and test equipment used to develop each system component, as well as tools normally purchased in final form or that require negligible effort to assemble.
Appropriations: |  | RDTEA
WBS Summary |  | $K
|  | Approp | Total | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034
Tooling and Test Equipment |  | RDTEA | 2923.9933 | 0 | 0 | 0 | 0 | 1.462 | 2377.2065 | 545.3247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost Build Up
Assumptions |  | Tooling and Test Equipment Period of Performance starts when the CSCI3 is complete (26Sep2014).
Tooling and Test Equipment Duration Estimate 22 months (End Date Estimated 26Jul2016).
Period of performance dates align with other I&A activities.
Methodology
| 1 | Engineering Build Up of Total Tooling and Test Equipment Development Cost = Labor Rate*Work Hours per Month * Integration Duration * I&A Staff Level
| 2 | Average Integration Staff Labor Rate per Hour $175 Base Year 2005 $
| 3 | Hours per Person Month is 160
| 4 | Duration 22 Months
| 5 | 4 person Staff Level
| 6 | Derive Phasing Method from front loaded Beta curve 60/40 with medium peakness
Inputs |  |  | Value | Cost Type | FY | Units | BY2014$K
|  | Tooling Cost | 2923.9933 |  |  |  | 2923.9933
|  | Software Wrap Rate | 175 | BY | 2005 | $ | 0.20767
|  | Hours per Person Month | 160
|  | Staff Level for Tooling | 4
|  | Duration Months | 22
|  | Milestone Start Date | 2014-09-01
|  | Milestone Finish Date | 2016-07-26
|  | Calculated Duration in Months | 22.8333
|  |  |  | From | To | Factor
|  | Cost Adjustments | BYtoBY | 2005 | 2014 | 1.1867
|  | RDTEA | BYtoBY | 2014 | 2005 | 0.84268
|  |  |  | 2010-10-01 | 2011-10-01 | 2012-10-01 | 2013-10-01 | 2014-10-01 | 2015-10-01 | 2016-10-01 | 2017-10-01 | 2018-10-01 | 2019-10-01 | 2020-10-01 | 2021-10-01 | 2022-10-01 | 2023-10-01 | 2024-10-01 | 2025-10-01 | 2026-10-01 | 2027-10-01 | 2028-10-01 | 2029-10-01 | 2030-10-01 | 2031-10-01 | 2032-10-01 | 2033-10-01 | 2034-10-01
Phasing |  |  |  | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034 | Total
|  |  | Months | 2014-10-01: 1; 2015-10-01: 12; 2016-10-01: 9.7667 | 22.7667
|  |  | Percent Per Year | 2014-10-01: 0.0005; 2015-10-01: 0.813; 2016-10-01: 0.1865 | 1
Notes For Common Estimate Changes:
If the Milestone Schedule changes, Start/Finish Dates are altered in any way the Months per year and Percent Per Year annual values must be manually updated
1. Update the Months per year values
2. Change the percent per year to reflect the months change and any change to the annual expenditure rate
If the expenditure rate changes, default based on a front loaded Beta Curve the Percent Per Year annual values must be manually updated

## 1.2
POWER GENERATION PLANT
WBS Element: |  |  | 1.2
SEPM (RDT&E)
WBS/CES Definition: |  | System Engineering. The technical and management efforts of directing and controlling a totally integrated engineering effort of a system or program. Program Management. The business and administrative planning, organizing, directing, coordinating, controlling, and approval actions designated to accomplish overall program objectives, which are not associated with specific hardware elements and are not included in systems engineering.
Appropriations: |  | RDTEA
WBS Summary |  | $K
|  | Approp | Total | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034
SEPM (RDT&E) |  | RDTEA | 32823.7231 | 0 | 1969.4234 | 8534.168 | 9518.8797 | 7221.2191 | 3938.8468 | 1312.9489 | 328.2372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost Build Up
Assumptions |  | SEPM Period of Performance starts when HW Development Begins (01Mar2011).
SEPM Period of Performance End Date Estimated 26Jul2017.
Methodology
| 1 | Engineering Build Up of Total Tooling and Test Equipment Development Cost = Labor Rate*Work Hours per Month * EMD Duration * SEPM Staff Level
| 2 | Average Integration Staff Labor Rate per Hour $150 Base Year 2005 $
| 3 | Hours per Person Month is 160
| 4 | SEPM needed across entire EMD period of Performance (Tech Baseline Estimate 76.8 months)
| 5 | 15 person Staff Level (Min 10 and Max 17)
| 6 | Derive Phasing Method from front loaded Beta curve 60/40 with medium peakness
Inputs |  |  | Value | Cost Type | FY | Units | BY2014$K
|  | SEPM Cost | 32823.7231 |  |  |  | 32823.7231
|  | SEPM Wrap Rate | 150 | BY | 2005 | $ | 0.178
|  | Hours per Person Month | 160
|  | Staff Level for SEPM | 15
|  | Milestone Start Date | 2011-03-01
|  | Milestone Finish Date | 2017-07-26
|  | Calculated Duration in Months | 76.8333
|  |  |  | From | To | Factor
|  | Cost Adjustments | BYtoBY | 2005 | 2014 | 1.1867
|  | RDTEA | BYtoBY | 2014 | 2005 | 0.84268
|  |  |  | 2010-10-01 | 2011-10-01 | 2012-10-01 | 2013-10-01 | 2014-10-01 | 2015-10-01 | 2016-10-01 | 2017-10-01 | 2018-10-01 | 2019-10-01 | 2020-10-01 | 2021-10-01 | 2022-10-01 | 2023-10-01 | 2024-10-01 | 2025-10-01 | 2026-10-01 | 2027-10-01 | 2028-10-01 | 2029-10-01 | 2030-10-01 | 2031-10-01 | 2032-10-01 | 2033-10-01 | 2034-10-01
Phasing |  |  |  | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034 | Total
|  |  | Months | 2011-10-01: 7.1333; 2012-10-01: 12; 2013-10-01: 12; 2014-10-01: 12; 2015-10-01: 12; 2016-10-01: 12; 2017-10-01: 9.7667 | 76.9
|  |  | Percent Per Year | 2011-10-01: 0.06; 2012-10-01: 0.26; 2013-10-01: 0.29; 2014-10-01: 0.22; 2015-10-01: 0.12; 2016-10-01: 0.04; 2017-10-01: 0.01 | 1
Notes For Common Estimate Changes:
If the Milestone Schedule changes, Start/Finish Dates are altered in any way the Months per year and Percent Per Year annual values must be manually updated
1. Update the Months per year values
2. Change the percent per year to reflect the months change and any change to the annual expenditure rate
If the expenditure rate changes, default based on a front loaded Beta Curve the Percent Per Year annual values must be manually updated

## 1.3
POWER GENERATION PLANT
WBS Element: |  |  | 1.3
Training
WBS/CES Definition: |  | Training. Deliverable training services, devices, accessories, aids, equipment, and parts used to facilitate instruction through which personnel will learn to operate and maintain the system with maximum efficiency. Includes, for example: a. All effort associated with the design, development, and production of deliverable training equipment and its associated software as well as the execution of training services
Appropriations: |  | RDTEA
WBS Summary |  | $K
|  | Approp | Total | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034
Training |  | RDTEA | 958.9419 | 0 | 0 | 0 | 0 | 0 | 0 | 191.7884 | 767.1535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost Build Up
Assumptions |  | Training Period of Performance starts when Integration and Assembly Ends (26Jul2016).
Training Period of Performance End Date Estimated 26Jul2017.
Methodology
| 1 | Training Cost is a Factor of the Development Hardware Estimate
| 2 | Training Factor Most likely value is 3%
| 3 | Derive Phasing Method from front loaded Beta curve 60/40 with medium peakness
Inputs |  |  | Value | Cost Type | FY | Units | BY2014$K
|  | Training Cost | 958.9419 |  |  |  | 958.9419
|  | Training Factor of Hardware | 0.03
|  | Hardware Cost | 31964.7288 |  | 2014 | $K | 31964.7288
|  | Milestone Start Date | 2016-07-26
|  | Milestone Finish Date | 2017-07-26
|  | Calculated Duration in Months | 12
|  |  |  | From | To | Factor
|  | Cost Adjustments |  |  | 2014 | #N/A
|  | RDTEA |  | 2014 |  | #N/A
|  |  |  | 2010-10-01 | 2011-10-01 | 2012-10-01 | 2013-10-01 | 2014-10-01 | 2015-10-01 | 2016-10-01 | 2017-10-01 | 2018-10-01 | 2019-10-01 | 2020-10-01 | 2021-10-01 | 2022-10-01 | 2023-10-01 | 2024-10-01 | 2025-10-01 | 2026-10-01 | 2027-10-01 | 2028-10-01 | 2029-10-01 | 2030-10-01 | 2031-10-01 | 2032-10-01 | 2033-10-01 | 2034-10-01
Phasing |  |  |  | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034 | Total
|  |  | Months | 2016-10-01: 2.2333; 2017-10-01: 9.7667 | 12
|  |  | Percent Per Year | 2016-10-01: 0.2; 2017-10-01: 0.8 | 1
Notes For Common Estimate Changes:
If the Milestone Schedule changes, Start/Finish Dates are altered in any way the Months per year and Percent Per Year annual values must be manually updated
1. Update the Months per year values
2. Change the percent per year to reflect the months change and any change to the annual expenditure rate
If the expenditure rate changes, default based on a front loaded Beta Curve the Percent Per Year annual values must be manually updated

## 1.4
POWER GENERATION PLANT
WBS Element: |  |  | 1.4
Data
WBS/CES Definition: |  | Data. The deliverable data required to be listed on a contract data requirements list, DD Form 1423.
Appropriations: |  | RDTEA
WBS Summary |  | $K
|  | Approp | Total | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034
Data |  | RDTEA | 706.7475 | 0 | 42.4048 | 183.7543 | 204.9568 | 155.4844 | 84.8097 | 28.2699 | 7.0675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost Build Up
Assumptions |  | Data Period of Performance starts when HW Development Begins (01Mar2011).
Data Period of Performance End Date Estimated 26Jul2017.
Data has the same period of performance at SEPM.
Methodology
| 1 | Data Cost is a Factor of the Development Hardware + Software Development Estimate
| 2 | Data Factor Most likely value is 1%
| 3 | Derive Phasing Method from front loaded Beta curve 60/40 with medium peakness
Inputs |  |  | Value | Cost Type | FY | Units | BY2014$K
|  | Data Cost | 706.7475 |  |  |  | 706.7475
|  | Data Factor of HW + SW | 0.01
|  | Hardware Cost | 31964.7288 |  | 2014 | $K | 31964.7288
|  | Software Cost | 38710.0184 |  | 2014 | $K | 38710.0184
|  | Milestone Start Date | 2011-03-01
|  | Milestone Finish Date | 2017-07-26
|  | Calculated Duration in Months | 76.8333
|  |  |  | From | To | Factor
|  | Cost Adjustments |  |  | 2014 | #N/A
|  | RDTEA |  | 2014 |  | #N/A
|  |  |  | 2010-10-01 | 2011-10-01 | 2012-10-01 | 2013-10-01 | 2014-10-01 | 2015-10-01 | 2016-10-01 | 2017-10-01 | 2018-10-01 | 2019-10-01 | 2020-10-01 | 2021-10-01 | 2022-10-01 | 2023-10-01 | 2024-10-01 | 2025-10-01 | 2026-10-01 | 2027-10-01 | 2028-10-01 | 2029-10-01 | 2030-10-01 | 2031-10-01 | 2032-10-01 | 2033-10-01 | 2034-10-01
Phasing |  |  |  | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034 | Total
|  |  | Months | 2011-10-01: 7.1333; 2012-10-01: 12; 2013-10-01: 12; 2014-10-01: 12; 2015-10-01: 12; 2016-10-01: 12; 2017-10-01: 9.7667 | 76.9
|  |  | Percent Per Year | 2011-10-01: 0.06; 2012-10-01: 0.26; 2013-10-01: 0.29; 2014-10-01: 0.22; 2015-10-01: 0.12; 2016-10-01: 0.04; 2017-10-01: 0.01 | 1
Notes For Common Estimate Changes:
If the Milestone Schedule changes, Start/Finish Dates are altered in any way the Months per year and Percent Per Year annual values must be manually updated
1. Update the Months per year values
2. Change the percent per year to reflect the months change and any change to the annual expenditure rate
If the expenditure rate changes, default based on a front loaded Beta Curve the Percent Per Year annual values must be manually updated

## 1.5
POWER GENERATION PLANT
WBS Element: |  |  | 1.5
System Test and Evaluation (ST&E)
WBS/CES Definition: |  | System Test and Evaluation. The use of pilot, prototype, production, or specifically fabricated hardware/ software to obtain or validate engineering data on the performance of the system during the developmental phase (normally funded from RDT&E) of the program. It also includes all effort associated with the development of any specialized tools or data in support of the system level test program.
Appropriations: |  | RDTEA
WBS Summary |  | $K
|  | Approp | Total | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034
ST&E |  | RDTEA | 2665.7705 | 0 | 0 | 0 | 0 | 0 | 0 | 533.1541 | 2132.6164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost Build Up
Assumptions |  | ST&E Period of Performance starts when the Integration and Assembly is complete (26JUL2016).
ST&E Duration Estimate 12 months (End Date Estimated 26Jul2017).
Methodology
| 1 | Engineering Build Up of Total ST&E Cost = Labor Rate*Work Hours per Month * ST&E Duration * ST&E Staff Level
| 2 | Average ST&E Staff Labor Rate per Hour $195 Base Year 2005 $
| 3 | Hours per Person Month is 160
| 4 | Duration 12 Months
| 5 | 6 person Staff Level
| 6 | Derive Phasing Method from front loaded Beta curve 60/40 with medium peakness
Inputs |  |  | Value | Cost Type | FY | Units | BY2014$K
|  | Test Cost | 2665.7705 |  |  |  | 2665.7705
|  | Test Wrap Rate | 195 | BY | 2005 | $ | 0.2314
|  | Hours per Person Month | 160
|  | Staff Level for Test | 6
|  | Duration Months | 12
|  | Milestone Start Date | 2016-07-26
|  | Milestone Finish Date | 2017-07-26
|  | Calculated Duration in Months | 12
|  |  |  | From | To | Factor
|  | Cost Adjustments | BYtoBY | 2005 | 2014 | 1.1867
|  | RDTEA | BYtoBY | 2014 | 2005 | 0.84268
|  |  |  | 2010-10-01 | 2011-10-01 | 2012-10-01 | 2013-10-01 | 2014-10-01 | 2015-10-01 | 2016-10-01 | 2017-10-01 | 2018-10-01 | 2019-10-01 | 2020-10-01 | 2021-10-01 | 2022-10-01 | 2023-10-01 | 2024-10-01 | 2025-10-01 | 2026-10-01 | 2027-10-01 | 2028-10-01 | 2029-10-01 | 2030-10-01 | 2031-10-01 | 2032-10-01 | 2033-10-01 | 2034-10-01
Phasing |  |  |  | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034 | Total
|  |  | Months | 2016-10-01: 2.2333; 2017-10-01: 9.7667 | 12
|  |  | Percent Per Year | 2016-10-01: 0.2; 2017-10-01: 0.8 | 1
Notes For Common Estimate Changes:
If the Milestone Schedule changes, Start/Finish Dates are altered in any way the Months per year and Percent Per Year annual values must be manually updated
1. Update the Months per year values
2. Change the percent per year to reflect the months change and any change to the annual expenditure rate
If the expenditure rate changes, default based on a front loaded Beta Curve the Percent Per Year annual values must be manually updated

## 2.1.1.1
POWER GENERATION PLANT
WBS Element: |  |  | 2.1.1.1
Structure
WBS/CES Definition: |  | Prime Mission Product Subsystem Hardware Structure. The hardware structure and associated resource components of the power generation plant.
Appropriations: |  | OPA
WBS Summary |  | $K
|  | Approp | Total | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034
Structure |  | OPA | 127476.0531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18210.8647 | 18210.8647 | 27316.2971 | 27316.2971 | 36421.7294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost Build Up
Assumptions |  | Based on Procurement Buy Quantity from 2018-2022
Methodology
| 1 | Production Structure Unit Cost Based on Average Unit Cost of Development Structure
| 2 | Production Factor Applied to the Unit Cost = 77.6%
| 3 | Based on 10 Development Quantities
| 4 | Phased according to the Buy Quantity Schedule
Inputs |  |  | Value | Cost Type | FY | Units | BY2014$K
|  | Production Structure Unit Cost | 1821.0865 |  |  |  | 1821.0865
|  | Total Development Structure | 23467.6092 |  | 2014 | $K | 23467.6092
|  | Number of Development Units | 10
|  | Production Factor | 0.776
|  |  |  | From | To | Factor
|  | Cost Adjustments |  |  | 2014 | #N/A
|  | OPA |  | 2014 |  | #N/A
Phasing |  |  |  | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034 | Total
|  |  | Buy Qty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 15 | 15 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70
|  |  | Annual Structure Calculation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18210.8647 | 18210.8647 | 27316.2971 | 27316.2971 | 36421.7294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127476.0531
Notes For Common Estimate Changes:
If the Structure Factor Changes: i.e. New Factor
1. Enter the new factor for Production Factor

## 2.1.1.2
POWER GENERATION PLANT
WBS Element: |  |  | 2.1.1.2
Cables, Conduits, and Connectors (CCC)
WBS/CES Definition: |  | Prime Mission Product Subsystem Hardware Cables, Conduits and Connectors. The hardware cables conduits and connectors and associated resource components of the power generation plant.
Appropriations: |  | OPA
WBS Summary |  | $K
|  | Approp | Total | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034
CCC |  | OPA | 11505.3169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1643.6167 | 1643.6167 | 2465.425 | 2465.425 | 3287.2334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost Build Up
Assumptions |  | Based on Procurement Buy Quantity from 2018-2022
Methodology
| 1 | Production CCC Unit Cost Based on Average Unit Cost of Development CCC
| 2 | Production Factor Applied to the Unit Cost = 77.6%
| 3 | Based on 10 Development Quantities
| 4 | Phased according to the Buy Quantity Schedule
Inputs |  |  | Value | Cost Type | FY | Units | BY2014$K
|  | Production CCC Unit Cost | 164.3617 |  |  |  | 164.3617
|  | Total Development CCC | 2118.0628 |  | 2014 | $K | 2118.0628
|  | Number of Development Units | 10
|  | Production Factor | 0.776
|  |  |  | From | To | Factor
|  | Cost Adjustments |  |  | 2014 | #N/A
|  | OPA |  | 2014 |  | #N/A
Phasing |  |  |  | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034 | Total
|  |  | Buy Qty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 15 | 15 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70
|  |  | Annual CCC Calculation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1643.6167 | 1643.6167 | 2465.425 | 2465.425 | 3287.2334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11505.3169
Notes For Common Estimate Changes:
If the CCC Factor Changes: i.e. New Factor
1. Enter the new factor for Production Factor

## 2.1.1.3
POWER GENERATION PLANT
WBS Element: |  |  | 2.1.1.3
Engine
WBS/CES Definition: |  | Engine The means for generating and delivering power in the required quantities and rates to the plant system.
Appropriations: |  | OPA
WBS Summary |  | $K
|  | Approp | Total | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034
Engine |  | OPA | 35080.0703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5712.241 | 5215.3523 | 7484.7541 | 7246.7955 | 9420.9274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost Build Up
Assumptions |  | Based on Procurement Buy Quantity from 2018-2022
Methodology
| 1 | Learning Curve applied to Engine Cost based on multi variable equation.
| 2 | Same Engine CER used in RD - CER inflated with RDTEA inflation factor.
| 3 | Engine T1 Cost=370.4 * kHpPerTon ^ 0.8747 * 0.878 ^ Oil in Base Year 2010 $K
| 4 | kHpPerTon = k Horse Power per Ton = 2
| 5 | Oil is a Dummy variable Oil=1, Coal=0. Default Technical Baseline is Oil Engine.
| 6 | Engine Learning Slope = 95%
| 7 | Start Production Unit Cost based on 0 Prior Quantities
| 8 | Phased according to the Buy Quantity Schedule
| 9 | RDTEA used to convert Engine T1 Cost to BY2014 to be consistent with Development estimate
Inputs |  |  | Value | Cost Type | FY | Units | BY2014$K
|  | Engine T1 Cost | 596.316 | BY | 2010 | $K | 637.9057
|  | Engine Horse Power per Ton | 2
|  | Engine Type Oil=1, Coal=0 | 1
|  | Learning Slope | 0.95
|  | Rate Slope | 1
|  |  |  | From | To | Factor
|  | Cost Adjustments | BYtoBY | 2010 | 2014 | 1.0697
|  | RDTEA | BYtoBY | 2014 | 2010 | 0.9348
Phasing |  |  |  | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034 | Total
|  |  | Buy Qty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 15 | 15 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70
|  |  | Phased Learning | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5712.241 | 5215.3523 | 7484.7541 | 7246.7955 | 9420.9274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35080.0703
Learning Curve Calculations
|  |  | Cumulative Unit Calculation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 35 | 50 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70
|  |  | Prior Quantity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 35 | 50 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70
|  |  | Unit Slope Exponent | -0.074001
|  |  | Rate Slope Exponent | 0
|  |  | Learning Curve Factor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.9547 | 8.1757 | 11.7333 | 11.3603 | 14.7685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Subsequent Years Learning Factor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.1757 | 11.7333 | 11.3603 | 14.7685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | First Year Learning Factor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.9547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Subsequent Years Learning Excel Equation | IF(OR(PriorQty=0,PriorQty=PRODQTOT),0,((CumQty^(UnitSlpExp+1)-PriorQty^(UnitSlpExp+1))/(UnitSlpExp+1)+(CumQty^UnitSlpExp-PriorQty^UnitSlpExp)/2+(CumQty^(UnitSlpExp-1)-PriorQty^(UnitSlpExp-1))*UnitSlpExp/12)*L42^RateSlpExp)
Notes For Common Estimate Changes:
The same Engine Unit Cost CER is used in the Development and Production portions of the estimate. If the CER used for 1.1.1.3 is changed, the CER used here in 2.1.1.3 should be changed as well
Learning Curve Set up for Basic Unit Theory with Rate Adjustment calculated based on T1 unit cost: method will accommodate schedule shift
To use this spreadsheet implementation with a different Analogous CER: The CER must equal a T1 result: Unit Number X, Cumulative Average and Lot Total CERs must be converted to the T1 result before loading into the Engine T1 Cost
This spreadsheet is set up to accommodate rate adjusted learning curves: the default is no rate adjustment, Rate Slope=1 to calculate with rate adjust the Rate Slope
Broken learning or cost improvement shifts of any kind are not modeled by this approach: Major changes to the learning curve factor equation would be required
This spreadsheet is designed to apply this learning curve to only one WBS element in the workbook, sharing this curve with other WBS Elements requires major equation modification

## 2.1.2
POWER GENERATION PLANT
WBS Element: |  |  | 2.1.2: 2.12.1 and 2.1.2.2
Procurement Software: Site Activation and Upgrade
WBS/CES Definition: |  | Prime Mission Product Subsystem Software 1…n (Specify). The software and associated resource components of the power generation Plant. Site Activation: This element includes the costs associated with shipping costs to the site, site survey, site preparation, equipment installation, equipment integration, test and checkout to allow implementation of the AIS solution. This should cover only those efforts that are incurred at the implementation site. Any effort related to re-design of the solution once implementation has begun should be captured here. Software Upgrade: The labor, material, and overhead costs incurred after deployment by depot-level maintenance activities, government software centers, laboratories, or contractors for supporting the update, maintenance and modification, integration, and configuration management of software. Includes operational, maintenance, and diagnostic software programs for the primary system, major subsystems, support equipment, and simulators and other training equipment. Excludes the costs of new development or major redesigns that provide new capabilities. If the costs of new development or major redesigns that provide new capabilities cannot be isolated, these costs will be considered as part of software maintenance and should be so noted in the estimate documentation.
Appropriations: |  | OPA
WBS Summary |  | $K
|  | Approp | Total | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034
Software |  | OPA | 19355.0092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5806.5028 | 0 | 0 | 13548.5064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software Activation |  | OPA | 5806.5028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5806.5028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software Upgrade |  | OPA | 13548.5064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13548.5064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost Build Up
Assumptions |  | Site Activation occurs the first year Engines are Procured: tied to Engine Procurement Buy Quantities
Upgrade occurs one year before the last year Engines are Procured: tied to Engine Procurement Buy Quantities
Methodology
| 1 | Activation Cost is a Factor of the Total Development Software (SW) Cost
| 2 | Activation Factor value is 15% of the total
| 3 | Upgrade Cost is a Factor of the Total Development Software (SW) Cost
| 4 | Upgrade Factor value is 35% of the total
Inputs |  |  | Value | Cost Type | FY | Units | BY2014$K
|  | Total Software Development | 38710.0184 | BY | 2014 | $K | 38710.0184
|  | Activation Factor of Software | 0.15
|  | Upgrade Factor of Software | 0.35
|  | Start Year For Activation Cost | 2018 | MIN('Ground & Assumptions'!D23:AB23)
|  | Start Year For Upgrade Cost | 2021 | MAX('Ground & Assumptions'!D23:AB23)-1
|  |  |  | From | To | Factor
|  | Cost Adjustments |  |  | 2014 | #N/A
|  | OPA |  | 2014 |  | #N/A
Phasing |  |  |  | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034 | Total
|  |  | Activation Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5806.5028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5806.5028
|  |  | Upgrade Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13548.5064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13548.5064
|  |  | Activation Cost Equation | IF(VALUE(RIGHT(E42,4))=$D$35,$D$32*$D$33,0)
|  |  | Upgrade Cost Equation | IF(VALUE(RIGHT(E42,4))=$D$36,$D$32*$D$34,0)
Notes For Common Estimate Changes:
If the Activation Strategy Changes: Start Activation one year prior to Engine Delivery
1. Modify the Start Year For Activation Cost Equation: include -1
If the Upgrade Strategy Changes: Change year of upgrade
1. Modify the Start Year For Upgrade Cost Equation: include + or - years

## 2.1.3
POWER GENERATION PLANT
WBS Element: |  |  | 2.1.3
Integration
WBS/CES Definition: |  | Integration, Assembly, Test and Checkout. In those instances in which an integration, assembly, test, and checkout element is used, this element includes all effort of technical and functional activities associated with the design, development, and production of mating surfaces, structures, equipment, parts, materials, and software required to assemble the Level 3 equipment (hardware/software) elements into a Level 2 mission equipment (hardware/ software) as a whole and not directly part of any other individual Level 3 element.
Appropriations: |  | OPA
WBS Summary |  | $K
|  | Approp | Total | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034
Integration |  | OPA | 26109.216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3835.0084 | 3760.4751 | 5589.9714 | 5554.2777 | 7369.4835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost Build Up
Assumptions |  | Integration occurs the same years as Hardware Production.
Methodology
| 1 | Integration Cost is a Factor of the Production Hardware Estimate
| 2 | Integration Factor Most likely value is 15%
Inputs |  |  | Value | Cost Type | FY | Units | BY2014$K
0
|  | Integration Factor of Hardware | 0.15
|  |  |  | From | To | Factor
|  | Cost Adjustments |  |  | 2014 | #N/A
|  | OPA |  | 2014 |  | #N/A
Phasing |  |  |  | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034 | Total
|  |  | Hardware Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25566.7224 | 25069.8337 | 37266.4763 | 37028.5177 | 49129.8902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174061.4403
|  |  | Integration Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3835.0084 | 3760.4751 | 5589.9714 | 5554.2777 | 7369.4835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26109.216
Notes For Common Estimate Changes:
If the Integration Factor Changes: i.e. New Factor
1. Enter the new factor for Integration Factor of PMP

## 2.2
POWER GENERATION PLANT
WBS Element: |  |  | 2.2
SEPM
WBS/CES Definition: |  | System Engineering. The technical and management efforts of directing and controlling a totally integrated engineering effort of a system or program. Includes, for example: a. Effort to define the system and the integrated planning and control of the technical program efforts of design engineering, specialty engineering, production engineering, and integrated test planning b. Effort associated with developing the Systems Engineering Management Plan (SEMP) c. Effort to transform an operational need or statement of deficiency into a description of system requirements and a preferred system configuration d. Technical planning and control effort for planning, monitoring, measuring, evaluating, directing, and re-planning the management of the technical program e. All programs, where applicable; value engineering, configuration management, Human Systems Integration (Human factors engineering; Personnel; Habitability; Manpower; Training; Environment, Safety and Occupational Health; Survivability), vulnerability, maintainability, reliability, standardization, system analysis, logistic support analysis, etc. f. Technical baseline management and event based technical reviews with independent subject matter expertise participation g. Cross product IPT integration h. Survivability/vulnerability analysis i. System of Systems (SoS) and System Level Architecting, modeling and simulation, verification and validation and external interface definition and management j. For sea systems; the expanded Ship Work Breakdown Structure (ESWBS), configuration management (812 and 813), human factors (892), standardization (893), value engineering (894), and reliability and maintainability (895) elements Excludes, for example: a. Actual design engineering and the production engineering directly related to the WBS element with which it is associated Program Management. The business and administrative planning, organizing, directing, coordinating, controlling, and approval actions designated to accomplish overall program objectives, which are not associated with specific hardware elements and are not included in systems engineering. Includes, for example: a. Cost, schedule, performance measurement management, warranty administration, contract management, data management, vendor liaison, subcontract management, etc. b. Support element management, defined as the logistics tasks management effort and technical control, and the business management of the support elements. The logistics management function encompasses the support evaluation and supportability assurance required to produce an affordable and supportable defense materiel system. c. Planning and management of all the functions of logistics. Examples are: 1. maintenance support planning and support facilities planning; other support requirements determination; support equipment requirements determination; supply support; packaging, handling, storage, and transportation; provisioning requirements determination and planning; training system requirements determination; computer resource determination; organizational, intermediate, and depot maintenance determination management; and data management d. For sea systems; the Expanded Ship Work Breakdown Structure (ESWBS), project management (897); data management (896); and supply support (8643) elements. Examples of Systems Engineering efforts are: a. System requirement and architecture definition, overall system design and margin management, design integrity analysis, system optimization, system/cost effectiveness analysis, and intra-system and inter-system compatibility assurance, etc.; the integration and balancing of reliability, maintainability, producibility, safety engineering, human health, environmental protection, manpower, personnel, training, and survivability; security requirements, quality assurance program, value engineering, preparation of equipment and component performance specifications, design of test and demonstration plans; determination of software development or software test facility/ environment requirements. Assessments of system effectiveness, life cycle costs, schedule, risk and evolutionary growth for each tradeoff following each iteration of the systems engineering process, and develop the associated required systems engineering products. b. Requirements Management- ensures requirements traceability and version control for all program requirements starting with the Capabilities Development Document (CDD) and Capabilities Production Document (CPD) to the system specification and lower level Configuration Item (CI) specifications. c. Interface Management - ensures interface compatibility of external and internal interfaces and coordination of changes between associate contractors and Integrated Product Teams (IPTs). d. Preparation of the Systems Engineering Management Plan (SEMP), specification tree, program risk analysis, system planning, decision control process, technical performance measurement, technical reviews, subcontractor and vendor reviews, work authorization, and technical documentation control. e. Reliability engineering—the engineering process and series of tasks required to examine the probability of a device or system performing its mission adequately for the period of time intended under the operating conditions expected to be encountered. f. Maintainability engineering—the engineering process and series of tasks required to measure the ability of an item or system to be retained in or restored to a specified condition of readiness, skill levels, etc., using prescribed procedures and resources at specific levels of maintenance and repair. g. Human Systems Integration—the engineering process and the series of tasks required to define, as a comprehensive technical and engineering effort involving the integration of the human operator and maintainer requirements while attempting to minimize lifecycle cost and maximize total system performance. h. Supportability analyses—an integral part of the systems engineering process beginning at program initiation and continuing throughout program development. Supportability analyses form the basis for related design requirements included in the system specification and for subsequent decisions concerning how to most cost effectively support the system and its infrastructure over its entire life cycle. i. Configuration Management – supports the identification and management of the technical baselines (functional baseline, allocated baseline, initial product baseline, final product baseline). j. Data Management – identifies the essential technical data necessary for the definition and sustainment of the system reflected in the respective technical baselines.
Appropriations: |  | OPA
WBS Summary |  | $K
|  | Approp | Total | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034
SEPM |  | OPA | 81224.4962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13027.0464 | 10667.2142 | 15856.8857 | 20768.5817 | 20904.7683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost Build Up
Assumptions |  | SEPM occurs the same years as Manufacturing Production.
Methodology
| 1 | SEPM Cost is a Factor of the Production Manufacturing (PMP) Estimate
| 2 | SEPM Factor Most likely value is 37%
Inputs |  |  | Value | Cost Type | FY | Units | BY2014$K
0
|  | SEPM Factor of PMP | 0.37
|  |  |  | From | To | Factor
|  | Cost Adjustments |  |  | 2014 | #N/A
|  | OPA |  | 2014 |  | #N/A
Phasing |  |  |  | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034 | Total
|  |  | Manufacturing Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35208.2335 | 28830.3088 | 42856.4477 | 56131.3018 | 56499.3738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 219525.6655
|  |  | SEPM Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13027.0464 | 10667.2142 | 15856.8857 | 20768.5817 | 20904.7683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81224.4962
|  |  | SEPM Equation | E62*$D$54 | F62*$D$54 | G62*$D$54 | H62*$D$54 | I62*$D$54 | J62*$D$54 | K62*$D$55 | L62*$D$54 | M62*$D$54 | N62*$D$54 | O62*$D$54 | P62*$D$54 | Q62*$D$54 | R62*$D$54 | S62*$D$54 | T62*$D$54 | U62*$D$54 | V62*$D$54 | W62*$D$54 | X62*$D$54 | Y62*$D$54 | Z62*$D$54 | AA62*$D$54 | AB62*$D$54 | AC62*$D$54 | SUM(E37:AC37)
Notes For Common Estimate Changes:
If the SEPM Factor Changes: i.e. New Factor
1. Enter the new factor for SEPM Factor of PMP

## 2.3
POWER GENERATION PLANT
WBS Element: |  |  | 2.3
Other Procurement
WBS/CES Definition: |  | Other This element includes the costs of any other procurement-funded costs for system engineering and technical control as well as the business management of the system/program. It encompasses the overall planning, direction, and control of the definition, development, and production of the system/program, including functions of logistics engineering and ILS management, e.g., maintenance support, facilities, personnel, training, testing, and activation of a system. System engineering/ management effort that can be associated specifically with the individual hardware elements is excluded. This element also includes any procurement reimbursement to MP for military personnel costs associated with project management not in the PM's office.
Appropriations: |  | OPA
WBS Summary |  | $K
|  | Approp | Total | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034
Other |  | OPA | 4733.6294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1071.407 | 1050.399 | 943.986 | 925.4765 | 742.3609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost Build Up
Assumptions |  | Other is a five year Throughput the same years as Manufacturing Production.
Methodology
| 1 | Other is a Then Year Dollar Throughput
Inputs |  |  | Value | Cost Type | FY | Units | BY2014$K
0
|  |  |  | From | To | Factor
|  | Cost Adjustments | TY to BY | 2018 | 2014 | 0.89284
|  | OPA | TY to BY | 2019 | 2014 | 0.87533
|  |  | TY to BY | 2020 | 2014 | 0.85817
|  |  | TY to BY | 2021 | 2014 | 0.84134
|  |  | TY to BY | 2022 | 2014 | 0.82485
Phasing |  |  |  | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034 | Total
|  |  | Other Cost TY Throughput | [8 empty] | 1200 | 1200 | 1100 | 1100 | 900 | [12 empty] | 5500
|  |  | Other Cost BY | [8 empty] | 1071.407 | 1050.399 | 943.986 | 925.4765 | 742.3609 | [12 empty] | 4733.6294
|  |  | Other Cost Equation | [8 empty] | G32*M39 | G33*N39 | G34*O39 | G35*P39 | G36*Q39 | [12 empty] | sum(E40:AC40)
Notes For Common Estimate Changes:
If the fiscal years of Other Cost TY Dollars Throughput changes: i.e. schedule slip
1. Enter dollar values in Other Cost TY Throughput table: ensure dollars are expressed in TY dollars
2. The Cost Adjustments Factor Table must be updated: Add rows above or below table, input new From years and fill in Factor equation
3. Fill Other Cost BY table equations to new fiscal years

## 3.1
POWER GENERATION PLANT
WBS Element: |  |  | 3.1
Unit Level Maintenance
WBS/CES Definition: |  | Unit-Level Maintenance - This element includes the cost of fuel and energy resources; operations, maintenance, and support materials consumed at the unit level; stock fund reimbursements for depot-level reparables; operational munitions expended in training; transportation in support of deployed unit training; temporary additional duty/temporary duty (TAD/TDY) pay; and other unit-level consumption costs, such as purchased services for equipment leases and service contracts. Also included here is the cost for painting, corrosion control, and tracking/disposal of HAZMATs used to operate, maintain, and clean the system.
Appropriations: |  | OMA
WBS Summary |  | $K
|  | Approp | Total | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034
Unit Level Maintenance |  | OMA | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 600 | 1050 | 1500 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 1800 | 1500 | 1050 | 600 | 0 | 0
Cost Build Up
Assumptions |  | Based on Fielded Quantity from 2019-2032
Methodology
| 1 | Unit Level Maintenance Cost Based on Average of Contract RFQ Response
| 2 | Unit Cost for Annual Maintenance is $30K in BY2014
| 3 | Based on Fielded Quantities with 10 year Operational Life
| 4 | Phased according to the Fielded Quantity Schedule
Inputs |  |  | Value | Cost Type | FY | Units | BY2014$K
|  | Annual Unit Level Maintenance | 30 | BY | 2014 | $K | 30
|  |  |  | From | To | Factor
|  | Cost Adjustments | BYtoBY | 2014 | 2014 | 1
|  | OMA | BYtoBY | 2014 | 2014 | 1
Phasing |  |  |  | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034 | Total
|  |  | Fielded Qty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 35 | 50 | 70 | 70 | 70 | 70 | 70 | 70 | 60 | 50 | 35 | 20 | 0 | 0 | 700
|  |  | Unit Level Maintenance Calculation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 600 | 1050 | 1500 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 1800 | 1500 | 1050 | 600 | 0 | 0 | 21000
Notes For Common Estimate Changes:
If the Unit Level Maintenance Changes: i.e. New Value
1. Enter the new cost for unit level maintenance with its cost properties
If the Operational Life of the System Changes
1. Go to Ground Rules and Assumptions and update the equations for Fielded Quantity Calculations

## 3.2.1
POWER GENERATION PLANT
WBS Element: |  |  | 3.2.1
Software Maintenance Support
WBS/CES Definition: |  | Software Maintenance Support - This element includes the labor, material, and overhead costs incurred after deployment by depot-level maintenance activities, government software centers, laboratories, or contractors for supporting the update, maintenance and modification, integration, and configuration management of software. It also includes operational maintenance, diagnostic software programs for the primary system, support equipment, training equipment, and operating and maintaining the associated computer and peripheral equipment in the software maintenance activity.
Appropriations: |  | OMA
WBS Summary |  | $K
|  | Approp | Total | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034
Software Maintenance Support |  | OMA | 50323.0239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3871.0018 | 3871.0018 | 3871.0018 | 3871.0018 | 3871.0018 | 3871.0018 | 3871.0018 | 3871.0018 | 3871.0018 | 3871.0018 | 3871.0018 | 3871.0018 | 3871.0018 | 0 | 0 | 0
Cost Build Up
Assumptions |  | Software Maintenance Support occurs the first year Engines are Fielded: tied to Engine Fielded Quantities: Support stops a year before the last units field
Methodology
| 1 | Software Maintenance Cost is a Factor of the Total Development Software (SW) Cost
| 2 | Annual Support Factor value is 10% of the total
| 3 | No Cost the last year of fielded quantities
| 4 | Phased according to the Fielded Quantity Schedule
Inputs |  |  | Value | Cost Type | FY | Units | BY2014$K
|  | Total Software Development | 38710.0184 | BY | 2014 | $K | 38710.0184
|  | Maintenance Factor of Software | 0.1
|  | Start Year For Maintenance Cost | 2019 | MIN('Ground & Assumptions'!D24:TAB24)
|  | Finish Year For Maintenance Cost | 2031 | MAX('Ground & Assumptions'!D24:AB24)-1
|  |  |  | From | To | Factor
|  | Cost Adjustments | BYtoBY | 2014 | 2014 | 1
|  | OMA | BYtoBY | 2014 | 2014 | 1
Phasing |  |  |  | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034 | Total
|  |  | Fielded Qty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 35 | 50 | 70 | 70 | 70 | 70 | 70 | 70 | 60 | 50 | 35 | 20 | 0 | 0 | 700
|  |  | Unit Level Maintenance Calculation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3871.0018 | 3871.0018 | 3871.0018 | 3871.0018 | 3871.0018 | 3871.0018 | 3871.0018 | 3871.0018 | 3871.0018 | 3871.0018 | 3871.0018 | 3871.0018 | 3871.0018 | 0 | 0 | 0 | 50323.0239
IF(AND(E40>0,VALUE(RIGHT(E39,4))<=$D$33),$H$30*$D$31,0)
Notes For Common Estimate Changes:
If the Annual Support Factor Changes: i.e. New Value
1. Enter the new factor
If the Operational Life of the System Changes
1. Go to Ground Rules and Assumptions and update the equations for Fielded Quantity Calculations

## 3.2.2
POWER GENERATION PLANT
WBS Element: |  |  | 3.2.2
Software Maintenance Upgrade
WBS/CES Definition: |  | Software Maintenance Upgrade - Included in this element are the labor, material, and overhead costs incurred in providing continued systems engineering and program management oversight to upgrade the software, to maintain operational reliability, to approve design changes, and to ensure system conformance with established specifications and standards, as well as ESH compliance (safety and health, HAZMAT reduction, pollution prevention). Costs in this category may include, but not limited to, government and/or contract engineering services, technical advice, and training for component or system installation, operation, maintenance and support.
Appropriations: |  | OMA
WBS Summary |  | $K
|  | Approp | Total | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034
Software Maintenance Upgrade |  | OMA | 31471.245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11613.0055 | 0 | 0 | 10451.705 | 0 | 0 | 9406.5345 | 0 | 0 | 0 | 0
Cost Build Up
Assumptions |  | Software Maintenance Upgrade occurs every three years from the year of the first upgrade delivered in procurement: there are three upgrades planned for the life of OM
Methodology
| 1 | The initial Software Upgrade Cost is a Factor of the Total Development Software (SW) Cost
| 2 | First Upgrade Factor is 30%
| 3 | Subsequent upgrade factors are 90% of the previous factor
| 4 | The number of years between software upgrades is 3
| 5 | The total number of upgrades for the System is 3
| 6 | The first year of Software Maintenance Upgrade is 3 years after the last Procurement Software Upgrade
Inputs |  |  | Value | Cost Type | FY | Units | BY2014$K
|  | Total Software Development | 38710.0184 | BY | 2014 | $K | 38710.0184
|  | First Maintenance Factor of SW | 0.3
|  | Subsequent Factor Multiplier | 0.9
|  | Second Maintenance Factor of SW | 0.27
|  | Third Maintenance Factor of SW | 0.243
|  | # of Years between SW Upgrades | 3
|  | Total # of Upgrades for the Sys | 3
|  | First Year of SW Maint Upgrade | 2024
|  |  |  | From | To | Factor
|  | Cost Adjustments | BYtoBY | 2014 | 2014 | 1
|  | OMA | BYtoBY | 2014 | 2014 | 1
Phasing |  |  |  | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | FY 2023 | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | FY 2029 | FY 2030 | FY 2031 | FY 2032 | FY 2033 | FY 2034 | Total
|  |  | Upgrade Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11613.0055 | 0 | 0 | 10451.705 | 0 | 0 | 9406.5345 | 0 | 0 | 0 | 0 | 31471.245
IF(VALUE(RIGHT(E45,4))=$D$39,$D$32*$D$33,IF(VALUE(RIGHT(E45,4))=$D$39+$D$37,$D$32*$D$35,IF(VALUE(RIGHT(E45,4))=$D$39+$D$37+$D$37,$D$32*$D$36,0)))
Notes For Common Estimate Changes:
If the Upgrade Cost Factor Changes: i.e. New Value
1. Enter the new factor
If the number of years between Software Upgrade Changes
1. Change the value for the number of years in cell D33
If the total number of upgrades for the system changes
1. The nested if equation in the Upgrade Schedule must be modified
2. Additional Maintenance Factors maybe required
If the upgrade cost factor is constant
1. Set the Subsequent Factor Multiplier to 1

## Inflation Tables
Year | RAW | WTD | RAW | WTD | RAW | WTD
| Code: | 2035 | Code: | 2040 | Code: | 2020
| Term: | OPA | Term: | RDTEA | Term: | OMA
| Database: | System | Database: | System | Database: | System
| Source: | OSD Inflation Indices for the Army | Source: | OSD Inflation Indices for the Army | Source: | OSD Inflation Indices for the Army
| RevDate: | 2014-02-17 | RevDate: | 2014-02-17 | RevDate: | 2014-02-17
2003 | 0.80366 | 0.82458 | 0.80366 | 0.81944 | 0.80366 | 0.81935
2004 | 0.81973 | 0.84455 | 0.81973 | 0.83897 | 0.81973 | 0.83557
2005 | 0.84268 | 0.86853 | 0.84268 | 0.86316 | 0.84268 | 0.85994
2006 | 0.86881 | 0.89167 | 0.86881 | 0.8872 | 0.86881 | 0.88749
2007 | 0.89226 | 0.91317 | 0.89226 | 0.9085 | 0.89226 | 0.90832
2008 | 0.91368 | 0.9285 | 0.91368 | 0.9258 | 0.91368 | 0.92559
2009 | 0.92738 | 0.94083 | 0.92738 | 0.93766 | 0.92738 | 0.93502
2010 | 0.9348 | 0.95817 | 0.9348 | 0.95196 | 0.9348 | 0.94875
2011 | 0.9535 | 0.97541 | 0.9535 | 0.97078 | 0.9535 | 0.96953
2012 | 0.97066 | 0.9907 | 0.97066 | 0.98643 | 0.97066 | 0.98362
2013 | 0.98522 | 1.0149 | 0.98522 | 1.0048 | 0.98522 | 0.99756
2014 | 1 | 1.0371 | 1 | 1.0312 | 1 | 1.0184
2015 | 1.017 | 1.0555 | 1.017 | 1.0537 | 1.017 | 1.0336
2016 | 1.0363 | 1.0765 | 1.0363 | 1.0747 | 1.0363 | 1.0539
2017 | 1.057 | 1.0981 | 1.057 | 1.0962 | 1.057 | 1.075
2018 | 1.0782 | 1.12 | 1.0782 | 1.1181 | 1.0782 | 1.0965
2019 | 1.0998 | 1.1424 | 1.0998 | 1.1405 | 1.0998 | 1.1184
2020 | 1.1217 | 1.1653 | 1.1217 | 1.1633 | 1.1217 | 1.1408
2021 | 1.1442 | 1.1886 | 1.1442 | 1.1866 | 1.1442 | 1.1636
2022 | 1.1671 | 1.2123 | 1.1671 | 1.2103 | 1.1671 | 1.1869
2023 | 1.1904 | 1.2366 | 1.1904 | 1.2345 | 1.1904 | 1.2106
2024 | 1.2142 | 1.2613 | 1.2142 | 1.2592 | 1.2142 | 1.2348
2025 | 1.2385 | 1.2866 | 1.2385 | 1.2844 | 1.2385 | 1.2595
2026 | 1.2633 | 1.3123 | 1.2633 | 1.3101 | 1.2633 | 1.2847
2027 | 1.2885 | 1.3385 | 1.2885 | 1.3363 | 1.2885 | 1.3104
2028 | 1.3143 | 1.3653 | 1.3143 | 1.363 | 1.3143 | 1.3366
2029 | 1.3406 | 1.3926 | 1.3406 | 1.3902 | 1.3406 | 1.3633
2030 | 1.3674 | 1.4205 | 1.3674 | 1.418 | 1.3674 | 1.3906
2031 | 1.3948 | 1.4489 | 1.3948 | 1.4464 | 1.3948 | 1.4184
2032 | 1.4226 | 1.4778 | 1.4226 | 1.4753 | 1.4226 | 1.4468
2033 | 1.4511 | 1.5074 | 1.4511 | 1.5048 | 1.4511 | 1.4757
2034 | 1.4801 | 1.5376 | 1.4801 | 1.5349 | 1.4801 | 1.5052
2035 | 1.5097 | 1.5683 | 1.5097 | 1.5656 | 1.5097 | 1.5353
2036 | 1.5399 | 1.5997 | 1.5399 | 1.5969 | 1.5399 | 1.5661